GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

ROADS AUTHORITY

BIDDING DOCUMENT

FOR THE

PROCUREMENT OF WORKS

BY

INTERNATIONAL COMPETITIVE BIDDING

| Subject of Procurement | Completion of the Upgrading of Chitipa – Ilomba (T301/D002) Road in Chitipa District |
| --- | --- |
| Procurement Reference Number | RA/DEV/CP/2022-23/01B |
| Procurement Method | International Competitive Bidding |
| Date of Issue | 14th May 2026 |

TABLE OF CONTENTS

Section I. Instructions to Bidders	3

Section 2.  Bid Data Sheet	27

Section 3. Evaluation and Qualification Criteria	29

Section 4. Bidding Forms	34

Section 5. Eligible Countries	71

Section 6. Corruption and Fraud	72

Section 7. Schedule of Requirements	75

Section 8. General Conditions of Contract	85

Section 9A Contract Data	109

Section 9B. Special Conditions of Contract	114

Section 10. Contract Forms	118

# SECTION I. INSTRUCTIONS TO BIDDERS

| SECTION I. INSTRUCTIONS TO BIDDERS |  |  |  |
| --- | --- | --- | --- |
| GENERAL |  |  |  |
| SCOPE OF BID |  |  |  |
| The Procuring and Disposing Entity as indicated in the Bid Data Sheet (BDS), invites Bids for the construction of Works, as described in Section 7, Schedule of Requirements. These Instructions to Bidders shall be read in conjunction with the BDS. The subject of procurement, the procurement reference number, and number of lots of this Bidding Document are provided in the BDS. The Bidding Document is issued under the procurement method indicated in the BDS In these Bidding Documents— “day” means calendar day; “in writing” means communicated in written form with proof of receipt; and if the context so requires, singular means plural and vice versa. The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the SCC. |  |  |  |
| SOURCE OF FUNDS The Procuring and Disposing Entity indicated in the BDS has an approved budget from public funds towards the cost of the procurement and intends to use these funds to cover for eligible payments under the Contract. Payments will be made directly by the Procuring and Disposing Entity and will be subject in all respects to the terms and conditions of the resulting Contract placed by the Procuring and Disposing Entity. |  |  |  |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in the Anti-Corruption legal framework in Malawi. In line with the existing Anti-Corruption legal framework, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the Bidding documents as part of the qualification criteria... |
| ELIGIBLE BIDDERS |  |  |  |
| A Bidder may be a natural person, a legal person, government-owned entity or any combination of them with a formal intent to enter into an agreement or under an existing agreement in the form of a joint venture, consortium, or association. In the case of a joint venture, consortium, or association, unless otherwise specified in the BDS, all parties shall be jointly and severally liable. A foreign Bidder shall enter a joint venture or sub-contracting arrangement with a Malawian firm where the Malawian firm shall be responsible for a proportion of the assignment as stipulated by the National Construction Industry (Subcontracting and Joint Ventures between Foreign Contractors and Malawian Contractors) Regulations, 2023. |  |  |  |
| This Invitation for Bids is open to all suppliers from eligible countries as defined in Section 5, Eligible Countries. A Bidder shall be deemed to have the nationality of a country if the Bidder is a citizen or is constituted, incorporated, or registered and operates in conformity with the provisions of the laws of that country. This criterion shall also apply to the determination of the nationality of proposed subcontractors for any part of the Contract including related services. |  |  |  |
| A Bidder shall not have a conflict of interest. Any Bidder found to have a conflict of interest shall be disqualified. A Bidder may be considered to have a conflict of interest for the purpose of this Bidding process, if the Bidder— - directly or indirectly controls, is controlled by or is under common control with another Bidder; - receives or has received any direct or indirect subsidy from another Bidder; - has the same legal representative as another Bidder; - has a relationship with another Bidder, directly or through common third parties, that puts it in a position to influence the Bid of another Bidder, or influence the decisions of the Procuring and Disposing Entity regarding this Bidding process; - participates in more than one Bid in this Bidding process. Participation by a Bidder in more than one Bid will result in the disqualification of all Bids in which such Bidder is involved but this does not limit the inclusion of the same subcontractor in more than one Bid; - any of its affiliates participated as a consultant in the preparation of the design or technical specifications of the works that are the subject of the Bid; - any of its affiliates has been hired (or is proposed to be hired) by the Procuring and Disposing Entity as Engineer for the Contract implementation; - would be providing goods, works, or non-consulting services resulting from, or directly related to consulting services for the preparation or implementation of the project specified in the BDS clause 2.1 that it provided or were provided by any affiliate that directly or indirectly controls, is controlled by, or is under common control with that firm; or - has a close business or family relationship with staff of the Procuring and Disposing Entity who— - are directly or indirectly involved in the preparation of the Bidding documents or specifications of the contract, and/or the Bid evaluation process of such contract; or - would be involved in the implementation or supervision of such contract unless the conflict stemming from such relationship has been resolved. |  |  |  |
| - 4.5. A Bidder— - that has been debarred from participating in public procurement in accordance with Section 79 of the Act, at the date of the deadline for Bid submission or thereafter, shall be ineligible; and - shall be declared ineligible for award of contract if it comes to the knowledge of the Director General that the Bidder or supplier in question is debarred by cooperating and/or development partners subject to agreement entered into between the Authority and such partners. |  |  |  |
| - 4.6. Government-owned enterprises shall be eligible if they can establish that they are legally and financially autonomous and are not a dependent agency, directly or indirectly, of the Procuring and Disposing Entity or the Government of Malawi. |  |  |  |
| - 4.7. Bidders shall provide such evidence of their eligibility satisfactorily to the Procuring and Disposing Entity, to verify that the Bidder— #### has the legal capacity to enter into an Agreement and is registered with appropriate professional regulatory institution as required by existing legislation; #### is not insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and #### has fulfilled their obligations to pay taxes according to the tax laws of their country of registration. - 4.8. In order to demonstrate compliance with the criteria in sub-clause 4.7, a Bidder shall submit with its Bid— #### a certified copy of Business registration certificate; #### Professional registration certificate where applicable based on the business the Bidder does; #### a declaration that the Bidder is not debarred; #### a copy of its valid annual tax clearance certificate issued by the Malawi Revenue Authority; and #### Such other documentary evidence as may be specified in the BDS. |  |  |  |
| - 4.9 Provided that Bidders in the micro, small and medium-sized –enterprises category and those eligible for set-asides, shall be eligible to enter into sub-contracting and joint ventures in accordance with rules issued by the concerned organs of government, and referred to in the Public Procurement and Disposal of Public Assets (Participation by Micro Small and Medium Enterprises) Order 2020 (MSME Order) issued by Order from the Authority. |  |  |  |
| - QUALIFICATION OF BIDDERS All Bidders shall provide in the Qualification Information Form in Section 4, Bidding Forms, a preliminary description of the proposed work method and schedule, including drawings and charts, as necessary. In the event that prequalification of potential Bidders has been undertaken, only Bids from prequalified Bidders will be considered for award of Contract. These qualified Bidders should submit with their Bids any information updating their original prequalification applications or, alternatively, confirm in their Bids that the originally submitted prequalification information remains essentially correct as of the date of Bid submission. The update or confirmation should be provided in the Qualification Information Form in Section 4, Bidding Forms. (a) If the Procuring and Disposing Entity has not undertaken prequalification of potential Bidders, all Bidders shall include the following information and documents with their Bids, using the Qualification Information Form in Section 4, Bidding Forms, unless otherwise stated in Section 3, Evaluation and Qualification Criteria___ |  |  |  |
| - copies of original documents defining the constitution or legal status, place of registration, and principal place of business or a copy of the Bidder’s registration certificate where such documents have been provided to obtain registered supplier status; written power of attorney of the signatory of the Bid to commit the Bidder; - total monetary value of construction works performed for each of the last five (5) years; - experience in works of a similar nature and size for each of the last five (5) years, and details of work underway or contractually committed; and clients who may be contacted for further information on those contracts; - major items of construction equipment proposed to carry out the Contract; - qualifications and experience of key site management and technical personnel proposed for the Contract; - reports on the financial standing of the Bidder including profit and loss statements and auditor’s reports for the past five (5) years; - evidence of adequacy of working capital for this Contract (access to line(s) of credit and availability of other financial resources); - written authorization to seek references from the Bidder’s bankers; - information regarding any litigation, current or during the last five (5) years, in which the Bidder is involved, the parties concerned, and disputed amount; and - proposal for subcontracting components of the Works. |  |
| - Bids submitted by a joint venture of two or more firms as partners shall comply with the following requirements, unless otherwise stated in Section 3, (Evaluation and Qualification Criteria)— |  |  |  |
| - the Bid shall include all the information listed in clause 5.3 for each joint venture partner; - availability of signed joint venture agreement; - the Bid shall be signed by all partners; - all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms; - one of the partners will be nominated as being in charge, authorised to incur liabilities, and receive instructions for and on behalf of any and all partners of the joint venture; and - the execution of the entire Contract, including payment, shall be done exclusively with the partner in charge. |  |  |  |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. |  |  |  |
| - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. ONE BID PER BIDDER - Each Bidder shall submit only one Bid, either individually or as a partner in a joint venture. A Bidder who submits or participates in more than one Bid (other than as a subcontractor or in cases of alternatives that have been permitted or requested) will cause all the Bids with the Bidder’s participation to be disqualified. SITE VISITS AND PRE-BID MEETINGS The Bidder, at its own responsibility and risk, is encouraged to visit and examine the Site of Works and its surroundings and obtain all information that may be necessary for preparing the Bid and entering a contract for construction of the Works. The costs of visiting the Site and attending pre-Bid meetings shall be at the Bidder’s own expense Where a pre-Bid meeting is to be held, report of such meeting shall be given in the BDS. |  |  |  |
| CONTENTS OF THE BIDDING DOCUMENT |  |  |  |
| SECTIONS OF BIDDING DOCUMENT |  |  |  |
| The Bidding Document consists of Parts 1, 2 and 3, which includes all Sections indicated below, and should be read in conjunction with any addenda issued in accordance with clause 10. PART 1 BIDDING PROCEDURES - Section 1 Instructions to Bidders (ITB) - Section 2 Bid Data Sheet (BDS) - Section 3 Evaluation and Qualification Criteria (EQC) - Section 4 Bidding Forms - Section 5 Eligible Countries - Section 6 Corruption and Fraud PART 2 SCHEDULE OF REQUIREMENTS - Section 7(A) – Scope of Works - Section 7(B) – Bills of Quantities (BOQs) (or Activity Schedule) - Section 7(C) – Drawings - Section 7(D) – Technical Specifications (TS) PART 3 CONTRACT - Section 8 General Conditions of Contract (GCC) - Section 9 Special Conditions of Contract (SCC) - Section 10 Contract Forms |  |  |  |
| The Invitation to Bid is not part of the Bidding Document. The Procuring and Disposing Entity is not responsible for the completeness of the Bidding Documents and their addenda if they were not obtained directly from the Procuring and Disposing Entity. A Bidding Document which was not obtained directly from the Procuring and Disposing Entity may be rejected during evaluation. Where a Bidding Document is obtained from the Procuring and Disposing Entity on a Bidder’s behalf, the Bidder’s name must be registered with the Procuring and Disposing Entity at the time of sale and issue. The Bidder is expected to examine all instructions, forms, terms, and specifications in the Bidding Documents. Failure to furnish all information or documentation required by the Bidding Documents may result in the rejection of the Bid. |  |  |  |
| CLARIFICATION OF BIDDING DOCUMENTS |  |  |  |
| A prospective Bidder requiring any clarification of the Bidding documents may request the Procuring and Disposing Entity in writing at the Procuring and Disposing Entity's address indicated in the BDS. The Procuring and Disposing Entity shall respond to any request for clarification received earlier than fourteen (14) days prior to the deadline for submission of Bids. Copies of the Procuring and Disposing Entity's response will be forwarded to all Bidders, including a description of the inquiry, but without identifying its source. Should the Procuring and Disposing Entity deem it necessary to amend the Bidding Documents as a result of a clarification, it shall do so following the procedure under clause 10 and clause 23.2. |  |  |  |
| AMENDMENT TO BIDDING DOCUMENTS |  |  |  |
| At any time, before the deadline for submission of Bids, the Procuring and Disposing Entity may modify the Bidding documents by issuing addenda. Any addendum thus issued shall be part of the Bidding documents and shall be communicated in writing to all Bidders who have obtained the Bidding documents directly from the Procuring and Disposing Entity. Prospective Bidders shall acknowledge receipt of each addendum in writing to the Procuring and Disposing Entity. To give prospective Bidders reasonable time in which to take an addendum into account in preparing their Bids, the Procuring and Disposing Entity may at its own discretion, extend the deadline for submission of Bids, in accordance with clause 23.2. |  |  |  |
| Preparation of Bids |  |  |  |
| COST OF BIDDING |  |  |  |
| - The Bidder shall bear all costs associated with the preparation and submission of its Bid, and the Procuring and Disposing Entity shall not be responsible or liable for those costs, regardless of the conduct or outcome of the Bidding process. |  |  |  |
| LANGUAGE OF BID |  |  |  |
| All communication in the Bidding process shall be in English and in writing unless otherwise specified in the BDS. The Bid including correspondence and documents relating to the Bid exchanged by the Bidder and the Procuring and Disposing Entity, shall be written in English unless otherwise specified in the BDS. Supporting documents and printed literature which are part of the Bid may be in another language provided that the documents are accompanied by an accurate translation of the relevant passages in English, in which case, for purposes of interpretation of the Bid, such translation shall govern. |  |  |  |
| DOCUMENTS COMPRISING THE BID |  |  |  |
| - The Bid shall comprise the following— Bid Submission Form; Bid Security; Priced Bill of Quantities or Activity Schedule; |  |  |  |
| Qualification Information; alternative Bids, if permissible; written confirmation authorising the signatory of the Bid to commit the Bidder, where applicable; documentary evidence in accordance with clause 18 establishing the Bidder’s eligibility to Bid; Environmental, Social, Health and Safety Performance Declaration; and any other document required in the BDS. |  |  |  |
| BID SUBMISSION FORM AND PRICE SCHEDULES A Bidder shall submit the Bid Submission Form using the template furnished in Section 4, Bidding Forms. The form must be completed without any alterations to its format, and no substitutes shall be accepted. All blank spaces shall be filled in with the information requested, which includes— the reference of the Bidding Document and the number of each addendum received; a brief description of the Works and Related Goods/Services offered; the total Bid price; the period of validity of the Bid; any discounts offered and the methodology for their application; a commitment to submit a performance security and the amount; confirmation that the Bidder has not been debarred; a declaration concerning investigations relating to any other public procurement tender exercise or awarded contract; a declaration on gratuities and commissions; the names and addresses of the Directors and Beneficial owners of the Bidder; a declaration concerning the country of registration the Bidder; a declaration that the Bidder, including all parties comprising the Bidder, is not participating, as a Bidder, in more than one Bid in this Bidding process; except for alternative Bids in accordance with ITB clause 15.3; and an authorised signature The Bidder shall submit the Price Schedules using the forms furnished in Section 4, Bidding forms. The Bidding forms shall indicate, as appropriate— the item number; a brief description of the works; quantity; unit prices; total price per item; summary and subtotals of Price; levy imposed by the Public Procurement and Disposal of Public Assets Authority, taxes, duties, where applicable, payable in Malawi; unit rate analysis; and authorised signature or initials of the Bidder. ALTERNATIVE BIDS Unless otherwise indicated in the BDS, alternative Bids shall not be considered. Where permitted, alternative Bids do not need to conform precisely to the Statement of Requirements, but must___ meet the objectives and/or performance requirements prescribed in the Statement of Requirements; be substantially within any delivery or completion schedule, budget or other performance parameters stated in the solicitation document; and - clearly state the benefits of the alternative Bid over any solution which conforms precisely to the Statement of Requirements, in terms of technical performance, price, operating costs or any other benefit. A Bidder may submit both a main Bid, which conforms, precisely to the Statement of Requirements and an alternative Bid, if required. Where a Bidder submits more than one Bid, each Bid shall be submitted as a completely separate Bid and shall conform to the instructions for preparation and submission of Bids in its own right, without any reliance on any other Bid. In particular, each Bid shall be separately signed, authorised, sealed, labelled and submitted in accordance with the instructions for submission of Bids and shall be accompanied by a separate Bid Security, if so required. Such Bids shall be labelled “Main Bid” and “Alternative Bid”. The evaluation of alternative Bids shall use the same methodology, criteria and weights as the evaluation of main Bids, except that the detailed technical evaluation shall take into account only the objectives and/or performance requirements prescribed in the Statement of Requirements. Bid Prices |  |  |  |
| The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the BDS. The Contract shall be for the whole Works, as described in clause 1.1, based on the— priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |  |  |  |
| The Bidder shall fill in rates and prices for all items of the Works described in the Bill of Quantities or in the case of a lump sum contract, for all items of the Works described in the drawings and specifications and listed in the Activity Schedule). Items in a series for which no rate or price is entered by the Bidder will not be paid for by the Procuring and Disposing Entity when executed and shall be deemed covered by the other rates and prices in the Bill of Quantities or Activity Schedule. |  |  |  |
| All duties, taxes, and other levies payable by the Contractor under the Contract, or for any other cause, as of the date twenty-eight (28) days prior to the deadline for submission of Bids, shall be included in the rates, prices, and total Bid price (or in the case of a lump sum contract, in the total Bid price) submitted by the Bidder. Construction levies and all other levies payable by the contractor under the contract shall be included in the rates, prices, and total Bid price or in the case of a lump sum contract, in the total Bid price submitted by the Bidder. The rates and prices or in the case of a lump sum contract, the lump sum price) quoted by the Bidder shall not be subject to adjustment during the performance of the Contract unless provided for in the BDS and SCC. The Bidder shall submit with the Bid all the information required under the SCC and GCC. |  |  |  |
| CURRENCIES OF BID |  |  |  |
| For local Bidders, the unit rates and prices shall be quoted in Malawi Kwacha. A Bidder expecting to incur expenditures in other currencies for inputs to the Works supplied from outside Malawi shall indicate in the Bid Submission Sheet, the percentage(s) of the Bid Price (excluding Provisional Sums), needed by the Bidder for the payment of such foreign currency requirements, limited to no more than three freely convertible currencies. For foreign Bidders, the unit rates and prices shall be quoted by the Bidder in the Bill of Quantities separately in the following currencies— - (a) for those inputs to the Works that the Bidder expects to supply from within Malawi, in Malawi Kwacha; and - (b) for those inputs to the Works that the Bidder expects to supply from outside Malawi, in up to any three freely convertible currencies. The rates of exchange to be used by the Bidder in arriving at the Malawi Kwacha equivalent and the percentage(s) shall be the selling rates for similar transactions established by the authority specified in the BDS prevailing on the date fourteen (14) days prior to the deadline for submission of Bids. These exchange rates shall apply for all payments. If the Bidder uses other rates of exchange, the provisions of clause 28.1 shall apply. In any case, payments will be computed using the rates quoted in the Bid. Bidders shall indicate details of their expected foreign currency requirements in the Bid, where provided for. - The Procuring and Disposing Entity may require the Bidder to clarify their foreign currency requirements and to substantiate that the amounts included in the rates and prices (or in the case of a lump sum contract, in the lump sum price) and in the Special Conditions of Contract are reasonable and responsive to clause 14.1.. |
| DOCUMENTS ESTABLISHING ELIGIBILITY OF THE BIDDER - To establish their eligibility in accordance with clause 4, Bidders shall complete the eligibility declarations in the Bid Submission Sheet, included in Section 4, Bidding Forms. PERIOD OF VALIDITY OF THE BIDS |  |  |  |
| Bids shall remain valid for the period specified in the BDS. A Procuring and Disposing Entity shall reject a Bid valid for a shorter period as non-responsive. In exceptional circumstances, prior to expiry of the Bid validity period, the Procuring and Disposing Entity may request Bidders to extend the period of validity of their Bids. The request and the responses shall be made in writing. If a Bid Security is requested in accordance with clause 20, it shall also be extended for a corresponding period. A Bidder may refuse the request without forfeiting its Bid Security. A Bidder granting the request shall not be required or permitted to modify its Bid, except as provided in clause 25.2. |  |  |  |
| In the case of contracts in which the Contract Price is fixed (not subject to price adjustment), if the period of Bid validity is extended beyond sixty (60) days, the amounts payable shall be increased by applying the factors specified in the BDS or in the request for extension, up to the notification of award. - Bid evaluation shall be based on the Bid prices without taking the above correction into consideration. |  |  |  |
| BID SECURITY |  |  |  |
| Unless otherwise specified in the BDS, the Bidder shall furnish as part of its Bid, a Bid security in prescribed form and in the amount and currency for the Bid Security specified in the BDS. |  |  |  |
| The Bid Security shall be in any of the following forms— a demand guarantee; an irrevocable letter of credit; or a cashier’s or certified cheque or payable order. All forms of security in (a), (b), and (c) shall be from a reputable bank in an eligible country and acceptable by Reserve Bank of Malawi. The Bid Security shall be submitted either using the Bid Security Form included in Section 4 (Bidding Forms), or in another substantially similar format without changing the content of the prescribed form, acceptable to the Procuring and Disposing Entity. In either case, the form must include the complete name of the Bidder. The Bid Security shall be valid for twenty-eighty (28) days beyond the end of the validity period of the Bid. This shall also apply if the period for which Bid validity is extended. |  |  |  |
| Any Bid not accompanied by an acceptable Bid Security shall be rejected. The Bid Security of a joint venture must define as “Bidder” all joint venture partners and list them in the following manner: a joint venture consisting of “______,” “______,” and “______”. |  |  |  |
| The Bid Security of unsuccessful Bidders will be returned within one (1) week after concluding the contract and after a Performance Security has been furnished by the successful Bidder. |  |  |  |
| The Bid Security of the successful Bidder will be discharged when the Bidder has signed the contract and furnished the required Performance Security. |  |  |  |
| - The Bid Security may be forfeited— |  |  |  |
| - if the Bidder withdraws its Bid after Bid opening during the period of Bid validity; - if the Bidder does not accept the correction of the Bid price, pursuant to clause 68; or - if the successful Bidder fails to-- - sign the contract; - furnish a Performance Security; or - accept the correction of its Bid Price. |  |  |  |
| FORMAT AND SIGNING OF BID |  |  |  |
| A Bidder shall prepare one original of the documents comprising the Bid as described in clause 13 and clearly mark it “ORIGINAL.” In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS and each clearly mark them “COPY.” In the event of any discrepancy between the original and the copies, the original shall prevail. |  |  |  |
| The original and all copies of the Bid shall be typed or written in indelible ink and shall be signed by a person duly authorised to sign on behalf of the Bidder. This authorisation shall consist of a written confirmation as specified in the BDS and shall be attached to the Bid. The name and position held by each person signing the authorisation must be typed or printed below the signature. The person or persons signing the Bid shall initial all pages of the Bid where entries or amendments have been made. |  |  |  |
| Any interlineation, erasures, or overwriting shall be valid only if they are signed or initialled by the person signing the Bid. |  |  |  |
| BID SUBMISSION |  |  |  |
| SEALING AND MARKING OF BIDS |  |  |  |
| - The Bidder shall enclose the original and each copy of the Bid, including alternative Bids, if permitted, in separate sealed envelopes, duly marking the envelopes as “ORIGINAL”, “COPY” or “ALTERNATIVE”. The envelopes containing the original and the copies shall then be enclosed in one single envelope. |  |  |  |
| The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. The inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 24. |  |  |  |
| - If all envelopes are not sealed and marked as required, the Procuring and Disposing Entity shall assume no responsibility for the misplacement or premature opening of the Bid. |  |  |  |
| DEADLINE FOR SUBMISSION OF BIDS |  |  |  |
| Bids shall be delivered to the Procuring and Disposing Entity at the address specified in clause 22.2(a) no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment in accordance with clause 10, in which case, all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |  |  |  |
| LATE BIDS |  |  |  |
| - Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in BDS will be returned unopened to the Bidder. |  |  |  |
| WITHDRAWAL, SUBSTITUTION AND MODIFICATION OF BIDS |  |  |  |
| Bidders may withdraw, substitute, or modify their Bids by giving notice in writing before the deadline prescribed in BDS, except that withdrawal notices do not require copies. |  |  |  |
| Each Bidder’s withdrawal, substitution or modification notice shall be prepared, sealed, marked, and delivered in accordance with clauses 21 and 22, with the outer and inner envelopes additionally marked “WITHDRAWAL”, “SUBSTITUTION” or “MODIFICATION” as appropriate. The corresponding substitution or modification of the Bid must accompany the written notice. |  |  |  |
| No Bid may be modified after the deadline for submission of Bids. Withdrawal of a Bid between the deadline for submission of Bids and the expiration of the period of Bid validity specified in the BDS or as extended pursuant to clause 19 may result in the forfeiture of the Bid Security. - Bidders may only offer discounts to, or otherwise modify the prices of their Bids by submitting Bid substitutions or modifications in accordance with this clause or included in the original Bid submission. |  |  |  |
| BID OPENING AND EVALUATION |  |  |  |
| BID OPENING |  |  |  |
| - The Procuring and Disposing Entity shall conduct the Bid opening in the presence of designated representatives of a Bidder who choose to attend, and at the address, date and time specified in the BDS. |  |  |  |
| - Envelopes marked "WITHDRAWAL" shall be opened first and read out first. Bids for which an acceptable notice of withdrawal has been submitted pursuant to clause 25 shall not be opened. Envelopes marked “SUBSTITUTION” shall be opened and read out and exchanged with the corresponding Bid being substituted, and the substituted Bid shall not be opened, but returned to the Bidder. No Bid substitution shall be permitted unless the corresponding substitution notice contains a valid authorisation to request the substitution and is read out at Bid opening. Envelopes marked “MODIFICATION” shall be opened and read out with the corresponding Bid. No Bid modification shall be permitted unless the corresponding modification notice contains a valid authorisation to request the modification and is read out at Bid opening. |  |  |  |
| All other envelopes shall be opened one at a time, reading out: the name of the Bidder and whether there is a modification; the Bid Prices, including any discounts and alternative offers; the presence of a Bid security, if required; and any other details as the Procuring and Disposing Entity may consider appropriate. Only discounts and alternative offers read out at Bid opening shall be considered for evaluation. No Bid shall be rejected at Bid opening except for late Bids. |  |  |  |
| The Procuring and Disposing Entity shall prepare records of the Bid opening, including the information disclosed to those present in accordance with sub-clause 26.1. copies of the records will be made available to any Bidder who requests them. |  |  |  |
| CONFIDENTIALITY AND EVALUATION OF BIDS |  |  |  |
| Information relating to the examination, evaluation, comparison, and post qualification of Bids, and recommendation of contract award, shall not be disclosed to Bidders or any other persons not officially concerned with such process until information on Contract award is communicated to all Bidders. Any effort by a Bidder to influence the Procuring and Disposing Entity’s processing of Bids or award decisions may result in the rejection of its Bid. From the time of Bid opening to the time of Contract award, if any Bidder wishes to contact the Procuring and Disposing Entity on any matter related to the Bidding process, it should do so in writing. A Procuring and Disposing Entity shall ensure that staff involved in the Bidding, evaluation and execution of contracts sign statements confirming that they are not in conflict of interest with any of the Bidders and that they shall uphold the confidentiality of all information that they have access to. |  |  |  |
| CLARIFICATION OF BIDS |  |  |  |
| To assist in the examination, evaluation and comparison of Bids, the Procuring and Disposing Entity may, in writing request any Bidder for clarification of the Bidder’s Bid, including breakdowns of unit rates or in the case of a lump sum contract, the prices in the Activity Schedule. The response shall be in writing, but no change in the price or substance of the Bid shall be sought, offered, or permitted except as required to confirm the correction of arithmetic errors discovered by the Procuring and Disposing Entity in the evaluation of the Bids. |  |  |  |
| - Subject to sub-clause 27.1 no Bidder shall contact the Procuring and Disposing Entity on any matter relating to its Bid from the time of the Bid opening to the time the contract is awarded. If the Bidder wishes to bring additional information to the notice of the Procuring and Disposing Entity, it should do so in writing. |  |  |  |
| EXAMINATION AND DETERMINATION OF RESPONSIVENESS OF BIDS |  |  |  |
| The Procuring and Disposing Entity shall determine whether each Bid meets the eligibility criteria, has been properly signed, is accompanied by the required Bid Security; and is substantially responsive to the requirements of the Bidding documents. |  |  |  |
| A substantially responsive Bid is one, which conforms to all the terms, conditions, and specifications of the Bidding documents, without material deviation, reservation, or omission. A material deviation or reservation is one that— - (a) affects in any substantial way the scope, quality, or performance of the Works; - (b) limits in any substantial way, inconsistencies with the Bidding documents, the Procuring and Disposing Entity’s rights or the Bidder’s obligations under the Contract; or - (c) if rectified, would affect unfairly the competitive position of other Bidders presenting substantially responsive Bids. |  |  |  |
| - If a Bid is not substantially responsive to the Bidding Documents, it shall be rejected by the Procuring and Disposing Entity and may not subsequently be made responsive by the Bidder by correction of the material deviation, reservation, or omission. |  |  |  |
| NONCONFORMITIES, ERRORS AND OMISSIONS |  |  |  |
| Where a Bid is substantially responsive, the Procuring and Disposing Entity may waive any non-conformity or omissions in the Bid that does not constitute a material deviation. Errors shall be corrected by the Procuring and Disposing Entity as follows— |  |  |  |
| For admeasurement contracts only, if there is a discrepancy between the unit price and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected, unless in the opinion of the Procuring and Disposing Entity there is an obvious misplacement of the decimal point in the unit price, in which case the total price as quoted shall govern and the unit price shall be corrected; |  |  |  |
| If there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail, and the total shall be corrected; and If there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a) and (b) above. |  |  |  |
| The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the above procedure for the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. - If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security may be forfeited. |  |  |  |
| PRELIMINARY EXAMINATION OF BIDS The Procuring and Disposing Entity shall examine the Bids to confirm that all documents and technical documentation requested in clause 13, 14 and 15 have been provided, and to determine the completeness of each document submitted. The Procuring and Disposing Entity shall confirm that the following documents and information have been provided in the Bid. If any of these documents or information is missing, the Bid shall be rejected— Bid Submission Form; Price Schedules; Written confirmation of authorisation to commit Bidder; and Bid Security, if applicable. EXAMINATION OF TERMS AND CONDITIONS The Procuring and Disposing Entity shall examine the Bid to confirm that the Bidder has accepted all terms and conditions specified in the GCC and the SCC without any material deviation or reservation. The Procuring and Disposing Entity shall evaluate the technical aspects of the Bid to confirm that all requirements specified in Section 7, Schedule of Requirements of the Bidding Documents, have been met without any material deviation or reservation If, after the examination of the terms and conditions and the technical evaluation, the Procuring and Disposing Entity determines that the Bid is not substantially responsive in accordance with clause 29, it shall reject the Bid. CURRENCY FOR BID EVALUATION |  |  |  |
| - For evaluation and comparison purposes, the Procuring and Disposing Entity shall convert all Bid prices expressed in the amounts in various currencies into Malawi Kwacha, using the selling exchange rate established by the source and on the date specified in the BDS. |  |  |  |
| DOMESTIC PREFERENCE - If so indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. |  |  |  |
| DETAILED EVALUATION |  |  |  |
| The Procuring and Disposing Entity shall evaluate each Bid that has been determined, up to this stage of the evaluation, to be substantially responsive. To evaluate a Bid, the Procuring and Disposing Entity shall use all the criteria and methodologies defined in this clause and in Section 3, Evaluation and Qualification Criteria. No other criteria or methodology shall be permitted. To evaluate a Bid, the Procuring and Disposing Entity shall consider the following— the Bid price; price adjustment for correction of arithmetic errors in accordance with clause 30.2; price adjustment due to discounts offered in accordance with clause 25.5; adjustment for nonconformities and omissions in accordance with clause 30.3; application of all the evaluation factors indicated in Section 3, Evaluation and Qualification Criteria; and adjustments due to the application of a margin of preference, in accordance with clause 34; In the calculation of the evaluated cost of Bids, the Procuring and Disposing Entity shall exclude and not consider any allowance for price adjustment during the period of execution of the Contract, if provided for in the Bid; The Procuring and Disposing Entity’s cost evaluation of a Bid may require the consideration of other factors, in addition to the Bid Price quoted in accordance with clause 13. These factors may be related to the characteristics, performance, and terms and conditions of execution of the works. The factors selected, if any, shall be expressed in monetary terms to facilitate comparison of Bids as specified in Section 3, Evaluation and Qualification Criteria. The factors to be used and the methodology of application shall be indicated in Section 3, Evaluation and Qualification Criteria. If these Bidding Documents allow Bidders to quote separate prices for different lots, and the award to a single Bidder of multiple lots, the methodology of evaluation to determine the lowest evaluated lot combinations, including any discounts offered in the Bid Submission Sheet, is specified in the BDS and detailed in Section 3 Evaluation Methodology and Criteria. FINANCIAL EVALUATION. A Bid that has passed detailed evaluation and complied with all the terms and conditions shall be evaluated financially to determine the conformity of prices offered. In doing so, the Procuring and Disposing Entity shall examine the contents of a price to confirm if all taxes or discounts have been taken into account.. The purpose of the financial evaluation process is to identify the Bidder offering the lowest price that would enable the Procuring and Disposal Entity to achieve the purpose on time, within the available resources and that meets the prescribe technical specifications and standards. The Bids shall further be examined on its economic viability to establish if the price offered reflects the market value of the works which has taken into account the minimum construction costs in line with the technical specifications and standards. The Procuring and Disposal Entity shall examine in detail all information submitted by the Bidder in relation to pricing and shall formulate its judgement on the basis of economic viability of the Bid price.. A Bid that has passed all the stages including financial evaluation shall be declared substantially responsive.. COMPARISON OF BIDS - The Procuring and Disposing Entity shall compare all substantially responsive Bids to determine the lowest evaluated Bid, in accordance with clause 35.6. ENVIRONMENTAL AND SOCIO-ECONOMIC POLICIES For sustainable development, A Bidder shall be evaluated taking into account compliance with Environmental protection, policies, laws and regulations applicable in Malawi. A Procuring and Disposing Entity may specify in its evaluation criteria, a method to determine or assess how Bidders promote general as well as specific policies and programmes for sustainability and environmental protection. A Bidder shall be evaluated taking into account compliance with the protection of Child Labour Guidelines and Policies, applicable in Malawi as well as policies for the protection of children and their rights. A Bidder shall be evaluated taking into account compliance with restrictions on Sexual Exploitation / prohibition policies, laws and regulations applicable in Malawi and internationally on Gender Based Violence and Gender Equality. The Procuring and Disposing Entity may specify in the evaluation criteria, a method to determine or assess how Bidders should show compliance with avoidance of Child Labour and Unfair Labour Practices as well as specific policies and programmes for protection of children from any form of child labour and adherence to applicable fair labour practices. POST-QUALIFICATION OF THE LOWEST EVALUATED BIDDER A Procuring and Disposing Entity shall determine to its satisfaction whether the Bidder that is selected as having submitted the lowest evaluated and substantially responsive Bid is qualified to perform the Contract satisfactorily. The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to clause 18, to clarifications in accordance with clause 28 and the qualification criteria indicated in Section 3, Evaluation and Qualification Criteria. Factors not included in Section 3 shall not be used in the evaluation of the Bidder’s qualification. The Procuring and Disposing Entity shall, in its own discretion, conduct due diligence on certain procurements. In doing so, it shall prepare its own budget for such an activity and shall not rely or depend on the resources of the Bidder. Due diligence reports shall form part of the evaluation data used by the evaluation teams or Internal Procurement and Disposal Teams when making decisions. An affirmative determination shall be a prerequisite for award of the Contract to the Bidder. A negative determination shall result in disqualification of the Bid, in which event the Procuring and Disposing Entity shall proceed to the next lowest evaluated Bid to make a similar determination of that Bidder’s capabilities to perform satisfactorily. PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID, AND TO REJECT ANY OR ALL BIDS - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to annul the Bidding process and reject all Bids at any time prior to contract award, without thereby incurring any liability to Bidders. |
| AWARD OF CONTRACT |  |  |  |
| AWARD CRITERIA |  |  |  |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the Bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be eligible and qualified to perform the contract satisfactorily. |  |  |  |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO VARY QUANTITIES AT TIME OF AWARD - At the time the Contract is awarded, the Procuring and Disposing Entity reserves the right to increase or decrease the quantity of Works and Related Goods/ Services originally specified in Section 7, Statement of Requirement, provided this does not exceed the percentages indicated in the BDS, and without any change in the unit prices or other terms and conditions of the Bid and the Bidding Documents. |  |  |  |
| NOTICE OF INTENTION TO AWARD THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |  |  |  |
| Prior to expiry of the period of Bid validity, where the works contract is below the threshold for publication of an intention to award a contract, the Procuring and Disposing Entity shall notify the successful Bidder, in writing, that its Bid has been accepted. At the same time, the Procuring and Disposing Entity shall also notify all other Bidders of the results of the Bidding. The notification of award shall not be sent until all the necessary approvals have been obtained or the fourteen days’ standstill period has expired, wherever necessary. Prior to expiry of the period of Bid validity, where the procurement contract is above the threshold for publication of an intention to award a contract is required, the Procuring and Disposing Entity shall publish the intention to award contract in two widely circulated newspapers and on the Authority's website for a period of fourteen (14) days for any procurement contract above a threshold to be set by the Director General before signing the contract. Prior to the signing of the contract but after the completion of intention to award proceedings, the Procuring and Disposing Entity may enter into negotiations with the successful Bidders on the modalities for the execution of the contract not changing the material factors of the contract. |  |  |  |
| Within thirty (30) days of receipt of notification of award from the Procuring and Disposing Entity, the successful Bidder shall furnish the performance security and the Environmental and Social Performance Security in accordance with the GCC, using for that purpose the Performance Security Form included in Section 10, Contract Forms, or another form acceptable to the Procuring and Disposing Entity. - Failure of the successful Bidder to submit the above-mentioned Performance Security and the Environmental and Social Performance Security or sign the Contract shall constitute sufficient grounds for annulment of the award and forfeiture of the Bid security. In that event, the Procuring and Disposing Entity may award the Contract to the next lowest evaluated Bidder whose Bid is substantially responsive and is determined by the Procuring and Disposing Entity to be qualified to perform the Contract satisfactorily. |  |  |  |
| SIGNING THE CONTRACT |  |  |  |
| Promptly after notification, or after the elapsing of the fourteen (14) days of the still period, or after successfully attending to all objections to the intention to award contract for contract above the set threshold, the Procuring and Disposing Entity shall send the successful Bidder the Contract documents. Within thirty (30) days of receipt of the Contract documents, the successful Bidder shall sign, date, and return the Contract documents to the Procuring and Disposing Entity to finalise the signing process. |  |  |  |
| SETTLEMENT OF DISPUTES In the event of a dispute arising out of the performance of the contract by either party, such disputes shall be resolved amicably. Should amicable dispute resolution fail, the matter shall be taken to arbitration, depending on the agreement by two parties. However, should arbitration still not yield positive results to either party, either party so wronged shall take the matter to the local courts. For purposes of this Contract, the Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Award, the Procuring and Disposing Entity and Bidder have not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |  |  |  |

# SECTION 2.  BID DATA SHEET

SECTION 2.  BID DATA SHEET

| Instructions to Bidders (ITB) reference | Data relevant to ITB |
| --- | --- |
| A. General |  |
| ITB 1.1, 2.1 | The Procuring and Disposing Entity is: Roads Authority The number and identification of Lots in this Bidding Document is: 1 |
| ITB 1.1; 22.2(b) | The subject of the procurement is: Completion of the Upgrading of Chitipa – Ilomba (T301/D002) Road Procurement Reference Number is: RA/DEV/CP/2022-23/01B |
| ITB 8.2 | The Procuring and Disposing Entity Shall hold a pre-Bid meeting and site visit. The pre-Bid meeting and site visit, shall take place at: Location: Ilomba - Junction Date: Friday, 22nd May 2026 Time: 10:00 Hours Central African Time |
| B. Bidding Documents |  |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Procurement Manager Street Address: John Chilembwe Highway Name of Building: Functional Buildings Floor/Room number: First Floor, Room No. 21 Town/City: Lilongwe Postal Address: Private Bag B346 Malawi Email address: ra@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 10 days prior to the submission date |
| C. Preparation of Bids |  |
| ITB 13 (i) | The Bidder shall submit with its Bid the following additional documents: - Code of Conduct for Contractor’s Personnel (ES) The Bidder shall submit its Code of Conduct that will apply to Contractor’s Personnel (as defined in Sub-Clause 1.1.17 of the General Conditions of Contract), to ensure compliance with the Contractor’s Environmental and Social (ES) obligations under the Contract. Bidders Shall complete and include the risks to be addressed by the Code in accordance with section VII- Works' Requirements, e.g. risks associated with: labour influx, Spread of communicable diseases, sexual harassment, gender based violence, sexual exploitation and abuse, illicit behaviour and crime and maintaining a safe environment. In addition the Bidder shall detail how the code of conduct will be implemented. This will include: how it will be introduced into conditions of employment/engagement, what training will be provided, how it will be monitored and how the contractor proposes to deal with any breaches. The Contractor shall be required to implement the agreed Code of conduct - Management Strategies and Implementation Plans (MSIP) to manage the (ES) risks The Bidder shall submit Management Strategies and Implementation Plans (MSIPs) to manage the following key Environmental and Social (ES) risks in alignment with the project ESIA/ESMP. - Traffic Management Plan to ensure safety of local communities and passengers from construction traffic - Water Resource Protection Plan to prevent contamination of drinking water; - Strategy to avoid and manage waste generation; - General strategy to avoid creation of noise nuisance, vibration and air pollution (due to e.g. dust); - A Grievance Redress Mechanism for the project - Boundary Marking and Protection Strategy for mobilization and construction to prevent offsite adverse impacts; - Strategy for obtaining Consents/Permits prior to the start of relevant works such as opening a quarry or borrow pit; - Strategy to manage occupational health and safety, incl. HIV prevention measures for contractor’s staff/workers and a grievance mechanism for workers to raise workplace related concerns; - Strategy to manage community health and safety incl. Gender Based Violence, Sexual Exploitation and Abuse, Child Labour and Violence Against Children prevention and response plan; HIV/STIs prevention plan; conflict resolution; - Strategy to ensure recruitment of locals and inclusion of youth and women in employment opportunities The Contractor shall be required to submit for approval, and subsequently implement, the Contractor’s Environmental and Social Management Plan (C-ESMP), in accordance with the Particular Conditions of Contract Sub-Clause 4.1, that includes the agreed Management Strategies and Implementation Plans described here. |
| ITB 15.1 | Alternative Bids shall not be permitted considered |
| ITB 16.1 | The Contract is Admeasurement. |
| ITB 16.6 | Bid Prices will be subject to adjustment during performance of the contract. |
| ITB 19.1 | Bids shall remain valid for 120 days. |
| ITB 20.2 | Bid Security shall be required. The amount of the Bid security shall be [MWK500,000,000.00] in Malawi Kwacha or its equivalent in United States Dollars exchanged at the prevailing Reserve Bank of Malawi rate on the transaction date. Foreign Banks issuing the Bid Security must do so through a corresponding local Bank |
| ITB 20.3 | A Bid Securing Declaration N/A. Where a Bid Securing Declaration is required no alteration to Bid Securing Declaration Form in Section 4 |
| ITB 22.1 | In addition to the original of the Bid, the number of copies is: Two (2) Hard Copies One (1) Electronic Copy of the whole bidding document in PDF Format, and the Priced Bills of Quantities in Excel Format. (these on a memory stick clearly labelled in the bidder’s name) |
| D. Bid Submission |  |
| ITB 23.2(a) | For Bid submission purposes only, the Procuring and Disposing Entity’s address is : Attention: Chief Executive Officer Street Address: John Chilembwe Highway Name of Building: Functional Buildings Floor/Room number: Floor No. 1, Room 21 Town/City: Lilongwe Postal Address/Post Code: Private Bag B346 |
| ITB 23.1 | The deadline for Bid submission is: Date: 10th June 2026 Time: 10:00 Hours Central African Time |
| ITB 26.1 | The Bid opening shall take place at: Street Address: Paul Kagame Road Name of Building: Functional Building Floor/Room number: Main Boardroom Town/City: Lilongwe Date:10th June 2026 Time: 10:00 Hours Central African Time |
| ITB 34.2 | A margin of preference Shall Not apply. A margin of preference for micro, small and medium enterprises and other marginalised groups Shall Not Apply A margin of preference for Preferential Treatment Shall not apply Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria |
| F. Award of Contract |  |
| ITB 46.2 | The Adjudicator proposed by the Procuring and Disposing Entity is: Malawi Engineering Institution The hourly fee for this proposed Adjudicator shall be:MWK50,000.00 The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

# SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

Procurement Reference Number:        RA/DEV/CP/2022-23/01B

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a Bid and determine whether a Bidder has the required qualifications. No other factors, methods or criteria shall be used.

- Evaluation Methodology

| - Methodology Used |  |  |
| --- | --- | --- |
| - The evaluation methodology to be used for the evaluation of Bids received shall be the Technical Compliance Selection (TCS) methodology. |  |  |
| - Summary of Methodology |  |  |
| - The evaluation shall be conducted in the following sequential stages – - A preliminary evaluation to determine the eligibility of Bidders and the administrative compliance of Bids received; - A detailed evaluation to determine the technical responsiveness of the eligible and compliant Bids; - A financial evaluation to compare costs of the responsive Bids received and thereafter determine the lowest evaluated Bid; and - Post qualification to confirm whether the lowest evaluated Bidder has the capacity and resources to effectively execute the procurement. Where applicable, a thorough due diligence should be conducted - Failure of a Bid at any stage of the evaluation shall prevent further consideration at the next stage of evaluation. Substantial responsiveness shall be considered a pass at the detailed evaluation stage. |  |  |
| - Preliminary Evaluation |  |  |
| - Eligibility Criteria |  |  |
| - The eligibility requirements shall be determined in accordance with ITB Clause 4 - The documentation required to provide evidence of eligibility shall be as prescribed in ITB 4 - For inclusion of a provision on Joint Venture, Consortiums and Associations - A certificate of registration issued by the Authority for Bidders currently registered with the Authority or a copy of the Bidder’s trading license or equivalent and a copy of the Bidder’s certificate of registration or equivalent for Bidders not currently registered with the Authority; and - A statement in the Bid submission sheet that the Bidder meets the eligibility criteria stated in ITB 4.1 and 4.4 - A declaration in the Bid submission sheet of nationality of the Bidder - A declaration in the Bid submission sheet that the Bidder is not under suspension by the authority - Fulfillment of obligations to pay taxes where applicable - For Joint Venture or Consortiums or Associations - A registered Power of Attorney from each member or partner if drawn and signed in Malawi; or a notarized Power of Attorney if drawn and signed outside Malawi, nominating a representative to conduct all business on its behalf during the Bid preparation, Bidding process and contract execution in case of award of the contract - The documentation in Section 3.2 for each member or partner and a copy of the Joint Venture / Consortium / Association Agreement which is legally binding on all partners or members stating that: - The partners or members shall jointly submit a Bid; - One of the parties will be nominated as lead member or partner to act for and on behalf of all members or partners; - The authorized representative of the lead member or partner who was granted power of attorney shall sign the Bid; - If the Bid is successful, the contract shall be executed in the name of the Joint Venture (JV), Consortium or Association and each member or partner shall sign the contract agreement; and - All partners shall be jointly and severally liable for the implementation of the contract in accordance with the contract terms - Declaration: Environmental and Social (ES) past performance A Bidder shall declare any civil work contracts that have been suspended or terminated and/or performance security called by a Client for reasons of breach of environmental, or social (including Sexual Exploitation and Abuse) contractual obligations in the past five years. |  |  |
| - Administrative Compliance Criteria |  |  |
| - The evaluation of Administrative Compliance criteria shall be conducted in accordance with ITB Clause 13. - Eligibility and administrative compliance shall be determined on a pass or fail basis and a Bid which is not eligible or administratively compliant shall be rejected at the preliminary stage of evaluation |  |  |
| - Detailed Evaluation |  |  |
| 5. Assessment of Responsiveness The assessment of responsiveness will consider the following criteria: - Acceptance of the conditions of the proposed contract; - Acceptable completion schedule; - Acceptability of the proposed program (work method and schedule), including relevant drawings and charts. 6. Mobilization Evaluation of the responsiveness of a Bid to the technical requirements will include an assessment of the Bidder's capacity to mobilize key equipment and personnel for the contract consistent with its proposal regarding work methods, scheduling, and material sourcing in sufficient detail and fully in accordance with the requirements stipulated in Section 7 (Statement of Requirements). |  |  |

7. 	Personnel and Equipment

A.    Personnel

The Bidder must demonstrate that it will have the key personnel for the following positions that meet the following requirements:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1. |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |
| 4. |  |  |  |

The Bidder shall provide details of the proposed personnel and their experience records in the relevant Forms included in Section 4, Bidding Forms.

B. Equipment

The Bidder must demonstrate that it shall have access to the key equipment listed hereafter (either by ownership, lease or  hire): attach documentary evidence of ownership, lease, hire such as registration books, agreements or memoranda or purchase order).

| No. | Equipment Type and Description/ Capacity | Minimum Number required |
| --- | --- | --- |
| 1. |  |  |
| 2. |  |  |

The Bidder shall provide further details of proposed items of equipment using the relevant Form in Section 4.

8. 	Qualification Criteria

  - The information required from Bidders in ITB Clause 5.3 is modified as follows:

  - The requirements for joint ventures in ITB Clause 5.3 are modified as follows:

  - To qualify for award of the Contract, in accordance with ITB Clause 5.3, Bidders shall meet the following minimum qualifying criteria:

- average annual volume of construction work over the past 3 Years of at least MWK 50 Billion or equivalent;

- experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 10 years (to comply with this requirement, works cited should be at least seventy (70) percent complete);

| Description | Unit | Quantity |
| --- | --- | --- |
| Earth works | m3 | 875,000 |
| Crushed Stone | m3 | 100,000 |
| Concrete | m3 | 1500 |
| Surfacing | m2 | 400,000 |

- proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment:

| S/N | Equipment Type and Description/ Capacity | No |
| --- | --- | --- |
| 1 | Self-propelled graders; | 4 |
| 2 | Dozers; | 2 |
| 3 | Loaders and/or excavators; | 2 |
| 4 | 20m3 Tipper trucks; | 20 |
| 5 | pneumatic-tyred rollers (123kw, 10t); | 2 |
| 6 | Vibrating Rollers (123kw, 10t); | 2 |
| 7 | Water Bowsers (10,000 to 18,000 litre). | 6 |
| 8 | Concrete mixer (6 cu.m capacity) | 2 |
| 9 | Bitumen distributor; | 2 |
| 10 | Asphalt Paver (at least 5.94m width capacity). | 1 |
| 11 | Sheepsfoot roller | 2 |
| 12 | Asphalt Plant (100 tonnes per hour) | 1 |
| 13 | Aggregate Crushing Plant (120 tonnes per hour) | 1 |

- personnel with the following qualifications and experience:

| S/N | Position | Qualifications and General Work Experience (years) | Experience in Similar Works |
| --- | --- | --- | --- |
| 1 | 1 x Site Agent: | Minimum of degree in Civil Engineering and at least fifteen (15) years of experience in road works | with at least 3 projects as a site agent; |
| 2 | 1xSite Engineer | Minimum of degree in Civil Engineering and at least ten (10) years of experience in road works | with at least 2 road projects as a site engineer; |
| 3 | 1xMaterials/Measurement Engineer: | Minimum of degree in Civil Engineering with at least Five (5) years’ experience in road works with at least | 1 road project as a Materials/Measurement Engineer; |
| 4 | 1 x Land Surveyor: | Minimum of Degree in Surveying and at least five (5) years of experience in road works with or Diploma in Civil Engineering and (10) years of experience in road experience | 2 road projects as a land surveyor or of 3 road projects as a land surveyor |
| 5 | 1 x Environmental, | Occupational Health and Safety Expert: A minimum qualification of a degree in a relevant discipline with at least two years’ experience in construction works | 1 road project as an environmental expert |
| 6 | 1 x Social Expert: | A minimum qualification of a degree in a relevant discipline with at least two years’ experience in construction works | 1 road project as a social Expert; |
| 7 | 5 x Foremen: | Minimum of Diploma in Civil Engineering with at least ten (10) years’ experience or least fifteen (15) years’ experience in road works | 5 projects as a foreman or Road Foremanship Certificate |

- liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MWK15 Billion or equivalent;

- Subcontracting agreement (clause 4.4 of the General Conditions of Contract) with the proposed subcontractors (the value of works proposed to be subcontracted in line with the contractors’ CIRA category).

  - A consistent history of contract non-performance, litigation or arbitration awards against the Applicant or any partner of a Joint Venture may result in disqualification.

  - The figures for each of the partners of a joint venture shall be added together to determine the Bidder’s compliance with the minimum qualifying criteria in (a) to (e)

  - for a joint venture to qualify, each of its partners must meet at least twenty-five (25) percent of minimum criteria (a), (b), and (e) above, and the partner in charge at least forty (40) percent of those minimum criteria. Failure to comply with this requirement will result in rejection of the joint venture’s Bid.

  - Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

9.	Participation by Micro, Small and Medium Enterprises

9.1  If  indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of preference for participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs as are necessary to confirm whether a particular contractor or group of contractors qualifies for preference based on being a micro, small and medium enterprise.

9.2  A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority, and Ministry of Trade.

9.3   The margin of preference for MSMEs shall be applied as follows:

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive Bids shall be classified into the following groups -

- Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference.

- Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to the percentage, as indicated in the MSME Order, of the Bid amount shall be added to Bids received from contractors in Group B.

# SECTION 4. BIDDING FORMS

LIST OF FORMS

- Bid Submission Form

- Beneficial Ownership Disclosure Form

- Price Schedules

- Bid Security Form (Bank Guarantee)

- Qualification Information Form A

- Qualification Form B: Pending Litigation

- Qualification Form C: Environmental, Social, Health and Safety Performance Declaration

- Qualification Form D: Current Contract Commitments / Works in Progress

- Qualification Form E: Financial Situation: Historical Financial Performance Qualification Form F: Average Annual Turnover

- Qualification Form G: Financial Resources

- Qualification Form H: General Experience

- Qualification Form I: Specific Experience 1

- Qualification Form J: Specific Experience 2

- Qualification Form K: Specific Experience in Key Activities 1

- Qualification Form L: Specific Experience in Key Activities 2

- Qualification Form M: Equipment

- Qualification Form N: Key Personnel

- Qualification Form O: Key Personnel – Resume and Declaration

- Qualification Form P: Schedule of Subcontractors

- Qualification Form Q: Unit Rates Analysis

- Environmental, Social, Health and Safety Declaration

Note: All forms, requiring information to be completed by the Bidder, are in bold in square brackets e.g. [insert date] etc.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder. Additional details on the price should be inserted if the contract payments are to be in various currencies. If the Bidder objects to the Adjudicator proposed by the Procuring and Disposing Entity, he should so state in his Bid, and present an alternative candidate, together with the candidate’s daily fees and biographical data, in accordance with clause 45 of the Instructions to Bidders.

BID SUBMISSION FORM

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda No.: [insert the number and issuing date of each Addenda];

- We offer to execute the [insert the name and procurement reference number of the Contract] in conformity with the Bidding Documents for the Contract Price of [insert amount in numbers and words];

- We offer to execute the works in accordance with the Work Program in conformity with the Bidding Documents for a period not exceeding [insert number of weeks or months]

The advance payment (which shall be payable in the same currencies and percentages as the Contract Price) required is:

| Amount | Currency |
| --- | --- |

- Our Bid shall be valid for a period of [specify the number of days that the Bid is valid for] calendar days from the date fixed for the Bid submission deadline in accordance with clause 19 of the ITB, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;

- We, including any subcontractors or suppliers for any part of the contract, have nationality from the following eligible countries: [insert the nationality of the Bidder, including that of all parties that comprise the Bidder, if the Bidder is a JV, and the nationality each subcontractor and supplier]

We have no conflict of interest in accordance with clause 4.3 of the ITB;

- Our firm, its affiliates or subsidiaries—including any subcontractors or suppliers for any part of the contract—has not been debarred from participation in public procurement by the Government of the Republic of Malawi, in accordance with  clause 4.4 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity.

- The following commissions, gratuities, or fees have been paid or are to be paid with respect to the Bidding process or execution of the Contract: [insert complete name of each Recipient, its full address, the reason for which each commission or gratuity was paid and the amount and currency of each such commission or gratuity]

| Name of Recipient | Address | Reason | Amount |
| --- | --- | --- | --- |

(If none has been paid or is to be paid, indicate “none.”)

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months):

| Name | Address |
| --- | --- |

The names and physical addresses of the Beneficial Owners our company are provided in the table below:

| Name | Address |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated Bid or any other Bid that you may receive.

- We accept the appointment of …………………………………………………………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator and propose instead that [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………………………... [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………………….[insert legal capacity of person signing the Bid]

Name: ………………………………………………………………………………………………………… [insert complete name of person signing the Bid]

Duly authorised to sign the Bid for and on behalf of:………………………………………………………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

Beneficial Ownership Disclosure Form

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder. In case of joint venture, the Bidder must submit a separate Form for each member. The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission. For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions: - directly or indirectly holding 5% or more of the shares - directly or indirectly holding 5% or more of the voting rights - directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder. - directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons; - has a significant stake in a company and on whose behalf activity of a company is conducted; or - 6. exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

PRICED SCHEDULES

(BILLS OF QUANTITIES OR ACTIVITY SCHEDULE)

(THE FOLLOWING TABLE SHALL BE USED WHEN CALCULATING FINAL BID PRICES FOR WORKS PROCUREMENTS)

| Description | Total Price |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| PPDA Levy (1%) |  |
| VAT |  |
| TOTAL |  |

Note to Bidders: This Bid Security should be on the letterhead of the issuing Financial Institution and should be signed by a person with the proper authority to sign the Bid Security. It should be included by the Bidder in its Bid, in accordance with ITB clause 20. Except for indicated fields, no changes shall be made in this template. Any changes made shall result to rejection of the Bid.

BID SECURITY (BANK GUARANTEE)

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

Whereas [insert complete name of Bidder] (hereinafter the “Bidder”) has submitted its Bid dated [insert date (as day, month and year) of Bid submission] for procurement reference no. [insert procurement reference no] for the construction of [insert name of Contract], hereinafter called the “Bid.”

KNOW ALL PEOPLE by these presents that WE [insert complete name of bank issuing the Bid Security], of [insert city of domicile and country of nationality] having our registered office at [insert full address of the issuing institution] (hereinafter the “Bank”), are bound unto [insert complete name of the Procuring and Disposing Entity] (hereinafter the “Procuring and Disposing Entity”) in the sum of [specify in words the amount and currency of the Bid security (specify the amount and currency in figures)], for which payment well and truly to be made to the aforementioned Procuring and Disposing Entity, the Bank binds itself, its successors or assignees by these presents.

Sealed with the Common Seal of this bank, this [insert day in numbers] day of [insert month], [insert year].

THE CONDITIONS of this obligation are as follow ___

1.	If the Bidder withdraws its Bid during the period of Bid validity specified by the Bidder in the Bid Submission Form, except as provided in clause 25.4 of the ITB; or

2.	If the Bidder, having been notified of the acceptance of its Bid by the Procuring and Disposing Entity, during the period of Bid validity, fails or refuses to:

(a)	execute the Contract; or

(b)	furnish the Performance Security; or

(c)	accept the correction of its Bid by the Procuring and Disposing Entity.

3. We undertake to pay the Procuring and Disposing Entity up to the above amount upon receipt of its first written demand, without the Procuring and Disposing Entity having to substantiate its demand, provided that in its demand the Procuring and Disposing Entity state that the amount claimed by it is due to it, owing to the occurrence of one or more of the above conditions, specifying the occurred conditions.

4. This guarantee shall remain in force up to and including twenty-eight (28) days after the period of Bid validity, as stated in the Bid Submission Form or as it may be extended by the Bidder, notice of which extension(s) to the Bank is hereby waived. Any demand in respect thereof should be received by the Bank no later than the above date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signed: [insert signature of person whose name and capacity are shown below]

Name: [insert complete name of person signing the Bid Security]	In the capacity of [insert legal capacity of person signing the Bid Security]

Duly authorized to sign the Bid for and on behalf of: [insert complete name of bank]

Dated on ____________ day of __________________, _______ [insert date of signing]

Note to Bidders: The information to be filled in by Bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in clause 5 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM A

| 1. Individual Bidders or Individual Members of Joint Ventures | 1.1 Constitution or legal status of Bidder: [attach copy] Place of registration: [insert] Principal place of business: [insert] Power of attorney of signatory of Bid: [attach] - Average annual volume of construction work performed in the previous number of years specified in Section 3, Evaluation and Qualification Criteria: [insert details in Form F] |
| --- | --- |
|  | 1.3 Work performed as prime Contractor on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date. [insert details in Forms H, I, J, K & L] |
|  | 1.4 Major items of Equipment proposed for carrying out the Works. List all information requested below. [insert details in Form M] |
|  | 1.5 Qualifications and experience of key personnel for administration and execution of the Contract. Attach biographical data. [insert details in Form N & O] |
|  | 1.6 Proposed subcontracts and firms involved. |
|  | 1.7 Financial reports for the last five (5) years: balance sheets, profit and loss statements, auditors’ reports, etc. List below and attach copies. |
|  | 1.8 Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. |
|  | 1.9 Name, address, and telephone, telex, and facsimile numbers of banks that may provide references if contacted by the Procuring and Disposing Entity. |
|  | 1.10 Information on any current litigation in which the Bidder is involved. [insert details in Form B] |
|  | 1.11 Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the Bidding documents. |

| 2. Joint Ventures | 2.1 The information listed in 1.1 - 1.10 above shall be provided for each partner of the joint venture. 2.2 The information in 1.11 shall be provided for the joint venture. 2.3 Attach the power of attorney of the signatory(ies) of the Bid authorizing signature of the Bid on behalf of the joint venture. 2.4 Attach the Agreement among all partners of the joint venture (and which is legally binding on all partners), which shows that - (a) all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms; (b) one of the partners will be nominated as being in charge, authorized to incur liabilities, and receive instructions for and on behalf of any and all partners of the joint venture; and (c) the execution of the entire Contract, including payment, shall be done exclusively with the partner in charge. |  |
| --- | --- | --- |
| 3. Additional Requirements |  | Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of clause 5.1 and clause 31 of the Instructions to Bidders, if applicable. |

QUALIFICATION FORM B: PENDING LITIGATION

| Pending Litigation, in accordance with Section 3 |  |  |  |
| --- | --- | --- | --- |
| - No pending litigation in accordance with clause 5.3(a)(ix) of Section 1 - Pending litigation in accordance with clause 5.3(a)(ix) of Section 1, as indicated below |  |  |  |
| Year | Outcome as Percent of Total Assets | Contract Identification | Total Contract Amount |
|  |  | Contract Identification: Name of Employer: Address of Employer: Matter in dispute: |  |
|  |  | Contract Identification: Name of Employer: Address of Employer: Matter in dispute: |  |
|  |  | Contract Identification: Name of Employer: Address of Employer: Matter in dispute: |  |

| Environmental, Social, Health, and Safety Performance Declaration in accordance with Section 3, Qualification Criteria, and Requirements |  |  |  |
| --- | --- | --- | --- |
| No suspension or termination of contract: A Client has not suspended or terminated a contract and/or called the performance security for a contract for reasons related to Environmental, Social, Health, or Safety (ESHS) performance since the date specified in Section 3, Qualification Criteria, and Requirements, clause 38 of the ITB. Declaration of suspension or termination of contract: The following contract(s) has/have been suspended or terminated and/or Performance Security called by a client(s) for reasons related to Environmental, Social, Health, or Safety (ESHS) performance since the date specified in Section 3, Qualification Criteria, and Requirements, clause 38 of the ITB. Details are described below: |  |  |  |
| Year | Suspended or terminated portion of contract | Contract Identification | Total Contract Amount (value, currency, exchange rate and MK equivalent) |
| [insert year] | [insert amount and percentage] | Contract Identification: [indicate complete contract name/ number, and any other identification] Name of Client: [insert full name] Address of Client: [insert street/city/country] Reason(s) for suspension or termination: [indicate main reason(s)] | [insert amount] |
| [insert year] | [insert amount and percentage] | Contract Identification: [indicate complete contract name/ number, and any other identification] Name of Client: [insert full name] Address of Client: [insert street/city/country] Reason(s) for suspension or termination: [indicate main reason(s)] | [insert amount] |
| … | … | [list all applicable contracts] | … |
| Performance Security called by client(s) for reasons related to ESHS Performance |  |  |  |
| Year | Contract Identification |  | Total Contract Amount (current value, currency, exchange rate and MK equivalent) |
| [insert year] | Contract Identification: [indicate complete contract name/ number, and any other identification] Name of Client: [insert full name] Address of Client: [insert street/city/country] Reason(s) for calling of performance security: [indicate main reason(s)] |  | [insert amount] |

QUALIFICATION FORM C: ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY PERFORMANCE DECLARATION

QUALIFICATION FORM D: CURRENT CONTRACT COMMITMENTS / WORKS IN PROGRESS

[The following table shall be filled in for the Bidder, each member of a Joint Venture / Consortium /Association]

Bidder’s Name: …………………………………………………………………………………… [insert full name]

Date: ……………/…………../………………… [insert day, month, year]

Joint Venture / Consortium / Association Member’s Name: ………………………………………………………………………………………………………………………… [insert full name]

Proc. Reference No: ………………………………………………………[insert Reference Number]

[Bidders and each partner to a JV/ Consortium / Association should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.]

| Name of contract | Client, contact address/tel/fax | Value of outstanding work | Estimated completion date | Average monthly invoicing over last six months (MWK /month) |
| --- | --- | --- | --- | --- |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| etc. |  |  |  |  |

QUALIFICATION FORM E: FINANCIAL SITUATION: HISTORICAL FINANCIAL PERFORMANCE

Bidder’s Name:  _______________________	Date:  _____________________

JV/ Consortium / Association Partner Legal Name:  ___________________

Procurement Reference No.:  _______________

To be completed by the Bidder and, if JV/ Consortium / Association, by each partner

| Financial information in MWK equivalent | Historic information for previous ______ (__) years (MWK equivalent in 000s) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Year 1 | Year 2 | Year 3 | Year … | Year n | Avg. | Avg. Ratio |
| Information from Audited Balance Sheet |  |  |  |  |  |  |  |
| Total Assets (TA) |  |  |  |  |  |  |  |
| Total Liabilities (TL) |  |  |  |  |  |  |  |
| Net Worth (NW) |  |  |  |  |  |  |  |
| Current Assets (CA) |  |  |  |  |  |  |  |
| Current Liabilities (CL) |  |  |  |  |  |  |  |
| Information from Income Statement |  |  |  |  |  |  |  |
| Total Revenue (TR) |  |  |  |  |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |  |  |  |  |

Attached are copies of financial statements (balance sheets, including all related notes, and income statements) for the years required above complying with the following conditions:

- Must reflect the financial situation of the Bidder or partner to a JV, and not sister or parent companies

- Historic financial statements must be audited by a certified accountant

- Historic financial statements must be complete, including all notes to the financial statements

- Historic financial statements must correspond to accounting periods already completed and audited (no statements for partial periods shall be requested or accepted)

QUALIFICATION FORM F: AVERAGE ANNUAL TURNOVER

Bidder’s Name:  _______________________	Date:  _____________________

JV/ Consortium / Association Partner Name:  ___________________

Procurement Reference No.:  _______________

| Annual turnover data (construction only) |  |  |
| --- | --- | --- |
| Year | Amount and Currency | MWK equivalent |
| *Average Annual Construction Turnover |  |  |

*Average annual turnover calculated as total certified payments received for work in progress or completed over the number of years specified in Section 3, divided by that same number of years.

QUALIFICATION FORM G: FINANCIAL RESOURCES

Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial means, net of current commitments, available to meet the total construction cash flow demands of the subject contract or contracts as indicated in Section 3: Evaluation and Qualification Criteria.

| Source of financing | Amount (MWK equivalent) |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| 4. |  |

QUALIFICATION FORM H: GENERAL EXPERIENCE

Bidder’s Name:  ____________________________     Date:  _____________________

JV/ Consortium / Association Partner Name:  ____________________________

Procurement Reference No.:  _______________

| Starting Month / Year | Ending Month / Year | Years* | Contract Identification | Role of Bidder |
| --- | --- | --- | --- | --- |
|  |  |  | Contract name: Brief Description of the Works performed by the Bidder: Name of Client: Address: |  |
|  |  |  | Contract name: Brief Description of the Works performed by the Bidder: Name of Client: Address: |  |
|  |  |  | Contract name: Brief Description of the Works performed by the Bidder: Name of Client: Address: |  |
|  |  |  | Contract name: Brief Description of the Works performed by the Bidder: Name of Client: Address: |  |
|  |  |  | Contract name: Brief Description of the Works performed by the Bidder: Name of Client: Address: |  |

*List calendar year for years with contracts with at least nine (9) months activity per year starting with the earliest year.

QUALIFICATION FORM I: SPECIFIC EXPERIENCE FORM 1

Bidder’s Name:  ________________________   	Date:  _____________________

JV/ Consortium / Association Partner Name: ________________________

Procurement Reference No.:  _______________

| Similar Contract Number: [insert specific number] of _ [insert total number of contracts required. | Information |  |  |
| --- | --- | --- | --- |
| Contract Identification |  |  |  |
| Award date Completion date |  |  |  |
| Role in Contract | Prime Contractor | Management Contractor |  Subcontractor |
| Total contract amount |  |  | MWK |
| If partner in a JV or subcontractor, specify participation of total contract amount | % |  | MWK |
| Client’s Name: |  |  |  |
| Address: Telephone/fax number: E-mail: |  |  |  |

QUALIFICATION FORM J: SPECIFIC EXPERIENCE FORM 2

Bidder’s Name:  ___________________________   	  Date:  _____________________

JV/ Consortium / Association Partner Name:  ___________________________

Procurement Reference No.:  _______________

| Similar Contract No. __[insert specific number] of ___[insert total number of contracts] required | Information |
| --- | --- |
| Description of the similarity in accordance with Section 3: Evaluation and Qualification Criteria.: |  |
| Amount |  |
| Physical size |  |
| Complexity |  |
| Methods/Technology |  |
| Physical Production Rate |  |

QUALIFICATION FORM K: SPECIFIC EXPERIENCE IN KEY ACTIVITIES 1

Bidder’s Name:  _________________________   Date:  ________________________

JV/ Consortium / Association Partner Name: _________________________

Procurement Reference No.:  __________________

|  | Information |  |  |
| --- | --- | --- | --- |
| Contract Identification | _______________________________________ |  |  |
| Award date Completion date | ______________________________________ _______________________________________ |  |  |
| Role in Contract |  Contractor |  Management Contractor |  Subcontractor |
| Total contract amount | _________________________ |  | ________ |
| If partner in a JV / Consortium / Association, specify participation of total contract amount | __________% | _____________ | ________ |
| Client’s Name: | _______________________________________ |  |  |
| Address: Telephone/fax number: E-mail: | _______________________________________ _______________________________________ _______________________________________ _______________________________________ |  |  |

QUALIFICATION FORM L: SPECIFIC EXPERIENCE IN KEY ACTIVITIES 2

Bidder’s Name:  ___________________________     	Date:  _____________________

JV/ Consortium / Association Partner Name:  __________________________

Procurement Reference No.:  __________________

| Description of the key activities in accordance with Section 3: | Information |
| --- | --- |

We, the undersigned, declare that the information contained in and attached to these forms is true and accurate as of the date of Bid submission:

Signed: [signature of person whose name and capacity are shown below]

Name: [insert complete name of authorized person signing the Qualification Form]

Duly authorised to sign the Qualification Form for and on behalf of: [insert complete name of Bidder or name of Joint Venture/ Consortium / Association]

Dated on ____________ day of __________________, _______ [insert day / month / year of signing]

QUALIFICATION FORM M: EQUIPMENT

The Bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key equipment listed in Section 3, Evaluation and Qualification Criteria. A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the Bidder.

| Item of equipment |  |  |
| --- | --- | --- |
| Equipment information | Name of manufacturer | Model and power rating |
|  | Capacity | Year of manufacture |
| Current status | Current location |  |
|  | Details of current commitments |  |
| Source | Indicate source of the equipment o Owned o Rented o Leased o Specially manufactured |  |

Omit the following information for equipment owned by the Bidder.

| Owner | Name of owner |  |
| --- | --- | --- |
|  | Address of owner |  |
|  | Telephone | Contact name and title |
|  | Fax | Telex |
| Agreements | Details of rental / lease / manufacture agreements specific to the project |  |

QUALIFICATION FORM N: KEY PERSONNEL

CONTRACTOR’S REPRESENTATIVE AND KEY PERSONNEL SCHEDULE

Bidders should provide the names and details of the suitably qualified Contractor’s Representative and Key Personnel to meet the specified requirements for each of the positions listed in Section III to perform the Contract. The data on their experience should be supplied using the Form P below for each candidate.

| 1. | Title of position: |
| --- | --- |
|  | Name |
| 2 | Title of position: |
|  | Name |
| 3. | Title of position: |
|  | Name |
| 4 | Title of position: |
|  | Name: |
| 5 | Title of position: |
|  | Name |
| 6 | Title of position: |
|  | Name |
| 7 | Title of position: |
|  | Name |
| 8 | Title of Position: |
|  | Name |

QUALIFICATION FORM O: KEY PERSONNEL

RESUME AND DECLARATION

CONTRACTOR’S REPRESENTATIVE AND KEY PERSONNEL

The Bidder shall provide all the information requested below.

| Position |  |  |
| --- | --- | --- |
| Personnel information | Name | Date of birth |
|  | Professional qualifications |  |
| Present employment | Name of Employer |  |
|  | Address of Employer |  |
|  | Telephone | Contact (manager / personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present Employer |

Summarise professional experience in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

| From | To | Company, Project, Position, and Relevant Technical and Management Experience* |
| --- | --- | --- |

DECLARATION

I, the undersigned [ insert either “Contractor’s Representative” or “Key Personnel” as applicable] , certify that to the best of my knowledge and belief, the information contained in this Form PER-2 correctly describes myself, my qualifications and my experience.

I confirm that I am available as certified in the following table and throughout the expected time schedule for this position as provided in the Bid:

| Commitment | Details |
| --- | --- |
| Commitment to duration of contract: | [insert period (start and end dates) for which this Contractor’s Representative or Key Personnel is available to work on this contract] |
| Time commitment: | [insert period (start and end dates) for which this Contractor’s Representative or Key Personnel is available to work on this contract] |

I understand that any misrepresentation or omission in this Form may:

- be taken into consideration during Bid evaluation;

- result in my disqualification from participating in the Bid; and

- result in my dismissal from the contract.

Name of Contractor’s Representative or Key Personnel: [insert name]

Signature: __________________________________________________________

Date: (day month year): _______________________________________________

QUALIFICATION FORM P: SCHEDULE OF SUBCONTRACTORS

With reference to clause 4 of the ITB, the Bidder shall list below the subcontractors he intends to appoint for the various items of work on these contract alternatives may be mentioned.

| Sections of the Works | Value of subcontract | Subcontractor (name and address) | Experience in similar work |
| --- | --- | --- | --- |

QUALIFICATION FORM Q: ANALYSIS OF MAIN- UNIT RATES (1)

SCHEDULE V-1

ANALYSIS OF MAIN UNIT RATES

| Item No. (See Bills) | Materials MWK | Labour MWK | Plant, Equipment Transport MWK | Fuel & Lubricants MWK | Overheads & Profit MWK | Total Rate MWK |
| --- | --- | --- | --- | --- | --- | --- |

Signed:___________________________________________________________________

Name and Position: ________________________________________________________

(Bidder)

QUALIFICATION FORM R: ANALYSIS OF MAIN UNIT RATES (2)

SCHEDULE V-2

ANALYSIS OF MAIN UNIT RATES – BREAKDOWN OF RATES

| Item | Description | Qty | Unit | Rate | Amount |
| --- | --- | --- | --- | --- | --- |
| No. |  |  |  |  |  |
| A | Materials |  |  |  |  |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| Total for Materials |  |  |  |  |  |
| B | Labour |  |  |  |  |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| Total for Labour |  |  |  |  |  |
| C | Plant, Equipment & Transport |  |  |  |  |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| Total for Plant, Equipment & Transport |  |  |  |  |  |
| D | Fuel and Lubricants |  |  |  |  |
| Total for Fuel and Lubricants |  |  |  |  |  |
| E | Overheads and Profits |  |  |  |  |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| Total for Overheads and Profits |  |  |  |  |  |

Signed:___________________________________________________________________

Name and Position: ________________________________________________________

(Bidder)

ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION

We, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

1. PLEDGE THAT-

- We have read, understood, and will comply with-

- the Environment Management legal framework or policies in conservation and management of the environment;

- all necessary and appropriate measures to protect and manage the environment;

- all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources; and

- all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters.

2. AGREE THAT -

- In the event that our Bid is successful, we shall, within fifteen (15) days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation  Plan.

- Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters.

- The Procuring and Disposing Entity shall forfeit the Environmental, Safety and Health Security if we are in breach of the obligation(s) under the Bid conditions.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name:………………………………………………………………………………………………………. [insert complete name of person signing the Bid]

Duly authorised to sign the Bid for and on behalf of:…………………………………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

# SECTION 5. ELIGIBLE COUNTRIES

Procurement Reference Number:

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if -

(a)	as a matter of law of  the Government of the Republic of Malawi prohibits commercial relations with that country; or

(b)	by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

# SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts.

For the purposes of this provision, unless the context otherwise requires-

#### "   “coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract;

#### “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels;

#### "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act (Cap 7:04 of the Laws of Malawi);

#### "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and

#### “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation.

The Government will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question;

The Authority shall debar a Bidder from participation in public procurement for a specified period if it at any time determines that the Bidder has engaged in corrupt, fraudulent, collusive, or coercive practices in competing for, or in executing, a contract; and

The Procuring and Disposing Entity shall cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the Bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- Bidders shall read and understand this provision; and will show acknowledgement of having read and understood the provision by signing Compliance Form below.

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________,  hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

- AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: [insert complete name of person signing the Bid]

Duly authorised to sign the Bid for and on behalf of: [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

# SECTION 7. SCHEDULE OF REQUIREMENTS

A. Scope of Works

  - Description of the Works

    - General

The description is only an indication of the work to be executed and may change due to unforeseen conditions on-site. All construction activities are not necessarily listed below and only the main and major activities are dealt with. The scope of works may change due to changes in site conditions, or as directed by the Employer or the Engineer.

The Chitipa – Ilomba – Tanzania Border Road is an earth road which lies in the northern part of Malawi and is approximately 31 km long. The road is the shortest route to the neighbouring Tanzanian town of Isongole in Irenje District. The road connects with the upgraded section of M009 at Chitipa Boma and traverses through the low lying areas towards the northern western tip of Malawi and leaves the M009, into T301 and D002 to connect with the Tanzanian Border at Songwe River.

The Project will involve the completion of the upgrading of the existing earth road to bitumen standard with a 6.8m carriageway and 1.5m shoulder on each side, the construction of Kaghoma bridge and drainage structures.

    - Pavement

The pavement structure for the Chitipa – Ilomba (T301/D002) Road in Chitipa shall consist of 50mm hot mix asphalt surfacing, Crushed Stone Base and 175mm Subbase constructed using chemically stabilized gravel with CBR>30%. The pavement layers shall rest on 150mm thick selected layer constructed using materials with soaked CBR>15%.

Fills shall be constructed as shown on drawing using materials with soaked CBR > 15%.

    - Structures

  - Prefabricated Pipe Culverts

The works shall involve installation of approved 900mm diameter precast concrete pipes with ogee type joint on Class A bedding. Drainage schedule has been provided in the book of drawings indicating location, size and length of each culvert. The total length of prefabricated culverts of 900mm diameter sizes is 60m.

  - Box Culverts

The works shall involve construction or installation of 2.0 m x 4.50 m Box Culvert,

4 cells of 2.0 m x 4.0 m Box Culvert, 2.0 m x 3.0 m Box Culvert, 2.0 m x 4.50 m Box Culvert, 2.0 m x 4.0 m Box Culvert, 2.0 m x 3.0 m Box Culvert, 4 cells of 2.0 m x 4.50 m Box Culvert.

  - Bridges

The project will involve construction of new single 14m span bridge across Kaghoma River at km 24+800. The bridge shall have 6.8m carriageway with 1.2m shoulder on each side.

    - Appurtenant Works

  - General

The road will include among others, the following appurtenant works; construction of construction of bus stops, construction of concrete lined drains, construction of road reserve boundary, kerbing works and shaping of road slopes.

  - Road Signage

All temporally road signs used during construction shall conform to requirements of SABS 1519 and shall be in Retro-reflective material.

Road sign details have been provided in the book of drawings. Unless advised otherwise by the Engineer, the upgrading works shall install all signs as indicated in the Book of Drawings. Section 5400 of the Technical Specifications applies.

  - Road Markings

Road marking details are provided in the book of drawings. Retro-reflective paint complying with the requirements of SABS 731-1 for type 1 paint shall be used.

Road marking will typically involve the white centreline, yellow lane demarcation lines, stop marking, pedestrian markings among others.

  - Drawings

A book of drawings shall be provided comprising layout of plans, long sections, cross sections, typical sections, drainage structures, road sign schedule, standard drawings, List of Control Points and the Setting out data.

  - Site Facilities

- Site facilities available

The Contractor will be responsible for the provision of a suitable site for his construction camp and to provide accommodation for his personnel.

The Contractor shall make his own arrangements for the supply of potable water and water for construction purposes, and for electrical power and all other services as well as all safety and security measures necessary for the duration of the contract. In his Bid he must make provision for all negotiations and procurement of these services, which will be deemed to have been included in his tendered rates.

- Site facilities required

The following facilities shall be required on the campsite:

  - Contractor’s offices

  - Engineer’s laboratory

  - Storage facility for building materials and equipment

  - workshop for servicing vehicles and road construction machinery

  - Parking areas

  - Portable water

  - Sanitation and Refusal disposal facilities

  - Generators to compliment power supply

- Security and Social Issues

The Contractor will be responsible for the security of his personnel and construction plant on and around the Site of the Works and for the security of his camp, and no claims in this regard will be considered by the Employer. Special attention shall be given to vulnerable groups such as women, girls and disabled workers. No underage persons shall be employed.

  - Climate

The project site is in Chitipa District and the climatic conditions for this project area is as shown in the table below;

Climatic Conditions

| Item | Chitipa |
| --- | --- |
| Mean Rainfall | 800 – 1200mm |
| Mean Temperature | 17 – 27 0C |

  - Features Requiring Special Attention

- Roads and Site to be Kept Clean

The Contractor shall make sure that roads and campsite are always kept clean. The Contractor shall provide dustbins designated for different waste types such as for biodegradable and non-biodegradable, and harmful and non-harmful. Oils from workshop and other waste from road construction shall only be disposed of in approved areas.

- Working Hours

The Contractor shall come up with working schedule for all employees. Working hours for all employees shall be properly spelt out. However, the working hours should be in accordance with the Malawi Government labour laws.

  - Construction Period

The estimated time for the Completion of the Upgrading of Chitipa – Ilomba (T301/D002) Road is twenty-four (24) calendar months.

  - Extension of Time Resulting from Abnormal Rainfall

It must be noted that the extension of time resulting from abnormal rainfall shall not be regarded as an event for which compensation can be claimed. This means that no payments whatsoever will be made, including any payments under time related obligations, regardless of the period of time by which the Time for Completion may be extended due to abnormal rainfall

B. BILLS OF QUANTITIES OR ACTIVITY SCHEDULE

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 7 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be initialled by a person with the proper authority to sign documents for the Bidder.

Priced Schedules

(Bills of Quantities or Activity Schedule)

PREAMBLE TO BILL OF QUANTITIES

  - This Preamble and the Bill of Quantities form an integral part of the Contract Documents. The Bill of Quantities shall be read in conjunction with the Instruction to Bidders, Conditions of Contract, Technical Specifications, and Drawings.

  - The quantities given in the Bill of Quantities are estimated and provisional. The basis of payment will be the actual quantities of work ordered and carried out, as measured by the Contractor and verified by the Engineers’ Representative and valued at the rates and prices tendered in the priced Bill of Quantities, where applicable, and otherwise at such rates and prices as the Supervisors’ Representative may fix within the terms of the Contract.

  - The rates and prices tendered in the priced Bill of Quantities shall, except in-so-far as it is otherwise provided under the Contract, include the cost of all constructional plant, labour, supervision, materials tests for quality control, erection, maintenance, insurance, profit, taxes and duties, together with all general risks, liabilities and obligations set out or implied in the Contract.

  - A rate or price shall be entered against each item in the priced Bill of Quantities, whether quantities are stated or not. The cost of items against which the Contractor has failed to enter a rate or price shall be deemed to be covered by other rates and prices entered in the Bill of Quantities.

  - The whole cost of complying with the provisions of the Contract shall be included in the items provided in the priced Bill of Quantities. Where no items are provided the cost shall be deemed to be distributed among the rates and prices entered for the related items of work.

  - General directions and descriptions of work and materials are not necessarily repeated nor summarised in the Bill of Quantities. The bidder is advised to refer to the relevant sections of the contract documentation before entering prices against each item in the priced Bill of Quantities.

  - Provisional Sums included and so designated in the Bill of Quantities shall be expended in whole or in part at the direction and discretion of the Supervisors’ Representative after obtaining approval of the Employer.

  - The method of measurement of completed work for payment shall be in accordance with the measurement and payment item in the General and Particular Specifications.

  - Errors will be corrected by the Employer for any arithmetic errors in computation or summation as follows:

  - where there is a discrepancy between amounts in figures and in words, the amount in words will govern; and

  - where there is a discrepancy between the unit rate and the total amount derived from the multiplication of the unit price and the quantity, the unit rate as quoted will govern.

  - The quantities of material or work stated in the Bill of Quantities shall not be regarded as constituting authorisation to the Contractor to order materials or execute work. The Contractor shall obtain the Supervisors’ Representatives’ detailed instructions for all work before ordering any materials or executing work or making arrangements therefore.

  - The short descriptions given of pay items in the Bill of Quantities are only for the purposes of identifying the items and providing specific details. Reference shall be made inter alia to the Drawings, Specifications, and Conditions of Contract for more detailed information regarding the extent of the work entailed under each item.

  - All rates and sums of money quoted in the Bill of Quantities shall be in Malawi Kwacha.

  - The Priced Bill of Quantities for the rehabilitation of the Golomoti – Monkey Bay Turn Off (M10) Road from Junction M05/M010 at Golomoti to Junction M010/S128 at Mtakataka/Monkey Bay turn Off shall be priced and summed up.

  - For the purpose of this Bill of Quantities, the following works shall have the meanings hereby assigned to them:

| Unit | The unit of measurement for each item of work as defined in the Project Specifications. |
| --- | --- |
| Quantity | The number of units of work for each item. |
| Rate | The payment per unit of measurement at which the Tenderer tenders to do the work. |
| Amount | The product of the quantity and the rate tendered for an item. |
| Lump sum | An amount tendered for an item, the extent of which is described in the Bill of Quantities, the Specifications or elsewhere but the quantity of work of which is not measured in any units. |
| Prime Cost Sum | A sum included in the Contract and so designated in the Schedule of Quantities for covering the prime cost of goods or materials to be supplied under the Contract and for delivery of such items to storage on site. The amount to be paid to the Contractor shall be the actual price paid by him |

  - The Tenderer shall fill in a rate or a lump sum for each item where provision has been made for it even where no quantities are given. Items against which no rate or lump sum has been entered in the tender will not be paid for when the work is executed, as it is assumed that the contractor does not wish to receive payment for any such work.

The Tenderer shall fill in a rate against all items where the words “rate only” appear in the amount column. The provisions of Subclause 1209(f) of the Standard Specifications shall apply to rate-only items.

The Tenderer shall not group a number of items together and tender one rate or lump sum for such group of items. The Tenderer also shall not indicate against any item that full compensation for such item has been included in another item. The Tenderer may not tender a zero rate for any item, failure to comply with this requirement may result in the tender being rejected.

The tendered lump sums and rates shall be valid irrespective of any change in the quantities during the execution of the Contract.

  - The works as executed will be measured for payment in accordance with the methods described in the Contract Documents under the various payment items, notwithstanding any custom to the contrary.

Attention is directed to the provisions of Clause 1220 of the Standard Specifications regarding the measurement of quantities for payment. Except where otherwise specified as in Clause 1220, the net measurements or mass of the finished work in place shall be taken for payment but excluding any volume or mass of work in excess of that ordered.

  - The short descriptions of the payment items given in the Bill of Quantities are only for the purposes of identifying the items and providing specific details. Reference shall be made, inter alia, to the drawings, Standard Specifications, Particular Specifications, General Conditions of Contract and Special Conditions of Contract for more detailed information regarding the extent of the work entailed under each item.

  - The pay item numbers that appear in the Bill of Quantities refer to the corresponding item numbers in the Standard Specifications. Certain pay item numbers appearing in the Schedule of Quantities are prefixed by the letter PS. This letter signifies that either:

    - a new pay item not listed in the Standard Specification has been described and listed in the Particular Specification, or

    - an existing measurement and / or payment clause occurring in the Standard Specifications has been clarified and / or modified in the Particular Specifications.

The listing of pay items with or without a PS prefix where relevant has, as stated, been done to assist Bidders and in no way absolves Bidders from the obligation to familiarise themselves with, and bid on the basis of the Documents as a whole. No claim based on errors in or omissions of pay item numbers and / or the prefix PS in the columns headed “Pay Item” in the Bill of Quantities will be considered.

  - Where a Pay Item has the unit of measurement equal to % the Tenderer must enter the percentage required by him under the “Rate” column, e.g. for 5% enter 5,0 not 0,05.

- SCHEDULE OF DAY WORK RATES

  - The Schedule of Day work Rates shall be used to calculate the payment due for work ordered as Day works, and for which no rates appear in the Bill of Quantities.

  - The description of the work, quality of materials and standard of workmanship shall be as described in the Specification.

  - The prices quoted in the Schedule shall cover all the necessary insurances, use and maintenance of ordinary plant (e.g. barrows, running planks, hand pumps, hand tools and appliances generally), superintendence, overhead charges and profit, and in the case of mechanically operated plant, the wages of the operator and assistant, consumables, stores, fuel, maintenance and transportation of plant to site.

  - The time of gangers, overseers, or charge hands working with their gangs, is to be paid for under appropriate items, but the time of Foremen is not to be included. This is to be covered by superintendence. The time actually spent by labour on work shall be recorded for this purpose.

  - The price quoted for labour shall be for straight time only and no overtime rates shall be payable. Rates shall only be paid for artisans working at their trade.

  - The rates for materials shall cover distribution within the site. Delivery to the site shall be charged in addition.

  - The cost of additional watching and lighting and other incidentals specially necessitated by Day works shall not be paid for separately.

  - The rates given in the Schedules shall be taken to be operative at the time of Bidding.

  - Day works shall be carried out on the written instructions from the Supervisors’ Representative.

  - The description of the plant should be completed by the Bidder when bidding.

C. DRAWINGS

| List of Drawings |  |
| --- | --- |
| Drawing No. | Drawing Title |

D. TECHNICAL SPECIFICATIONS

### SECTION 1200:	GENERAL REQUIREMENTS AND PROVISIONS

# PS1204:		PROGRAMME OF WORK

Replace the first paragraph with the following

- APPROVED PROGRAMME

The contractor shall submit his programme of work, within the time stated in the Particular Conditions of Contract, to the Engineer for approval. The Contractor shall ensure that he has at his disposal adequate staff with the necessary expertise to develop and maintain the network programme for the duration of the contract and to provide the information required by the Engineer as specified hereafter.

The programme shall be in a bar chart (Gantt chart) or any other time-activity format acceptable to the Engineer and shall clearly show:

- The proposed rate of progress in order to complete the works within the required period as tendered, showing the various activities, their duration and proposed resources (major plant and labour) for each element of the works.  Sufficient details shall be provided to enable the Engineer to be able to assess construction progress.  All activities, including establishment on site, trimming and finishing and the completion of all minor ancillary works are to be included in the programme.

- The sequence of activities and any dependencies (time or resource related) between them; the critical path activities; the amount of slack time for non-critical activities;

- Key dates in respect of work to be carried out, or information, etc., to be provided, by others.

- The anticipated value of work to be done during each month and any

- Other information specifically required by the Engineer.

When drawing up his programme, the Contractor shall, take into consideration:

- Testing and approval process of materials and works

- Expected weather conditions and their effects.

- Known physical conditions or artificial obstructions.

- The accommodation and safeguarding of public traffic.

- Dealing with, altering and installing services.

- Expropriation and all other actions required in terms of this contract.

The following details shall be submitted together with the programme:

- The number of working hours per day, working days per week, assumed holiday or shut-down periods on which the programme is based.

- The overall labour and major plant resources on which the programme is based.

- The detailed traffic accommodation proposals on which the programme is based (road or lane closures, lengths of sections to be worked, timing etc).

- The rate of production for major works components such as layer works, subbase, base, surfacing, etc (units per day / hour) on which the programmed time for carrying out the work is based.

The Contractor shall base his initial programme of work on the scope of the work as described in the Particular Specifications.  This programme shall be reviewed on a regular basis by the Contractor in accordance with changing circumstances, delays and amendments to the work ordered by the Engineer as a result of further examinations made by him.

Minor revisions to the approved programme may be introduced from time to time by mutual agreement between the Contractor and the Engineer.  Should the Engineer believe that a major revision of the programme is required, the Contractor will be notified in writing and a revised programme shall be submitted within two weeks of receipt of such notification.

It should be noted that it is in the Contractor's interest to provide a comprehensive programme giving as much information as possible about the times allowed for the various activities as well as resource or other limitations affecting the programme, since the approved programme may be used to evaluate any claims in terms of the General Conditions of Contract for extensions of time.

- REPORTING

The Contractor shall submit to the Engineer, at least three working days before each monthly site meeting copies of the following:

- The construction programme with progress charts and programme graphs updated to reflect the actual progress to date.

(ii)	A summary of progress on site over the month preceding the site meeting.  The report shall be in the form of a detailed narrative to the construction programme.

(iii)	Details of activities running late, indicating what steps have been or will be taken to ensure that the work is completed within the specified time.

- A report on all labour, plant and materials on site, according to sub-clauses PCC 4.20 and PCC 6.10 of the Particular Conditions.

PS 1205 Workmanship and Quality Control

Add the following paragraphs:

(a)	Inspections

The Engineer will inspect the works during the course of construction. The Contractor shall accord the Engineer every facility he may require for such inspection.

Any inspection, examination or test either of workmanship, material or performance shall not exempt the Contractor from any of his obligations under the contract. The liability of the Contractor for defective material or workmanship that may be discovered after any portion or portions of the work have been put into service shall be in accordance with the General Conditions of Contract notwithstanding that the defective item(s) may have previously been inspected and approved by the Engineer.

(b)	Workmanship

(i)	Testing of Materials

The Contractor shall carry out tests on materials and workmanship in order to ensure compliance with the requirements of the Specifications. The frequency of testing shall be in accordance with the requirements of the Standard and/or Technical Specifications, but the Contractor may increase the specified frequency in order to have more control of the quality of the Works.

All tests shall be conducted in accordance with the latest published methods listed below.

1.	British Standards Institution (BSI)

2.	American Society for Testing and Materials (Abbreviation: ASTM)

3.	American Association of State Highways and Transportation Officials (AASHTO)

4.	Technical Methods For Highways (TMH): Standard Methods of Testing Road Construction Materials, TMH1 2nd Edition, published by the South African Department of Transport, 1986.

5.	South African Bureau of Standard Specifications, (SABS)

6. 	MS-2 Asphalt Mix Design Methods (Asphalt Institute)

In addition to the above, standard specifications or test methods of other bodies may be referred to in these specifications, or test methods may be described where no acceptable standard methods exist.

The Contractor shall submit all test results to the Engineer on a weekly basis. Work for which process control test results have not been submitted to the Engineer will not be approved.

(ii)	Contractor’s Laboratory

The Contractor shall establish on site and maintain in good order a laboratory with approved equipment sufficient to enable him to carry out process control testing required to ensure conformity with the Specifications. As a minimum, the laboratory shall be equipped with equipment and facilities as specified for the Engineer's Laboratory.

The laboratory equipment to be used shall be tested and calibrated by the supplier or by his Agent before their use for process control testing. The calibration shall be done at the beginning of the Contract and shall be repeated every six months or at such other interval as the Engineer may decide. Proof of calibration in the form of certificates shall be submitted to the Engineer not later than seven days after calibration, failing which the Engineer shall declare the equipment unsuitable for use on the project. Results of any tests carried out prior to the testing and calibration of the equipment will be rejected.

Results of compaction densities obtained by nuclear density testing equipment shall be compared to results obtained by the sand replacement method at the rate of one sand replacement test per fifteen nuclear density tests.

The Contractor shall employ a qualified Materials Engineer with at least eight (8) years’ experience to supervise the Contractor’s Laboratory and quality control tests. Prior to deploying the Materials Engineer to the site, the Contractor shall submit to the Engineer his academic details and Curricula Vitae. The Engineer reserves the right to reject the proposed personnel if in his opinion he is not qualified or sufficiently experienced to supervise or carry out quality tests.

The Contractor shall maintain record of test results in files clearly numbered in a logical sequence.  The Engineer shall have access to the records at all times.

(iii)	Laboratory for the Consulting Engineer

The Contractor shall establish on site and equip a laboratory for use by the Engineer. The laboratory building shall be constructed in accordance with the drawings and specifications issued by the Engineer as part of the Contract drawings. Alternatively, the Contractor can identify rented laboratory building to the satisfaction of the Engineer.

The Contractor shall supply, install and insure the laboratory equipment required by the Engineer for carrying out quality assurance tests. The laboratory shall be equipped with all equipment, chemicals, supplies, etc. necessary for the performance of the following tests and procedures as described in:

BS 1377:1975 “Methods of Testing Soils for Civil Engineering Purposes”.

Method

1.5 	Preparation of disturbed samples for testing

2.1	Test 1:	Determination of the moisture content

1 (A):	Standard method (oven-drying method)

1 (B):	Subsidiary method (sand bath method)

2.2	Test 2  Determination of the liquid limit

2 (A)	Method using cone Penetrometer

2 (B)   	Method using the Casagrande apparatus

2.3	Test 3	Determination of the plastic limit

2.4	Test 4	Determination of the plasticity index

2.6	Test 6  Determination of the specific gravity of soil particles

6 (A)		Method for fine, medium-and coarse-grained soils

6 (B)		Method for fine-grained soils

2.7	Test 7	Determination of the particle size distribution

7 (A)		Standard method by wet sieving

4.2	Test13	Determination of the dry density moisture contents relation - 4.5kg Rammer method

4.4	Test 15 Determination of the dry density of soil on the site

15 (A)	Sand replacement method suitable for fine, medium and coarse-grained soils: small pouring cylinder method (minimum of 3 sets)

15 (B)  	Sand replacement methods suitable for fine- medium, and coarse-grained soils: large pouring cylinder method (minimum of 2 sets)

5.1	Test 16   Determination of the California Bearing Ratio (CBR)

Notes:

(1)	Two soaking tanks 1500mm x 1000mm x 600mm deep to be provided, together with apparatuses for measuring swell (minimum 10No).

(2)	At least 25 moulds and 75 x 2 kg surcharge weights to be provided.

BS 812: 1975 “Methods for Sampling and Testing of Minerals Aggregates Sand and Fillers”.

Part 1:	Sampling size, shape and classification, Sections 5 to 7 inclusive

Part 2:	Physical Properties, Section 5 to 7 inclusive

Part 3:	Mechanical Properties, Section 7 and 8

BS 1881: 1970 “Methods of testing Concrete”

Part 2:	Slump test, Compacting factor test

Part 3:	Making and curing test cubes

Note:

At least 30 moulds shall be supplied and the curing tank shall not be used for any other purpose.

Part 4:	Test compressive strength of test cubes

Note:

The gap between the platens of the compressive testing machine must be capable opening to at least 200mm.

U.K. Transport and Road Research Laboratory publication - Road Note 39

“Road Note 39 – Recommendations for Road Surface Dressing”

Road Tray (Appendix1)

BS 1707: 1970 “Hot Binder Distributors for Road surface Dressing”

Depot Tray Test

Standard Methods for Testing Penetration and its Products” 1959 (Institute Petroleum)

IP 49/72 Penetration Test for Bitumen

ASTM Designation: C88-78 Standard Method of Testing for Soundness of Aggregates by use of Sodium Sulphate or Magnesium”

AASHTO Designation: T176-65 Standard Method of Test for Plastic Fines in Graded Aggregates in Soils by Use of the Sand Equivalent Test”

The equipment will be as scheduled in these Particular Specifications. All equipment furnished for use by the Engineer must be calibrated as stated above. The Contractor shall maintain throughout the contract period both the laboratory building and the laboratory equipment and shall replace any damaged equipment within seven days of receiving the Engineer’s instruction to do so.

The laboratory equipment will revert to the Employer at the end of the contract.

Payment for the provision of laboratory building and equipment shall be as tendered by the Contractor. The tendered rate shall include full compensation for procuring, furnishing, insuring, calibrating and maintaining in good order all the facilities and equipment.

(c)	Cost of Testing

(i)	Testing by Contractor and Provision of Samples

The cost of testing of materials and workmanship undertaken by the Contractor to ensure compliance with the Specification, including the submission of certificates that materials supplied by him comply with the relevant BS or other Specifications, shall be deemed to be covered by the prices tendered under the relevant items in the Bills of Quantities for work in which the materials are incorporated. The same applies to samples that the Contractor must supply to the Engineer for testing.

(ii)	Additional Testing

The Engineer shall have the right to take samples and/or order any additional tests on workmanship or materials supplied by the Contractor. Where such additional testing is required, the cost thereof to the Contractor shall be determined.  If the costs of individual tests are not itemised in the Bills of Quantities the cost of additional testing shall be classified as additional work under Clauses 7.4 and 13 of the General Conditions of Contract, provided that the test indicate compliance with the Specification otherwise the cost shall be borne by the Contractor.

PS1206	THE SETTING-OUT OF WORK AND PROTECTION OF BEACONS

Add the following at the beginning of this clause:

“Upon issuance of the order to commence, the Engineer shall issue to the Contractor a set of setting out co-ordinates and the Contractor shall set out the works accurately and shall be responsible for any error(s) which may occur in such setting out and shall amend and rectify such error(s) at his own expense.

In addition to setting out data, the Engineer shall issue to the Contractor co-ordinates of Benchmarks and control points for survey control. The Contractor shall, prior to using the benchmarks and control points, check their accuracy and confirm in writing to the Engineer that the information is sufficient for setting out the works accurately. Should discrepancies be found in the information issued by the Engineer, the Contractor shall afford the Engineer the opportunity to investigate the discrepancies and correct them within a period of seven calendar days. The Contractor shall programme his work in such a way that this requirement will not impact negatively on the rate of progress of the works, and no claim for extension of time will be entered pursuant to this requirement.

The Contractor may if he deems it necessary, establish additional control points. Any additional control points shall consist of steel pegs set in concrete at positions not likely to be affected by the works. The coordinates of the established points shall be issued to the Engineer in the form ‘Name, Y, X, Z’”

Replace the second sentence in the second paragraph with:

“In case that the reference beacons along the contract sections have been either destroyed, displaced or damaged before the handing over of the site to the contractor, then the Engineer will arrange to have new reference benchmarks reinstated by the Contractor at 500 m intervals and the cost of the re-establishment work will be paid under Section 1800 (Day Works) of the Particular Specifications”.

## PS1207:	NOTICES, SIGNS AND ADVERTISEMENTS

Add the following to the second paragraph:

“See Volume 2 Drawing No. CP-ILOM-TZ/TSH/601 of this document for details of the Notice Boards.  These boards shall remain in position until the end of the maintenance period, and shall then be removed without delay.

PS 1208:	MEASUREMENTS

Add the following clause to 1208 (c):

“Cross-sectional levels shall be taken at not greater than 20-metre intervals jointly from the Surveyor of the Engineer and of the Contractor and agreed between the Contractor and the Engineer before any clearing, grubbing, stripping of topsoil or earthworks are undertaken and at any stage thereafter that the Engineer may require.

Cross sections shall be taken at the same interval as the setting out. The cross sections shall cover the entire road reserve and shall contain a minimum of seven points consisting of centre point and three equally spaced points on either side of the centre point. The points shall be in line and perpendicular to the centre line. The results of the survey shall be certified by the Engineer as soon as possible”

## PS1209		PAYMENT

- Rates to be inclusive

Replace “period of maintenance” in the last line of the first paragraph with “Defects Notification Period”

(c)	The meanings of certain phrases in payment clauses

(i)	Procuring and furnishing (materials)

Insert “duties” in the sixth line of sub-clause after “all tax”

PS 1210	CERTIFICATE OF PRACTICAL COMPLETION OF THE WORKS

Replace the words “Certificate of Practical Completion of the Works” in title and text of this clause by the words “Taking-over Certificate”

Amend the sub-clauses of this clause as follows:

In (b) add "and all storm water drainage works;"

Add the following to this clause:

“Opening of a section of road to public traffic before the requirements of Clause 1210 have been met, if such opening should be allowed by the Engineer, shall not entitle the Contractor to the issue of a Taking-over Certificate for the road section in question.”

PS 1214:	Contractor’s Activities in Respect of Property Outside the Road Reserve and of Services Moved, Damaged or Altered

Add the following clause 1214 (f):

“Any of the Contractor’s activities outside the Site or outside the road reserve on property not belonging to the Employer shall be exclusively at the Contractor’s own risk, cost and responsibility.”

## PS1215	EXTENSION OF TIME RESULTING FROM ABNORMAL RAINFALL

Method (ii) (Critical – path method) will be used for determining the extension of time due to inclement weather.

Add the following table B1215/1 at the end of section on Method (ii) (Critical Path)

Abnormal rain as shown in table B1215/1 shall be proven by rainfall records for previous five years (prior to contract start date) from Department of Climate Change and Meteorological Services. For the purposes of calculating an extension of time due to climatic conditions the number of days in excess of the number of working days anticipated to be lost due to climatic conditions as shown in Table B1215/1 shall be taken into account:

Table B1215/1: Anticipation days (“n” working days) lost due to climatic conditions:

| Month | Rain days |
| --- | --- |
| January | 18 |
| February | 13 |
| March | 12 |
| April | 6 |
| May | 1 |
| June | 0 |
| July | 0 |
| August | 0 |
| September | 0 |
| October | 1 |
| November | 4 |
| December | 13 |
| Total | 68 |

Source: Department of Climate Change and Meteorological Services

The Engineer will certify a day lost due to climatic conditions only if:

(a)	no work on the critical path according to the latest approved programme for completion of the works could be carried out during that specific working day or if

(b)	only 30% or less of the work force and plant planned for that specific day, could work.

The extension of time as a result of climatic conditions will be calculated monthly as being equal to the number of days certified by the Engineer as lost due to climatic conditions, less the number of days in Table B1215/1.  The total extension of time for the contract will be the sum of the monthly extensions.  If the total extension of time for the Contract is negative it will be disregarded when determining the completion date(s)."

Add the following new clauses:

PS 1230:	LAND AVAILABLE

The land available to the Contractor free of charge shall be as follows:

i.	The land occupied by the Permanent Works

ii.	The land occupied by approved (usually existing and public) temporary diversion routes

Land to be identified and acquired by the contractor

The contractor shall provide and maintain such buildings and sheds as maybe required for the use of the workmen employed in the works and for the storage of materials requiring protection and shall remove the same from the site on completion of the works and make good everything disturbed. The contractor shall be responsible for identifying a suitable site for location of the temporary facilities that he may require and he shall obtain approval of usage of any piece of land from the relevant local authority

The contractor shall make all negotiations and pay all necessary compensation fees for any land he may require, including borrow areas for fill material outside the road reserve (if approved by the Engineer).

The land available to the contractor is not necessarily the land to be cleared, which shall be indicated by the Engineer. The costs of clearing for the purpose of borrowing material, opening access roads, working space, or any other purpose of work not forming part of the permanent works shall be borne by the contractor.

PS 1231:	COMPENSATION

The costs of agreed compensation for disturbance of buildings, crops, trees and relocation of fences and services within the land available free of charge shall be paid by the Contractor through the Contract and he shall be reimbursed net under the relevant items in the Bill of Quantities.

The cost of all other compensation shall be borne by the Contractor.

The Contractor shall cooperate with the appropriate authorities and shall make all necessary arrangements to agree compensation.  Construction of the Works shall not commence until compensation has been agreed.

PS 1232:	GRAVES AND TOMBS

Areas which contain graves and/or tombs within the Site shall be cleared by the Contractor, who shall seek assistance from the District Commissioner to obtain the consent of the Village Authorities to enter into each of such areas for the removal and reburial of corpses and remains.  Compensation to the Village Authorities, if any, shall be reimbursed to the Contractor through the Contract under the relevant item in the Bill of Quantities.

PS 1233:	COPIES OF SUPPLY ORDERS

The Contractor shall provide the Engineer with copies of all orders for the supply of materials and goods required in connection with the Works.

PS 1234:	DRAWINGS

The Contractor shall be issued with two copies of each of the Drawings forming part of the Contract documents, as well as with two copies of any further drawings which may be issued by the Engineer from time to time.  Any additional copies of drawings required by the Contractor may be purchased from the Engineer.”

PS 1235:	AMENITY AND ACCESS

The Contractor shall ensure that, in carrying out the Works, he causes no damage by plant, workmen, flooding, dust, subsidence or otherwise to property. He shall take all precautions to the satisfaction of the Engineer to ensure that such hazards are avoided and public amenity maintained.  The Contractor shall make good, forthwith and at his own cost, any damages and inconveniences caused by him; failing to do which the matter shall be treated under Sub-Clause 4.18 of the General Conditions of Contract, as amended, and the Employer shall be entitled to employ and pay other persons to carry out the same, and all costs shall be recoverable from the Contractor by the Employer in accordance with such sub-clause.

PS 1236:	DUST CONTROL

The Contractor shall take appropriate measures to protect the Works and adjacent private and public property from dust contamination and nuisance.”

## PS1237	REPORTING OF INCIDENTS AND ACCIDENTS

“The Contractor shall report every incident and accident which occurs on the road, within the extent of the Works, to the Engineer within twenty-four (24) hours of such incident /accident, irrespective of whether such incident/accident has a bearing on the damage to the works or to persons, property or things.  The report must be in writing and must contain full particulars of the incident/accident.  Photographs of each incident/accident shall also be included in the report.  The Engineer has the right to conduct any or all enquiries, on either the Site or elsewhere, as to the causes and consequences of any such incident/accident.  The Contractor shall also keep a comprehensive record of all incidents/accidents which occur on the road and shall make such records available to the Engineer on demand.”

PS 1238	MAXIMISING THE USE OF LABOUR

This Contract has been established and shall be priced as equipment-based type of road works project.  However, the Roads Authority is desirous of making a contribution towards reducing the level of unemployment in the project area.  To this end, the following items of work have been identified as suitable for maximising the use of manual labour.

(a)	Bush clearing and the removal of roots from the surface after grubbing has been done by machine, and loading of such roots for transport to disposal areas.

(b)	Excavation and backfilling for culverts, kerbs and channels, including for removal of existing units, all to a maximum depth of 1,5m.

(c)	Excavations for guardrail posts, road sign footings, guide blocks and erosion protection works, all to a maximum depth of 1,5m.

(d)	Constructing gabion baskets and stone pitching.

(e)	Placing of kerbs and concrete edging.

(f)	Erection of road signs.

(g)	Base correction.

(h)	Back chipping during surfacing operations.

(i)	Trimming of cut slopes, and final trimming of shoulder breakpoints and fill slopes.

(j)	Trimming of open drains, side drains, inlet and outlet channels of culverts.

(k)	Trimming of catch - water drains, mitre banks and mitre drains.

(l)	Finishing off the road, road reserve and borrow pits.

Tenderers are required to submit a tender for the Works under the condition that at least the items listed above must be done using manual labour.  Additional information and suggestions which will further the use of labour will be viewed in a positive light.

The Employer is also desirous of making a contribution towards equal opportunities for women, not only in respect of labour, but also throughout the human resource base of the Contract.  No gender restrictions shall apply throughout the workforce.  In respect of the latter and as far as is practicable, the Contractor is required to employ at least 15% of his unskilled labour force from the feminine gender. In addition, only Malawian citizens shall be employed in the Contractor's unskilled labour force.

## PS1239	ENVIRONMENTAL AND SOCIAL IMPACT CONTROL

Before any work is commenced on the Site, the Contractor's site management staff including foremen shall attend an environmental and social awareness-training course presented by the Engineer.  The Contractor shall liaise with the Engineer prior to the Commencement Date to fix a date and venue for the course.  The Engineer will provide the course content.  The Contractor shall provide a suitable venue and ensure that the specified employees attend the course.

The environmental/social awareness-training course shall be held in the morning during normal working hours. The information presented at the course shall be communicated to the Contractors employees on the site, to any new employees coming onto site after the initial training course and to his suppliers as required by the Project Specification. The Contractor shall ensure that all attendees sign an attendance register, and shall provide the Engineer with a copy of the attendance register the day after each course.

In addition to aspects of design which are intended to avoid or reduce environmental impact, and also in addition to normal good construction practice expected to the Contractor, the requirements of the Project Environmental Management Plan (see under Section 6 D Clause A: Environmental and Social Impact Management) shall be strictly followed. Any non-compliance with these requirements which could have been avoided in the opinion of the Engineer may be considered sufficient grounds for withholding payment of part or all of the amounts to be paid for the pay item PS13.05.

PS 1240          HIV/ AIDS PREVENTION PROGRAMME

The contractor shall from the commencement of the contract through his Environmental, Occupational Health and Safety Expert (EOHSE) implement a generic AIDS awareness training programme for all permanent and temporary workers of the main contractor and all subcontractors. The type of training; the number of trainees and the cost of all training shall be as agreed by the Employer and the Engineer.

The training material for the structured training programme shall, as far as possible, be accredited by the Ministry of Health and be delivered by suitably qualified and accredited trainers. The training programme shall be subject to the approval of the Employer and the Engineer, and the Contractor shall if so, instructed by the Engineer, alter or amend the programme and course content.

The Contractor shall be responsible for the provision of everything necessary for the delivery of the training programme, including the following:

- Transport of the selected workers (as necessary)

- Stationery and all other necessary materials.

No separate payment will be made for the training venue and everything necessary for the delivery of the training.

All Training shall take place during normal working hours and the Contractor shall make adequate allowance in his programme of work to accommodate the training to be provided. All selected workers shall be remunerated in respect of all time spent undergoing skills training. The EOHSE must make sure that the specified workers attend the HIV/AIDS Prevention training courses.

The Contractor shall keep comprehensive records of the training given to each worker and whenever required shall provide copies of such records to the Engineer. At the successful completion of a course, each candidate shall be issued at the Contractor’s own cost with a certificate.

The Contractor shall ensure that all attendees sign an attendance register, and shall provide the Engineer with a copy of the attendance register the day after each course. The EOHSE shall prepare a quarterly report on the programme.

SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15% of the tender sum

Add the following new pay items:

PS 13.02: 	Authorised Compensation					Unit

- Allow Provisional Sum for Authorised Compensation……………..…………………………………   Provisional Sum

- Handling Cost and profit in respect of item PS 13.02(a) ………………   %

The contractor has to enter the percentage in the rate column and then calculate the amount for pay item PS13.02 (b)

PS13.03:	Relocation of Services:

(a)	Allow Provisional sum allowed for the protection and

relocation of services …………………………..…………… Provisional sum

(b)	Handling Cost and profit in respect of item PS13.03 (a) ……………….  %

The contractor has to enter the percentage in the rate column and then calculate the amount for pay item PS13.03 (b)

The provisional sum allowed under sub item (a) shall be expended to cover the actual costs for the protection and moving of services by the Contractor and others.

The provisional sums shall be expended only with the approval of the Engineer.

PS 13.04: Construction of Sign Boards …………………………………………….   No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

PS 13.05: Contractor’s Environmental and Social Obligations

| (a) | Allow for the undertaking and implementation of all |  |  |
| --- | --- | --- | --- |
|  | the requirements of the Environmental and Social Management |  |  |
|  | Plan | Lump Sum | 1.00 |
| (b) | Provide assistance and environmental training to staff | Prov. Sum | 1.00 |
| (c) | Handling costs, profit and overheads in respect of item 13.05 (b) | % |  |
| (d) | Provide Road Safety training to staff and the surrounding community | Prov. Sum | 1.00 |
| (e) | Handling costs, profit and overheads in respect of Item 13.05 (d) | % |  |

The provisional sum for sub-item PS13.05 (a), allows for the undertaking and implementation of all the requirements of the Environmental and Social Management Plan as specified in the document. This money shall only be expended on the direct instruction of the Engineer. The reimbursement shall be for the final invoice amount from the training institution/s (excluding VAT) for the training.

The provisional sum allowed for pay item PS13.05 (b) is to remunerate the trainees attending the environmental training at a rate per hour for attending training. The reimbursement shall be for actual attendance (total hours).

The percentage tendered for pay item PS13.05 (c) shall be applied to the amounts expended under pay items PS13.05 (b) to generate an amount that covers all the monies required by the Contractor for managing the training, paying the trainees, and any other costs that may arise from these payments, including any Contractor’s profits and overheads.

The provisional sum allowed for pay item PS13.05 (d) is to remunerate the trainees attending the Road Safety training at a rate per hour for attending training. The reimbursement shall be for actual attendance (total hours).

The percentage tendered for pay item PS13.05 (e) shall be applied to the amounts expended under pay items PS13.05 (d) to generate an amount that covers all the monies required by the Contractor for managing the training, paying the trainees, and any other costs that may arise from these payments, including any Contractor’s profits and overheads.

PS13.06    HIV/Aids and Occurrence of Pandemic Awareness Training

(a) Training……………………………………………………   Provisional Sum

(b)	Remuneration of the workers undergoing training ……  Provisional Sum

(c) Occurrence of pandemic (i.e., covid 19) Prevention Measures…Provisional Sum

(d) Handling costs and profit in respect of sub-items PS13.06 (a), (b)

and (c) (state as % and extend as an amount) ………………………  %

The provisional sum for sub-item PS13.06 (a), allows for the provision of the HIV/AIDS awareness training programme delivered as specified in the document. This money shall only be expended on the direct instruction of the Engineer. The reimbursement shall be for the final invoice amount from the training institution/s (excluding VAT) for the training.

The provisional sum allowed for pay item PS13.06 (b) is to remunerate the trainees at a rate per hour for attending training. The reimbursement shall be for actual attendance (total hours).

The provisional sum for sub-item PS13.06 (c), allows for provision of prevention of any outbreak i.e COVID-19 or Cholera. The payment shall only be when there is an outbreak and the contractor is indeed employing prevention measures.

The percentage tendered for pay item PS13.06(d) shall be applied to the amounts expended under pay items PS13.04 (a) (b) and (c) to generate an amount that covers all the monies required by the Contractor for managing the training, paying the trainees, and any other costs that may arise from these payments, including any Contractor’s profits and overheads.

PS13.07 Public Awareness Programmes

- Television and Radio Broadcast and Print Media Publications	P.S.

- Sensitization of the surrounding community	P.S

- Handling costs and profit in respect of sub-items PS13.07(a) and (b)

- (stated as % and extend as an amount) ………..................……………......	%

The provisional sum for sub-item PS13.07 (a) allows for the provision of the Public awareness programmes and activities provided as specified in the document. This money shall only be expended on the direct instruction of the Engineer. The reimbursement shall be for the final invoice amount from the public awareness service providers (excluding VAT).

The provisional Sum allowed for pay item PS13.07 is to remunerate the public awareness service providers at a rate agreed by the Roads Authority. The reimbursement shall be for actual costs incurred.

The percentage tendered for pay item PS13.07 (b) shall be applied to the amounts expected under pay items PS13.07 (i) to generate an amount that covers all the monies required by the Contractor for managing the public awareness activities, paying the media service providers, and any other costs that may arise from these payments, including any Contractor’s profits and overheads.

SECTION 1400 HOUSING, OFFICES AND LABORATORIES FOR THE ENGINEER'S SITE PERSONNEL

Replace clause 1401 with the following:

PS 1401: SCOPE

This Section covers the provision of accommodation for the Engineer’s supervisory staff. This accommodation shall be the necessary laboratory accommodation, and the provision of all the necessary services.

Replace clause 1402 with the following:

PS 1402: LABORATORY

Provision of the laboratory facilities for the use of the Engineer shall be ready for occupation and use by the Engineer within thirty (30) days (including days for mobilization) of the official commencement date.

The Contractor shall make all arrangements and pay all necessary charges for the provision and maintenance of the following services to the laboratory to the satisfaction of the Engineer:

  - Supply of electricity for power and light (220-250 v AC, 50 Hz) from a public utility.

  - Supply of clean, fresh, potable water; either from a public utility or provided directly by the Contractor.

  - Disposal of sewage and waste water

  - Split type remote controlled air conditioners. The air conditioners shall have 2.5 KW minimum power and shall be capable of heating during winter.

  - Laboratory furniture and equipment specified in these specifications. The furniture and equipment shall be new and of quality acceptable to the Engineer.

  - A full-time attendant to clean and service the laboratory including all utensils and sundries for that purpose.

Furniture and Equipment for the Engineer's Laboratory Office

The Contractor shall supply new furniture and new equipment for the Engineer's laboratory as hereinafter listed falling under the item in the Bills of Quantities.

Furniture for the Engineer's Laboratory Office

Item											No

Desks with lockable drawers (1830 x 915mm)						2

Table (1830 x 915mm)									1

Chair (2 arm chairs) robust and comfortable						6

Shelves (1830 x 1200mm x 350mm) with backing					1

Cupboards (1730mm x 900mm x 550mm (3shelves and lock)				1

Steel filing cabinets (1300mm x 460mm x 600mm) deep with 4 drawers on

runners and lock									4

Wall Board										1

Electric heater, 750watt minimum rating							1

Waste paper baskets									2

Punch											1

Stapling machine									1

Stationary as required

Laboratory Installations and Equipment, etc.

All equipment, chemicals supplies etc. necessary for the performance of the tests and procedures as described in BS 1377:1975 “Methods of Testing Soils for Civil Engineering Purposes" shall be supplied by the Contractor.

Please refer to PS 1205 (b) (iii) regarding the required tests and procedures.

Miscellaneous Laboratory Equipment

The laboratories shall be supplied and resupplied, as often as necessary, with the minimum level of ancillary equipment as detailed below:

Item											No.

Metal thermometers reading to 260°C							2

Graduated steel rule									2

1000ml capacity measuring cylinder graduated to 5ml					2

500ml capacity measuring cylinder graduated to 5ml					2

1000m1 beaker										2

Hotplate gas type									4

Wire gauze for use with hotplate								12

Tablespoons										3

Chisel blade, 200mm x 25mm								4

Knife, 200mm blade with wooden handle						4

Trowel, 150mm blade approximately 100mm wide					4

Plastic bucket with lid, approximately 300mm diameter and 450mm deep			6

Pick with handle									15

Shovel with handle									15

Panga											12

Metal drying trays, 1 metre square with raised edges					10

Paint brush 25mm wide									3

Hard bristle broom with handle								2

Scientific calculator									4

Ovens (aggregate volume 1m3 minimum)						2

Rain gauges										3

Plus, printed test forms, samples bags, hessian, plastic or 4 ply paper for large disturbed samples, towels soap etc., as required.

Asphalt testing Laboratory Equipment

Stability and Flow machine (Digital)							1

Centrifugal extractor									1

Specimen Mould Assembly         							6

Specimen Extractor									1

Compaction Hammer 									1

Compaction Pedestral 									1

Specimen Mould Holder 								1

Breaking Head 										1

Loading Jack										1

Oven											1

Mixing Apparatus									1

Water Bath (Controller 25oC)								1

Kinematic viscometer (complete)							1

100mm Core drilling machine with 12 core drills						1

MTD test equipment									1

Penetrometer with 5 needles								1

Softening point devices including heating						1

Miscellaneous Equipment for Asphalt Testing

- Containers									12

- Mixing Tools									1

- Thermometers									1

- Balance (2.5 kg)									1

- Gloves										4

- Rubber Gloves									4

- Marking Crayons									12

- Scoop										1

- Spoon

- Sample ejecting device

- Stability mould										1

- 2 Litre flasks									2

- Thin-film Oven									6

- Vernia Caliper									2

- Timer										1

For the laboratory works of the Engineer the Contractor has to provide as much semi-skilled workers as requested.

The laboratory shall at all times be provided with a sufficient stock of consumables equipment to allow for usage, breakage and deterioration. In the event of any item of equipment becoming unserviceable through any cause the Contractor shall, at his own cost, order replacements or spare parts to be air-freighted from the same suppler. This replacement equipment shall be new and as determined by the Engineer.

Protective Clothing for the Supervisor's Staff

- dust coats for laboratory staff including replacements as required

- sets of water-proof coats for all staff, mouth musk, safety boots and safety helmets for each of the staff; including replacements as required.

The reticulation network and the wiring installation of the laboratory shall be maintained at the highest standard of safety and reliability, with particular reference to the earthing installation and safety/protective devices.

The Contractor shall be responsible for providing all sanitary services necessary for keeping latrines in a clean, neat and hygienic condition. When no municipal sewage treatment is available, the Contractor shall provide the necessary septic tanks for all latrines. Waste water and septic tank effluent shall be discharged into properly designed French drains. The Contractor shall also make provision for the removal of all rubbish. Where the construction of septic tank or water - borne sewage scheme is unfeasible, the Contractor shall construct conservancy tanks and make arrangements for the removal and disposal of sewage.

The Contractor shall provide adequate 24 - hour security for the laboratory. The Contractor shall take all reasonable precautions to prevent unauthorized entry to the laboratory and to ensure overall security of camps, field laboratories and the site in general.

Maintenance or Replacement of Equipment and Provision of Consumables

All equipment provided shall be kept full serviceable at all times by the Contractor. The Contractor shall repair/replace any defective equipment within three days after notification by the Engineer's staff. The contractor shall also provide all stationary, paper (including also special photo quality paper) Laser Jet toner cartridges, colour and black ink cartridges, USB Memory sticks, CDs and CD storage containers required by the Engineer.

The Contractor shall insure the equipment against any loss, damage or theft and he shall indemnify the Engineer against any claims in this regard. This equipment shall be available for use by the Engineer at all times. The Contractor shall maintain the equipment in good working order and keep it clean throughout the contract period.

Ownership of all the buildings, services, fittings and associated works, the laboratory furnishing shall remain with the contractor at the end of the Contract or at such earlier date as the Engineer may instruct with the exception of the laboratory equipment and furniture which shall revert to the Employer.

PS1407	MEASUREMENT AND PAYMENT

Change pay item 14.01, 14.02 and 14.03 as follows:

PS14.01	Office and Laboratory Accommodation

Item	Unit

  - Office building as specified in drawings ………………..........................Lump sum

  - Laboratory building as specified in drawings……………………………Lump Sum

Add: The tendered lump sums shall include all the materials and standards for office and laboratory in accordance with the details given in Particular Specifications and in the drawings.

PS14.02	Office and Laboratory Furniture

  - Office furniture as specified in the Particular Specifications .............	Lump sum

  - Laboratory furniture as specified in the Particular Specifications.............	Lump sum

Add: The tendered lump sums shall include all the furniture for laboratory in accordance with the details and as listed in Particular Specifications.

PS14.03	Laboratory Fittings, Installations and Equipment

    - Office fittings, installations and equipment (except computers) ............Lump sum

    - Laboratory fittings, installations and equipment.....................................Lump sum

Add: The tendered lump sums shall include all the fittings, installations and equipment for laboratory in accordance with the details and as listed in Particular Specifications.

Amend Pay Item 14.08 as follows:

PS14.08 Services

(a)	office and laboratory............	Month

The tendered amounts shall include all specified services rendered to laboratory.

Amend pay Item 14.11 in the Standard Specifications as follows:

S14.11		 Supply and Maintenance of Engineer's Vehicles

Item 											Unit

- Supply of double cab pick-up as approved					No

- Supply of single cab pick-up as approved					No

- Operate and maintain vehicles as specified for an average of 5000 km per month

vehicle-month

- Operate vehicles as specified for travel distance in excess of an average 5000 km per month											Km

The vehicles to be supplied will be as specified under Clause PS 14.05.

Payment for operating and maintaining vehicles under item S14.11, subitems (c) and

(d) above, for the Engineer, his staff and the Employer's, will be made as follows:

- By rates per vehicle month, subitem (b). Such rates shall include for the first 5000km (as indicated) per vehicle travelled in any calendar month. Should a vehicle be used for less than 5000 km (as indicated) in a particular month, then the unused distance shall be offset against months when the distance travelled exceeds 5000 km (as indicated).

- By a rate per km, subitem (c), over and above the first 5000 km (as indicated) per vehicle travelled in any one calendar month, subject to the condition mentioned in (i) above.

The rates bid by the Contractor shall include for provision of the vehicle, all licensing, insurance, fuel, lubricants, maintenance and repairs and replacement of the vehicles should this be considered necessary by the Engineer.

Upon completion of the Contract, the vehicles specified herein shall revert to the Employer.

PS14.12 Security at Engineers’ Office and Laboratory.......................	month

The unit of measurement for the supply of security guards shall be the month. The rate tendered shall be full compensation for the supply of security guards, including transport, weapons, equipment and uniforms as may be applicable, as well as all other costs necessary to provide the security service. The tendered rate shall be payable for as long as the security service is required and provided, but not after the official completion date of the Contract`

PS14.13 Provision of semi-skilled labour for use by the Engineer

- Provision of Labourers	P.S.

- Handling cost and profit in respect of PS 14.13 (a)

(State % and extend as an amount)	%

Payment under Item PS14.13 (a) shall be made monthly and the amount due to the Contractor will be equal to the total of the actual amount paid to the Engineer's semiskilled labourers plus the direct cost of medical and pension benefits, Workmen's Compensation, sick leave and holiday pay, incurred by the Contractor in respect of the Engineer's semi-skilled labourers. The Contractor shall advise the Engineer of the full monthly cost for each semi-skilled labourer engaged. No payment other than that provided above will be made in respect of the employment of semi-skilled labourers for the Engineer. Contract price adjustment will not apply to this item.

PS14.14 Survey equipment for use by the Engineer

Item	                       Unit

- Supply and maintenance of the survey equipment for use by the Engineer.............Month

The unit of measurement for the supply and maintenance of the survey equipment as described in detail in the Particular Specifications including software programme shall be per month.

The tendered rate shall include full compensation for the supply and maintenance of the equipment. The tendered sum per month will be payable for as long as the equipment is required but not after the official completion date of the contract.

SECTION 1500		ACCOMMODATION OF TRAFFIC

## PS1502		GENERAL REQUIREMENTS

Add the following new sub – clauses:

(i)	Moving and display of signs

The Contractor shall adhere strictly on the sign layout and spacing shown on the drawings or directed by the Engineer.  Any sign not required for or which is in contradiction with the prevailing situation, shall be removed or covered with non-transparent material without delay.  Where permanent signs are to be covered it shall be done with non-plastic material.

(j) Failure to comply with provisions for the accommodation of traffic

The failure of or refusal by the Contractor to construct and / or maintain diversions, barricades, traffic signs or road markings at the proper time, or to take the necessary precautions for safety and convenience of public traffic as specified or instructed by the Engineer, shall be sufficient cause to suspend payment on this contract until the required construction or maintenance has been completed to the satisfaction of the Engineer considering that there is a risk to the public.  Such stoppage of the payment will not be acceptable as a reason for extension of time or additional compensation.

PS1503	TEMPORARY TRAFFIC-CONTROL FACILITIES

Add the following after the second paragraph:

No work may proceed in any section where accommodation of traffic is required until such time as the relevant requirements with regard to sign posting are met. The Contractor shall keep sufficient surplus signs, delineators and barricades on the site to allow for the replacement of damaged or missing items within a period of three hours of instructions having been given by the Engineer.

- Traffic-control devices

Add the following:

Sufficient flagmen suitably trained and equipped as detailed in sub-clause (g) below, shall be provided at all designated access points on public road to and from the working areas to the satisfaction of the Engineer.  The flags shall be at least 750 mm x 500 mm on a stick of adequate length.

When movable temporary signs are used, provision shall be made for sandbags on the sign bases to prevent the signs from being overturned by wind or eddies behind moving traffic, as detailed in sub-clause (h) below.

- Road signs and barricades

Add the following:

Retro-reflective material for temporary road signs shall comply with the requirements of SANS 1519.

The retro-reflective coefficients determined according to the methods of SANS 1519, shall be at least 60% of the values given in Table 1 of SANS 1519.

The classes shall be as specified in Sub-clause 5402 (g) of the Standard Specifications.

Road signs that do not comply with these standards shall be cleaned and re-tested or removed from the site and replaced with approved road signs.

(c)	Channelization devices and barricades

Add the following:

Delineators shall comply with the following requirements:

- A minimum contrast ratio of 4 shall exist between the yellow call 1 retro-reflective material and the black non-reflective material.

- Delineators shall be affixed in a flexible manner to the base units and shall be able to withstand wind speeds of at least 60 km/h without overturning.  The bases shall be stabilised by placing of sandbags.

- The bottom edge of the delineator shall not be more than 200 mm above the road surface.

Cones (red-orange, fluorescent) with minimum height of 750 mm may be used as supplementary traffic-control facilities to delineators, but only for short-term lane deviations during daylight.  Lane closures or deviations continuing into night time shall be demarcated by delineators.  The maximum spacing between delineators or cones is 30 m.

Add the following sub-clauses:

- Worker clothing and safety jackets

All construction workers shall wear high visibility clothing when on the construction site.  Any worker working on or adjacent to a trafficked road shall wear a safety jacket (reflective vests).  Overalls shall be either orange or red-orange or yellow in colour with retro-reflective strips.  Raincoats shall be bright orange or red-orange.

In addition, all flagmen are to be distinctly dressed in high visibility orange overalls, a safety jacket similar to those worn by traffic officers as supplied by Sparks and Ellis or similar approved.

Safety jackets shall also be made available to the Engineer and all his staff free of charge.

PS 1517: Measurement and Payment

Pay item 15.09 is not applicable and deleted. Pay items 15.01, 15.02, 15.03, 15.04, 15.05, 15.06, 15.07, 15.08, 15.10, 15.11, and 15.12 are combined and included into one pay item 15.01.  The layout out for accommodation of traffic shall be in accordance with drawings No. C5-02, C5-03 and C5-04.

Item											          Unit

## PS15.01: Accommodating traffic, including all notices, signing, construction, providing, maintaining and reinstating temporary diversions ………………………................................……………………………………………...km

SECTION 1600	OVERHAUL

PS1601	Scope

Free-haul distance for this contract will be unlimited.  Subsequently no separate payment will be made for overhaul irrespective of the material or the distance hauled.

SECTION 1700	CLEARING AND GRUBBING

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause re-clearing and re-grubbing.  Payment for clearing and grubbing shall be made only once.  Re-clearing and re-grubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  Penalty, depending on its size and age, shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

The tendered rate for Item No. 17.01 shall also include the full compensation for safe removal of existing road signs with the resulting holes backfilled with acceptable material. The removed road signs shall be properly stacked and stored; the Engineer shall give an instruction for the final custody. Waste material shall be disposed of in accordance with the Specifications.

Add the following new pay items:

PS 17.04: Demolition, dismantling, removal and clearing of existing structures

Item											Unit

PS 17.04(a):	Masonry structures ………………………………..…………………… m3

PS 17.04(b):	Mass Concrete structures …………………………..…………...….… m3

The tendered rate shall include full compensation for demolition or dismantling of the existing structures, clearing and disposal of the waste material from site including unlimited haulage costs.

Add the following new Pay Items:

Item	Unit

PS17.05 Treatment of ant or termite holes with approved Insecticide...........	Square metre (m2)

The rate shall be for full compensation for scarifying the surface to a depth of at least 100mm, applying approved ant poison, remixing and spreading of the material. The application rate shall not be less than 5 litres of diluted ant poison per square metre or as directed by the Engineer. The concentrated chemical shall be diluted in accordance with the manufacturer’s recommendations. Mixing of the poison and its application shall be carried out in the presence of the Engineer or his representative."

Create the following new section:

# SECTION PS 1800:	DAY WORKS

# PS1801	SCOPE

This section covers the listing of day work items in accordance with the General and/or Special Conditions of Contract determining payment for work which cannot be quantified in specific units in the Schedule of Quantities, or for work ordered by the Engineer during the construction period which was not foreseen at tender stage and for which no applicable rate exists in the Schedule of Quantities.

# PS1802	ORDERING OF DAYWORK

No day work shall   be undertaken unless written authorisation has been obtained from the     Engineer.

# PS1803	MEASUREMENT AND PAYMENT

# Item 									Unit

# PS18.01 PERSONNEL DURING NORMAL WORKING HOURS

| (a) | Unskilled labour | Hr |
| --- | --- | --- |
| (b) | Semi - skilled labour | Hr |
| (c) | Skilled labour | Hr |
| (d) | Ganger | Hr |
| (e) | Flagmen | Hr |
| (f) | Operators | Hr |
| (g) | Foremen | Hr |
| (h) | Surveyor | Hr |
| (i) | Lab technician | Hr |

# Item 									Unit

PS18.02 PERSONNEL OUTSIDE NORMAL WORKING HOURS

| (a) | Unskilled labour | Hr |
| --- | --- | --- |
| (b) | Semi - skilled labour | Hr |
| (c) | Skilled labour | Hr |
| (d) | Ganger | Hr |
| (e) | Flagmen | Hr |
| (f) | Operators | Hr |
| (g) | Foremen | Hr |
| (h) | Surveyor | Hr |
| (i) | Lab technician | Hr |

# Item 									Unit

## PS18.03	PLANT

| (a) | Tip truck 10m³ | Hr |
| --- | --- | --- |
| (b) | Motor grader Complete with scarifer (CAT 14G or equivalent) | Hr |
| (c) | Wheeled loader (CAT 980G or equivalent) | Hr |
| (d) | TLB (CAT 450 or equivalent). | Hr |
| (e) | Water bowser self-propelled (10 000L) | Hr |
| (f) | Vibratory roller (123KW, 10T) | Hr |
| (g) | Pneumatic roller (123KW, 10T) | Hr |
| (h) | Grid roller with tractor (5 to 7T) | Hr |
| (i) | Tractor (110HP) | Hr |
| (j) | Tracked excavator (CAT 223 or equivalent) | Hr |
| (k) | Bulldozer (CAT D8R or equivalent) . | Hr |
| (l) | Excavator (CAT 225 or equivalent) | Hr |
| (m) | Concrete Mixer (15HP, 0.5m3) | Hr |
| (n) | Water Pump | Hr |
| (o) | Light duty Vehicle | km |
| (p) | Flatbed truck | km |

The unit of measurement for items PS18.01 to PS18.03 shall be the hour for the item of plant or   personnel. Non- working hours for the plant breakdown, lack of operator or any other reason shall not be measured. The item shall be taken from the time that the personnel and /or plant depart until return.

Measurement shall only be for work instructed and directed by the Engineer where the Engineer may consider no other appropriate rates is available in the schedule of quantities. Prior to the commencement of any work by the labourers described under items PS18.01 and PS18.02, the Contractor must obtain written consent from the Engineer regarding the classification of all labourers in terms of “unskilled”, “semi-skilled”, and “skilled labourers”

The tendered rates for labour for the items PS18.01 and PS18.02 shall include full compensation to cover overhead charges and profit, leave pay, bonuses, subsistence allowances, Employer’s contributions, additional payment for over overtime where applicable, insurances, housing, site supervision, use of small hand tools and appliances, non-mechanical plant, operative and contingent costs relating to the supply of personnel.

The tendered rates for Plant for item PS18.03 shall be all-inclusive hire charge for the use of trucks or plant/equipment including driver or operator and shall apply only to vehicles, plant and equipment nominated in writing by the Engineer. The tendered rate for item PS18.04 shall include full compensation for the operating costs including fuel, maintenance, depreciation, administrative and contingent costs as well as profit

# Item 											Unit

### PS18.04	 Materials

(a)	Procurement of materials ………………...... Provisional Sum

(b)	Contractor’s handling costs, profit 	and all other charges in respect of sub item PS18.04(a).	  Percentage (%)

The Unit of measurement for sub-item PS18.04(a) shall be the amount actually paid for the procurement of materials to be purchased and shall be made in accordance with the provision of the General Condition of Contract. Only the actual quantities of materials used, as verified by the Engineer, shall be paid for.

The percentage tendered for sub-item PS18.04(b) shall be the percentage of the amounts actually paid for the procurement of the materials as ordered under the sub-item PS18.04(a) and shall be in full and final compensation in respect of the Contractor’s handling costs, profit, and all other charges in connection with the procurement and supply of the materials to the point of usage.

## Item 							        	    	     Unit

# PS18.05	Transport

- LDV	…………………..………………………...     kilometre (km)

- Flatbed truck …………………………………….....     kilometre (km)

The unit of measurement for item PS18.05 shall be the kilometre distance that the vehicle travelled for transporting personnel and/or Plant. All travelling shall be approved by the Engineer.

The tendered rate for item PS18.05 shall include full compensation for the cost of the vehicle including fuel, maintenance, depreciation and running costs.

The above-mentioned tendered rates shall be in full compensation for the various items, as specified and not additional compensation shall be considered.

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant-based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following items:

Item 								       				Unit

PS21.20 Backfill existing drains within road prism ................................................		m3

The unit of measure shall be the cubic metre. The tendered rate shall include for full compensation for procurement of the specified material from the Contractor’s borrow pit, placing it in existing drains after the drains have been cleared to the approval of the Engineer in layers  and compacting it to specified densities.

SECTION 2200:	PREFABRICATED CULVERTS

PS2203	MATERIALS

Add the following sub-clause:

(j)	Steel reinforcement

Steel reinforcement for inlet and outlet structures, manholes and other appurtenant structures shall comply with the requirements of section 6300 of the standard specifications.

PS2204         CONSTRUCTION METHODS

Add the following to this sub-clause:

Culverts shall be constructed using the trench method as described in paragraph (a)

PS2211       BACKFILLING OF PREFABRICATED CULVERTS

Amend the first paragraph of sub-clause (a) to read as follows:

"The material used for the back-filling alongside the culvert shall be selected material of at least G7 quality.  Where the excavated material is not of adequate quality selected material shall be imported for this purpose.  The material placed over the top of the culvert shall be of the same quality as that of the road pavement at a similar depth but in any event of at least G7 quality."

### PS2218	MEASUREMENT AND PAYMENT

Item											Unit

PS22.02 Backfilling:

Delete the last but one paragraph of item 22.02 and substitute with the following:

The tendered rates shall include full compensation for backfilling under, alongside and over conduits, for disposing of excess excavated material, for watering and compacting the backfill material to the specified densities. In addition, the rates tendered for sub item (b) shall include full compensation for supplying selected material of subbase quality from approved sources, including the free haul distance stated in Clause 1600 and as amended herein.

Amend the description of Item 22.14 to read:

Item												Unit

PS22.14 Removing and stacking existing culverts of all sizes and types..................	m

Amend the description of item 22.23 (b) to read

Item 												Unit

PS 22.23 Service ducts

(a) Ordinary pipes (PVC, not exceeding 300mm diameter) …………………………………….m

(b) Concrete pipe culverts 900mm diameter …………………………………………………...   m

PS2300	CONCRETE KERBING, CONCRETE CHANNELLING, OPEN CONCRETE CHUTES AND CONCRETE LININGS FOR OPEN DRAINS

PS2302	MATERIALS

(d)	Bedding material

Add the following:

"A class 15/13 semi-dry concrete mix shall be used unless otherwise directed by the Engineer"

Replace Pay Item 23.08 with the following new pay items:

Item											Unit

PS23.08	Concrete lining for open drains:

(a)	Cast in situ concrete lining (Concrete Class 20/19) for open drains

(All types of drains including formwork Class F2 surface finish,

sealing of joints with approved sealant and weep holes):

(i)	75mm thick to vertical or inclined surfaces............................................m2

(ii)	100mm thick to horizontal surfaces.......................................................m2

(b) Concrete class 20/19 in precast slabs 150mm thick to bridge open drain

Including reinforcement and all formwork (crossover slabs)……. …………….m3

The unit of measurement shall be the square metre of the drain surface lined as specified in drawings. The tendered rate shall include full compensation for painting open joint surfaces as specified.

The tendered rate shall include full compensation for casting concrete of the specified thickness and class, for supplying and fixing formwork, for weep holes, for forming and sealing joints, all as specified in the drawings.

Add the following new pay items

Item                                                                                                                              Unit

PS 23.16	Access bridge to DWG No PCL/CON/2022-23/PCL/STD/JI/002

      - Type I………………………………………………………………….No

      - Type 2…………………………………………………………………No

      - Type 3………………………………………………………………….No

      - Type 4…………………………………………………………………No

PS23.20 	Precast concrete class 25/19 cover panels including formwork,

F2 surface finish, as per standard drawings no (RA/CON/2022-23/PCL/STD/DR/005)

    - 150mm thick

(i) Width not exceeding 2360mm……………………………………………….m

    - 200mm thick

(i) Width not exceeding 2360mm……………………………………………….m

The unit of measure shall be the metre of completed panel as constructed.

The tendered rate per metre shall include compensation for procuring, furnishing and installing the complete as specified in the drawings

PS 23.21 Extra over precast covers for

    - Panels with grates and frame………………………………………………No

    - Panels with lifting hooks at the specified interval………………………..No

PS 23.22 Concrete Pavements

    - Class 30/19 cast in situ concrete reinforced with mesh A393 in platforms for bus bays and lay bays as detailed in drawing RA/CON/2022-23/PCL/STD/BS/001………m3

SECTION 3100	BORROW MATERIAL

PS 3101:	SCOPE

Add the following to the end of this clause:

The possible locations of sites for proposed quarries and borrow pits for construction materials are indicated in the materials survey report. The Contractor shall satisfy himself as to the suitability of such sources by trial pits dug on a 25 m grid through the full depth of the material being investigated and testing samples from each pit for classification, CBR and compaction. It shall be, in any case the responsibility of the Contractor to provide sufficient material of approved quality to complete the Works.

The Contractor may, with the approval of the Engineer, locate and open up quarries and borrow pits in addition to those indicated in the materials survey, in which case he shall investigate these additional sources as specified above for borrow areas designated in the materials survey.

The Contractor must obtain a permit from the Chief Mining Engineer before opening up stone quarries.

The Contractor shall remove all ant-hills, ants’ nests, vegetation, topsoil, overburden, boulders, rock, unsuitable and oversize material, and shall provide, erect, operate and maintain all plant necessary for the operation of quarries and borrow pits, together with all access roads, bridges and the like, all at his own expense unless otherwise provided as a pay item.

PS 3102:	Negotiations with Owners and Authorities

Replace clause 3102 with the following:

The Contractor shall satisfy himself that all necessary negotiations have been made with the owner (if any) of the land on which any borrow pit is situated, prior to the opening of such borrow area. The attention of the Contractor is drawn to the provisions of Clause 1214.

PS 3108:	Classification of Borrow Pits for Gravel Materials for Pavement Layers

Delete this clause in its entirety.

Add the following clause to Section 3100:

PS 3110:	Explosives and Blasting

Blasting shall be carried out in strict accordance with the latest Government regulations, and at all times shall be carried out and supervised by fully qualified persons in terms of these Regulations. If in any situation blasting is considered dangerous, the Engineer’s decision in this respect shall be final. Should any damage of any kind occur, the Contractor shall be solely responsible for such damage or any claims that may arise therefrom, and shall, at his own expense, carry out repairs or restoration as the Engineer may direct.

Care shall be taken that no undischarged cartridges are allowed to remain in the excavation. Careless or indiscriminate use of explosives will result in the Engineer withdrawing permission for their use and under such circumstances the Contractor shall resort to other methods of excavation.

The Contractor shall obtain the written permission of the Engineer for each location where the Contractor requires using explosives.

SECTION 3200	SELECTION, STOCKPILING AND BREAKING-DOWN THE MATERIAL FROM BORROW PITS AND CUTTINGS, AND PLACING AND COMPACTING THE GRAVEL LAYERS

PS3202        SELECTING THE MATERIALS

Add the following:

“The quality of the materials in the borrow pit is inconsistent. Good quality material is often limited to small pockets. It may therefore be necessary to stockpile and mix materials to ensure that the quality of the material will comply with the specified requirements for a particular layer for which it will be used. The cost for these processes shall be deemed to be covered by the rates for the various items of work for which these materials are used.”

PS 3206	CONTROLLING THE MOISTURE CONTENT OF MATERIALS

Add the following to the third paragraph:

The time required for doing work to accelerate the drying out of wet material or for dealing with wet material as described above, shall not be regarded as part of a delay caused by inclement weather in terms of clause PS 1215.

SECTION 3300	MASS EARTHWORKS

PS3305	TREATING THE ROADBED

(a)	Removing unsuitable material

Add the following to the first paragraph of this sub-clause:

"Roadbed material within 1.0 m of the finished road level shall have a minimum CBR of 3 at 90% of modified AASHTO density, after compaction. Any material which does not meet this requirement shall be treated as unsuitable and removed."

(c)	Preparing and compacting the roadbed

Where the roadbed is anywhere within 1.0m of the selected formation layer, it shall be compacted to 93% of modified AASHTO density. Roadbed shall be compacted to 90% of modified AASHTO density where it is more than 1.0m below the selected formation layer.

PS 3312	MEASUREMENT AND PAYMENT

Delete in pay – items 33.01, 33.02, 33.04 and 33.07 the wording “including free – haul up to 0.5 km” and replace with: “including unlimited free – haul distance”.

Amend pay Item 33.01, Cut and borrow to fill (a) and (e) with the following:

Item											Unit

PS 33.01	Cut and borrow to fill including unlimited free-haul:

- Gravel or soft fill material in compacted layer

thicknesses of 200 mm or less

- compacted to 93% modified AASHTO density……….… 	cubic metre

- Rockfill (as specified in subclause 3209(c)) ……….… 		cubic metre

PS33.03	Extra over 33.01 for excavating and breaking down the material

  - Hard material							cubic metre

PS33.04	Cut to spoil including unlimited free haul material obtained from

(a) Soft excavation ……………………………….. 				m³

(b) Hard excavation ……………………………….. 				m³

PS33.07	Removal of unsuitable material obtained from any type of material

and excavation in any layer thickness with unlimited free haul……………… m³

PS33.10	Roadbed preparation and the compaction material

| (a) (b) | Compacted to 90% modified AASHTO…………………………………….m³ |
| --- | --- |
|  | Compacted to 95% modified AASHTO…………………………………….m³ |

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3403	CONSTRUCTION

(b)	Placing and compaction

- Shoulders

Add the following:

Shoulders shall be constructed from the same material as the base

PS3407	MEASUREMENT AND PAYMENT

Change pay item 34.01 as follows:

Delete the wording “including free – haul up to 1.0 km” and replace with “including unlimited free – haul distance”.

Delete the second paragraph (payment paragraph) of item 34.01 and substitute with the following:

The tendered rates shall include full compensation for mixing, watering, placing and compacting the material supplied under item PS34.01, and the protection and maintenance of the layer and the conducting of control tests, all as specified.

SECTION 3500: STABILISATION

PS 3502	MATERIALS

Add the following:

e) Emulsion Treated Base Materials

The materials to be used in the construction shall conform to the required specifications. The contractor shall issue to the consultant test results of the materials to be used including certifications from the suppliers before they are used on site.

The following materials will be required:

1.	Material to be treated

2.	Bitumen Emulsion

3.	Active filler – Hydrated lime/ Cement

4.	Clean Water

The mix design is determined by the nature and proportions of the following ingredients:

•	Aggregate and its performance characteristics.

•	Bitumen type (foamed bitumen or bitumen emulsion), the amount added, and compatibility with the aggregate.

The full mix design procedure can be found in the “Technical Guideline: Bitumen Stabilised Materials. (2020). Southern African Bitumen Association (Sabita)”.

The mix design has to take into account the fundamental distress mechanisms which are permanent deformation and moisture susceptibility. Resistance to permanent deformation can be increased by; improving the aggregate properties, increasing the maximum particle size, improving the compaction, reducing the moisture content, limiting bitumen application to less than 3% and limiting the addition of active filler to a maximum of 1%.  Moisture resistance is enhanced by; increasing the bitumen content, improving the compaction and smooth continuous grading.

The cost of bitumen stabilised materials is mainly dominated by the cost of bitumen, so it is important to effectively optimise the addition content of bitumen. Due to advances in the testing methods, like calculating the internal tensile strain of a sample, accurate and reliable refinements can be made of the amounts of bitumen required.

f) Plant and Equipment

i) Mixing Plant

The plant used to produce bitumen stabilised materials must be capable of accurately blending predetermined proportions of different input materials whilst simultaneously adding the correct amount of bitumen stabilising agent, water and active filler to consistently produce a homogenous product.

The mixer should have sufficient power to mix the material at a throughput that allows economic production (± 200 tons per hour).

ii) Paver

The thickness of the layer constructed and the paving width dictate the volume of the emulsion treated material that the paver must handle.

iii) Vibratory roller

Unlike in situ treated materials where layer thicknesses in excess of 200 mm are the norm, paved layers of bitumen stabilised materials seldom exceed 150 mm in thickness.  Such a layer thickness can be compacted using a vibrating roller

iv) Static Tank for Storage of Emulsion

Static tanks should be provided to cater for storing sufficient bitumen emulsion for the needs of the project.  Normally such tanks have a capacity of between 60 000 litres and 120 000 litres.  The static tank must be fitted with a circulating pump system to enable the stored emulsion to be properly circulated from time to time, especially if no emulsion has been drawn or added for more than 2 days.

## PS 3503	CHEMICAL STABILIZATION

Add the following:

i) Layer Construction Using a Paver/Finisher

Unlike asphalt, a bitumen stabilised material is not a cohesive material and it is paved at ambient temperatures. Paver set up and operating procedures are, therefore, different.

i.	Paver Setup

Setting up the paver and screed are fundamental requirements on any paving job. Adjustments need to be made to the screed so that it achieves the consistent “float” that is imperative to obtain a smooth mat.

Trial sections for paved bitumen stabilised materials should be constructed off site to achieve the proper paver setup.

ii.	Paving the Layer

The same fundamental procedures for paving hot mixed asphalt are applicable to paving a bitumen stabilised materials and shall follow clause 4207.

iii.	Construction Joints

Longitudinal joints generally receive the following treatment:

•	Once the first half-width is paved, the 500 mm wide section closest to the centre-line receives only one pass with the roller without vibration, leaving it in a relatively uncompacted state.

•	Immediately before paving the second half-width, the exposed edge on the centre-line together with the partially compacted strip is thoroughly moistened. This is normally undertaken by a separate team equipped with hand sprayers walking ahead of the paver.

•	Prior to paving the second half-width, the bevelled end plate is removed from the centre-line end of the screed. This allows the screed to butt up against the exposed step of the first half-width.

The partially compacted strip of material remaining on the first half-width then receives the full compaction and finishing treatment together with the second half-width.

Lateral joints occur at every location where paving stop and a ramp must be constructed to accommodate the traffic. The following day, or when paving restarts, the material in the ramp must be removed and the previously paved material cut back to achieve a 45° slope and a consistent level profile. The material lying on the slope is then thoroughly moistened before paving continues.

iv.	Compacting the Paved layer

The primary concern when using the heavy vibrating rollers required to compact a paved layer of bitumen stabilised materials is loss of shape. The rolling pattern should be determined from the Trial Section.

Tandem smooth drum rollers are always used to compact the layer behind the paver. Equipped with two vibrating (and/or oscillating) drums, these rollers normally achieve the required density with relatively few passes. However, operators need training to prevent over-rolling and shape loss since the technique required to compact bitumen stabilised material is very different from compacting hot mixed asphalt.

v.	Curing and Trafficking

On compaction, the increase in density is not sufficient to ensure resistance to traffic damage. An increase in cohesion is required for resistance to traffic damage, which is dictated by the time required for the bitumen emulsion to break out of suspension. This normally takes a few hours at the surface where evaporation triggers the break, but can take several days for the bitumen emulsion deeper in the layer.

vi.	Surfacing

Prior to applying Asphalt surfacing, the surface needs to be thoroughly cleaned to expose the texture of the material aggregates. A prime coat should not be applied on emulsion treated bases because the dispersed bitumen present at the surface of the cleaned layer provides adequate adhesion for a bituminous surfacing layer.

PS 3506	QUALITY OF MATERIALS AND WORKMANSHIP

Add the following:

d) Emulsion treated base process control

In-Plant treatment of the materials, provides the ability to control the quality and blend proportions of input materials increases the degree of confidence that the mixed product meets performance expectations. In addition, the application rate of bitumen stabilising agent and active filler can be minimised with confidence knowing that the material to be mixed will be similar to that used in the mix design.

Where the base layer is paver laid, the location selected for constructing the Trial Section should be a side road away from the permanent work. Trial Sections provide an opportunity to determine an appropriate rolling pattern as well as the number of roller-passes required to achieve the target density.

The important process controls when placing the base layer include:

•	Checking that the surface on which the new layer is to be constructed has been properly prepared by removing all loose material and spraying with sufficient water to prevent the material from being placed on a dry floor (that will suck the moisture from the new material, making it difficult to compact). Similarly, all construction joints have been thoroughly moistened before placing the abutting fresh material.

•	When placing by paver:

- Check the critical screed settings. Once the screed has been set up and an acceptable mat achieved, the settings must not be altered.

- Care must be taken to prevent segregation. Material tipped into the paver’s hopper at the start of work must remain in the wings until the end of work when it can be removed from site. This means that the wings must not be tilted to feed this material through to the screed.

- As with all paving operations, paving should be continuous by limiting the advance speed to the delivery rate of material.

- Trucks delivering material are to be engaged by the paver meeting the waiting truck (not the truck reversing into the paver).

When compacting the new layer; to prevent the material from drying out, ensure that the correct combination of rollers compact the material as soon as it has been placed. The operation of each roller, the rolling pattern and the sequence of rolling are all determined by constructing a Trial Section and these must be followed meticulously to achieve the required density without rolling the layer out of shape. Finishing is usually carried out with a Pneumatic Tyred Roller (PTR) adding sufficient water through the wheel sprinklers to achieve a tightly knit surface.

e) Core Specimens for testing

A series of cores can be extracted from the layer and tested for compliance. Core samples may be extracted from the full thickness of the completed layer, measured to determine the thickness of the layer and then tested for ITS (Indirect tensile strength) values. Cores cannot be successfully extracted until the layer has developed sufficient strength and the delay period is dictated by the rate of moisture loss from the material which is primarily a function of weather conditions and layer thickness. When conditions are warm and dry, cores can usually be extracted from a 150 mm thick layer after 7 days. The delay period is further influenced by the stability of the emulsion and delays in excess of 30 days are normal.

## PS3507 MEASUREMENT AND PAYMENT

Amend pay item 35.01 and 35.02

Item                                                 							unit

PS35.01 Chemical Stabilization

    - 200mm thick extra over unstabilized compacted layers of crushed stone base….….m3

    - 200mm thick extra over unstabilized compacted layers of natural gravel subbase layer……………………………………………………………………………….….m3

The unit of measurement shall be the cubic meter of stabilized material, the quantity of which shall be determined in accordance with the authorized dimensions of the layers treated as instructed by the Engineer.

Item                                                 							unit

PS35.02 Chemical Stabilizing agent

(a) Ordinary Portland Cement ………………………………………………… tonne

(e) Anionic Stable Grade Bitumen emulsion………………………………….litres

SECTION 3600:  CRUSHED-STONE BASE OR SUBBASE

PS 3602 MATERIALS

Add the following:

Existing crushed stone base shall be scarified and removed to stockpile for re-use as subbase material in the new construction.

The crushed stone material for base course shall be obtained from commercial sources or from approved quarry pits and crushed by the Contractor.

SECTION 4100	PRIME COAT

PS 4102	MATERIALS

- Priming material

Add the following:

The prime coat shall be MC 30 cut-back bitumen.

SECTION 4300:   MATERIALS AND GENERAL REQUIREMENTS FOR SEALS

PS 4303:        Plant and Equipment

- General

Add the following:

The Contractor shall ensure that he has a very good competent surfacing team, which is capable of delivering a high quality standard of workmanship; i.e. Competent and experienced Asphalt Foreman, operators and attendants, who have abilities of carrying out binder distribution and seal work operations within specified tolerance of applications and according to final product requirements.

The Engineer will instruct the removal of incompetent staff from site and a replacement thereof with a competent staff if satisfactory performance is not achieved and maintained.

(b)	Binder distributor

Add the following:

"The binder distributor shall be capable of spraying the binder to the specified application rates and to the satisfaction of the Engineer.  It is important that the pump of the distributor shall be capable of delivering the binder at the spray bar nozzles at the correct pressure to obtain the specified application rates, irrespective of the viscosity properties of the proposed binder.  The spray bar of the distributor shall be fitted with fishplates at the outside edge of the bar to prevent over spraying onto shoulders or staining of concrete elements on the edge of the surfacing of the road.  If instructed by the Engineer, the outside nozzles of the spray bar shall be turned to a 45o angle to achieve a thickened edge of binder along the outside limits of the seal area.

The variation in the rate of application between two adjoining 100 mm strips shall not exceed 5%, excluding the outside 300 mm on either side of the spray bar.  The coefficient of the variation shall not exceed 10%.  The test procedure shall be as prescribed in the Modified Tray-test contained in TRH 3 and shall be carried out each time the distributor is established on site or at least once per week. The binder distributor shall thus carry a set of troughs at all times in order to allow the execution of this test.

A calibration certificate, not older than 3 months, for the binder distributor shall be presented to the Engineer in order to ensure accurate application rates.

The binder distributor shall be fitted with a suitable valve or other access gate for taking of samples of the binder for testing purposes."

PS 4304:     GENERAL LIMITATION AND REQUIREMENTS

- Weather limitations

(i) Non-homogeneous Modified Binders (summer grade)

The minimum road surface temperature for applying bitumen-rubber binder shall be 25°C, and if below 25°C, the air temperature shall be at least 20°C and rising. As soon as the minimum air   temperature at night is recorded to fall below 10°C, seal-work shall cease until warmer weather conditions are experienced.

Application of binders shall not be allowed if the existing cracks in the road contain moisture after rain.

(d)  Preparation of areas to be sealed

(ii) Newly constructed seals

For the repair and filling of uneven spots in the completed base shallower than 12mm, a slurry complying with the requirements of clause 4604 (c) shall be used, based on one of the gradings of a Fine slurry.

60% stable mix-grade emulsion prepared from 70/100 penetration grade bitumen shall be used as binder.

The mix of fine aggregate, which shall be used for repairs shall comply with the following requirements by volume in the case of the irregularities exceeding 12mm in depth:

9.5mm   nominal sized aggregate                                    1 part

6.7mm   nominal sized aggregate                                    1 part

Fine –graded crusher sand                                                1 part

Each patch shall be compacted by means of two passes of a steel-wheeled roller of minimum mass of one comma five (1.5) tons, which compaction must be applied within four (4) hours after the emulsion has broken.

(iii) Existing Surfaces to be resealed

If so instructed the Contractor shall seal wide cracks by hand-application of Petrol seal. Payment will be made at Dayworks rates. Localised undulations shall be repaired as for base corrections, where and if so instructed, also on Dayworks rates.

Except at the intersections, the existing surfacing shall be cut back to a width of 7.4m with a roller cutting blade attached to a heavy self-propelled roller. The redundant surfacing strips shall be removed and edge break repairs shall be carried out before completion of the reconstruction of the shoulders, where such reconstruction is instructed.

Three (3) weeks prior to commencements of resealing operations an MSP 3 inverted emulsion rejuvenator shall be applied over the full width of the narrowed existing road seal, plus 100mm to 300mm wider along each side. The MSP 3 rejuvenator spray, shall be applied in half widths at an application rate of 0.5 l/m² during the summer months, before the start of the rains and the sprayed section kept closed to traffic for at least five (5) hours before re-opening.

PS 4305:       HEATING AND STORAGE OF BITUMINOUS BINDERS

- Non- homogenous (heterogeneous) modified binders (summer grade)

Bitumen rubber binder shall not be stored at all. Once the rubber is added to the base bitumen, the product shall be applied to the road as soon as it is adequately digested and at spraying temperature. Any binder left in the distributor at the end of the allowable spraying period, or not applied due to an unforeseen stoppage lasting till beyond the spraying period, shall be removed from site. Even a forced stoppage in the blending period between addition of the rubber and heating to spraying temperature shall not be considered as a reason for the approval of storing the binder for later use. Reference shall be made to the specified limitations regarding the programme of work and lengths of construction areas described in section 1200 and 1500 of these specifications.

The Engineer’s supervisory staff shall, through timeous notification by the Contractor, be afforded the opportunity to attend to all bitumen rubber blending operations in order to exercise control sampling and testing on the binder from the stage just prior to the addition of the rubber to the base bitumen up to the end of the allowable spraying period. Failure to conform to the requirements will be considered reason enough by the Engineer to reject the batch of binder.

PS 4310:	Dust Control

Delete paragraph two.

SECTION 5100 	MARKER AND KILOMETRE POSTS

PS 5101 SCOPE

Add the following to this Clause:

Road reserve demarcation beacons shall be constructed according to details on drawing No. RA/CON/2022-23/PCL/STD/MB/001 at an interval of 200m on either side of the road.

PS 5106	MEASUREMENT AND PAYMENT

Add the following pay item:

Item                                                                                                                 Unit

PS 51.03 Road reserve demarcation beacons as per drawing no RA/CON/2022-23/PCL/STD/MB/001……………………………….…………………………..…. No.

The unit of measurement shall be the number of beacons installed to the satisfaction of the Engineer

The tendered rate shall include full compensation for excavation, materials, construction, backfilling and plastering of the beacon.

SECTION 5200: GUARDRAILS

PS 5202	MATERIALS

5202(b) Guardrail posts

Add the following:

(iii)	Concrete posts

Guardrail posts shall be of prefabricated concrete according to the detail on the drawings. Timber spacer blocks shall comply with specifications of Clause 5202.

PS 5203 CONSTRUCTION

5203(a) Erection

Add the following to the 3rd paragraph:

The bolts shall be tack welded to the nuts in order to reduce the risk of vandalism.

PS 5206 MEASUREMENT AND PAYMENT

Add the following pay item:

Item											Unit

PS52.13 Galvanised and painted guardrails on concrete posts including end units and reflective plates as per drawing no. RA/CON/2022-23/PCL/STD/GR/001-005………………………metre (m)

The unit of measurement shall be the metre of guardrail erected including concrete posts, end units and reflective plates.

The tendered rate shall include full compensation for furnishing all materials and labour and for erecting the galvanized guardrails painted as specified on the drawings or as directed by the Engineer, complete with prefabricated concrete posts, spacer blocks, bolts, nuts, washers and reinforcing plates, bull noses and for excavating and backfilling post holes with 15Mpa concrete and/or selected excavated material and removing surplus excavated material.

## SECTION 5400:	ROAD SIGNS

PS 5401	SCOPE

Substitute the second paragraph with the following:

All Road Traffic Signs shall comply with the South African Development Community (SADC) Road Traffic Sign Specifications.

(1)	The Traffic Sign details shown on the drawings give general information on the erection, placing and details of several of the required signs. Details of signs not shown on the drawing shall be in accordance with Regulations. The specifications information regarding the dimensions and locations of signs reference should be made to "The SADC Road Traffic Signs Manual”.

(2)	The exact location of signs shall be as directed by the Engineer.

(3)	Sign faces will be constructed of sheet steel of a minimum thickness of 1.6 mm and the back of the sign shall be painted grey.

- Regulatory and warning signs shall be similarly mounted; larger signs shall be mounted on two or more 75mm diameter galvanised mild steel posts. Where the horizontal or vertical dimension exceeds 900mm, the sign shall be stiffened by means of 25mm x 25mm rectangular hollow sections as detailed on the drawings. All guide or information sign posts are to be painted grey. Sign posts for regulatory and warning signs shall be painted with alternating bands of yellow and black.

(5)	The size of guide or information signs shall be as specified in the regulations. The layout of the sign (letter spacing, size, border size, etc.) and colours shall be as given in the SADC Regulations.

- The size, colours and letter series type for regulatory signs will be as given in the SADC Regulations, or as shown on the drawings or as instructed by the Engineer.

All warning and regulatory traffic signs on the Main Road shall be at least size 1200mm for the design speed of 120km/hr.

All warning and regulatory traffic signs on the Access Roads shall be at least size 914mm for the design speed of 80km/hr.

(7)	Warning signs will be on an equilateral triangle with a white reflectorized symbol on a blue reflectorized background. The size of the triangle will be as given in the SADC Road Traffic Sign Specification or as shown on the drawings or as instructed by the Engineer.

(8)	All signs are to be reflectorized with engineering grade retro reflective materials. The material is to be good quality and is to be affixed to the sheet metal according to the manufacturer’s recommendations".

### PS 5409	MEASUREMENT AND PAYMENT

Delete pay items 54.01, 54.02 and 54.03 and replace with the following:

Item												Unit

PS54.01	Road sign boards with painted or coloured background.

Symbols, lettering and borders in Class 1 retro-reflective

material, complete with posts and supports pre-painted

galvanised steel plate (Chromadek or approved equivalent)

position as shown on the drawings:

(a)	Area not exceeding 2m2..........................................................................	m2

(b)	Area exceeding 2m2 but not 10m2..........................................................	m2

(c)	Area exceeding 10m2............................................................................. 	m2

Add the following new pay item:

Item												Unit

PS54.10	Erection of Standard Road Signs...........................................................	No

The unit of measurement shall be the number of specified road signs erected. The tendered rate shall include full compensation for the provision and fixing in position of sign faces, posts, nuts, for painting the surfaces, lettering, excavation for posts, concreting, backfilling, removal of excess excavated materials, etc. and all that is necessary to make the work comply with the specifications.

- SECTION 5500: ROAD MARKINGS

- PS 5501 SCOPE

Add the following: -

After sections of road are completed and before being opened to traffic all road markings are to be completed. The road studs will not be placed at this stage. The Contractor shall return during the Defects Notification Period to re-paint all road marking as specified as well as the placement of road studs.

All Road Traffic Markings shall comply with the South African Development Community (SADC) Road Traffic Sign Specifications.

The Contractor may use thermoplastic marking material and shall provide a three year guarantee for the road traffic markings. Towards the end of the Defects Notification Period the Contractor shall repaint all road traffic markings. No separate payment shall be payable. The Contractor shall make appropriate allowance in his programme and his tender rates for re-painting at the end of the Defects Notification Period.

The Employer shall withhold retention monies due until the Contractor has repainted the road markings to the satisfaction of the Engineer. Should the Contractor fail to remobilize the road marking unit team and attend to the notified defects within the Defects Notification Period, the Employer may use the retention money to engage other Contractors to carry out the outstanding work and deduct these costs from the retention monies. Should these retention moneys be insufficient to cover the cost of correcting the road traffic markings then the Employer may recover the shortfall from the Contractor by legal processes.

- PS 5502 MATERIALS

- 5502(b) Road studs

Delete the first paragraph of the sub clause and substitute with the following:

Road studs shall consist of an acrylic plastic shell filled with a tightly adherent potting compound. The shell shall contain two prismatic retro-reflective faces to reflect incident light from opposite directions. The colour shall conform to the colour requirements of ASTM D4280.

The shell shall be moulded of methyl methacrylate conforming to ASTM D788 Grade 8. The outer surface of the shell shall be smooth. The base of the marker shall be substantially free from gloss and substances that may reduce its bond to adhesive.

The filler shall be a potting compound capable of supporting a minimum load of 909 kg when tested in accordance with ASTM D4280.

The size, colour and spacing of road studs shall be as indicated on the Drawings or directed by the Engineer.

- PS 5504 MECHANICAL EQUIPMENT FOR PAINTING

Insert the following additional paragraph after the first paragraph:

Equipment for thermoplastic marking shall consist of at least one truck mounted storage boiler, a screed box on wheels and an extruder or spraying machine. A steel manual screed shall be used to paint arrows and other symbols. The extruder may be truck-mounted or self-propelled. Boilers must be fitted with mechanical stirrers to keep the mineral matter and glass beads in suspension. Accurate thermometers and thermostats are required on all boilers.

- PS 5507 APPLYING THE PAINT

Add the following at the end of the third paragraph:

The thickness of thermoplastic laid in the trial and for each day’s work shall be checked by applying the material to a clean steel plate. The plate sample shall be taken while marking is in progress by positioning the plate on the road in the projection of the line which is about to be marked. The thickness shall then be confirmed with callipers. Gaps left within the road markings due to testing shall be immediately reinstated.

- Add the following to end of the last but one paragraph:

The rate of application of thermoplastic road paint shall be related to volume and be that amount sufficient to achieve the specified nominal line thickness.

- Add the following to the last paragraph:

After completion of a section of asphalt surfacing and before opening the section to traffic, the pre- marking of the centre and edge lines shall be done. At least two weeks shall elapse after completion of the surfacing before the permanent road markings shall be applied, unless otherwise directed by the Engineer.

- PS 5508 APPLYING THE RETRO-REFLECTIVE BEADS

Add the following to the end of the first paragraph:

In the case of thermoplastic paint, the rate of application of beads shall be 0.5kg/m2 of marking. This amount shall be in addition to the quantity already mixed within the composition of the thermoplastic.

- PS 5514	MEASUREMENT AND PAYMENT

Delete pay item 55.04: Variation in the rate of paint application.

The Contractor shall be deemed to have included the cost of this item in the rates tendered for road marking.

SECTION 5700	LANDSCAPING, TOPSOILING AND GRASSING

PS 5702:	Materials

Add the following to the relevant sub-clauses:

(a)	Fertiliser/Soil-Improvement Material

Fertilisers shall not be used in this Contract.

(b)	Grass Cuttings

Grass cuttings shall be fresh cuttings of the species as specified by the Engineer

(c)	Grass Seeds

The Contractor may use grass seeding in lieu of planting, but no additional payment shall be made for hand seeding or hydro-seeding.

(d)	Trees, Shrubs and Hedge Plants

This sub-clause is deleted.

(e)	Grass Sods

Delete this sub-clause and replace it with the following:

“Veld sods may be obtained from approved areas where a suitable type and density of grass are found. No additional payment shall be made for sods.”

(f)	Anti-Erosion Compounds

This sub-clause is deleted.

(g)	Topsoil

Delete paragraphs two, three and four, and replace them with the following:

“Topsoil shall be obtained from stripping operations under embankments and in cuttings in accordance with Sub-Clauses 1702(c) and 1703(a). Topsoil stripped from borrow areas shall not be used for top-soiling elsewhere but must be used to rehabilitate the borrow areas themselves. If the Contractor fails to conserve the topsoil as prescribed in Sub-Clause 1702(C), he shall obtain suitable topsoil from other sources at his own cost.

“Care shall be taken to prevent the compaction of the topsoil in stockpiles or in the Works in any way, particularly by trucks driven over such material.”

PS 5704:	Preparing Areas for Grassing

(a)	Soil Ripping

This sub-clause is deleted.

(b)	Areas Which Do Not Require Topsoil

This sub-clause is deleted.

(c)	Areas Which Require Topsoil

Add the following to this sub-clause:

All surfaces to be grassed shall immediately before grassing be roughened to ensure a proper bond with the topsoil. Topsoil free from stones shall be placed on the prepared surface and trimmed to a thickness slightly higher than the final thickness.

Where shown on the Drawings or directed by the Engineer the verges and the slopes of cuttings and embankments shall be covered with topsoil and lightly rolled to the required final thickness.

(d)	Fertilising

This sub-clause is deleted.

PS 5705	Grassing

The Contractor shall choose the method of establishing grass. No additional payment shall be made regardless of the method of grassing employed by the Contractor.

Add the following to this sub-clause:

(a)	Planting Grass Cuttings

Fresh grass cuttings of the “Kapinga” species or other approved species shall be planted by the Contractor at 250 mm centres and watered at frequent intervals to ensure the grass takes root and spreads out quickly. Grass cuttings that have been allowed to dry out shall not be planted.

All grass shall be planted before the start of the defects liability period for any section of the road.

Add the following to this sub-clause:

(c)	Hydroseeding

The Engineer shall approve the types and mixtures of seeds to be used before the Contractor orders any seed. Hydroseeding shall be carried out with an approved hydroseeding machine at a rate of application of not less than 38 kg of seed mixture per hectare. Mulch shall be added to the hydroseeding mix at an approved rate.

(d)	Top-soiling Only

This sub-clause is deleted.

Add the following to this sub-clause:

(e)	Grassing with an Approved Grass Planter

Grassing shall be done with an approved grass planter which plants the seeds in rows spaced not more than 250 mm apart. The planter shall plant the seeds approximately 6 mm deep and shall lightly compact the topsoil.

(g)	Other Methods

This sub-clause is deleted.

(h)	The Grassing of Borrow Pits, Temporary Bypasses, Camp Sites, Access Roads and Stockpile Sites

This sub-clause is deleted.

PS 5706:	Maintaining the Grass

(a)	Watering, Weeding, Mowing and Replanting

On line one of paragraph two delete “mow” and replace with “cut”.

(b)	Acceptable Cover

At the beginning of this sub-clause add the following as first paragraph:

“The Contractor shall be solely responsible for establishing an acceptable grass cover and for the cost of re-establishing grass by any method where no acceptable cover has been established.”

(c)	Maintenance Period

The maintenance period in respect of grass shall commence when an acceptable grass cover as defined in (b) above has been established and shall last one year or to the end of the period of the Contract, whichever expires later.

The Contractor shall be responsible for watering, cutting and maintenance of all grassed areas during the period of maintenance.

(d)	Proprietary Brand Materials Used for Erosion Prevention

This sub-clause is deleted.

(e)	Responsibility for Establishing an Acceptable Cover

This sub-clause is deleted. Sub-Clause 5706(b) applies.

(f)	Re-Fertilising

This sub-clause is deleted.

PS 5707(C):	TREES AND SHRUBS

Add the following:

All trees and shrubs grass shall be planted prior to the start of the defects liability period for any section of the road.

PS 5709: Measurement and Payment

Merge pay items 57.01 and 57.02 as follows

Item										Unit

PS 57.01   Trimming and shaping by hand and/or machine……………………Kilometre (km)

The unit of measurement shall be the kilometre of road trimmed on both sides. In the last paragraph under Item 57.01, payment shall NOT distinguish between machine trimming which can reasonably be done by bulldozer or motor grader, and hand trimming.

Add the following pay item:

Item												Unit

PS 57.12 Paving walkways with interlocking blocks

    - On walkway and Median with 60mm thick, 25Mpa interlocking blocks…………… m2

    - 30mm thick sand bedding for interlocking blocks…………………………………… m2

The tendered rate shall include the full compensation for the supply and laying of approved sand bedding and paving units in accordance with the specifications. Sand and Paving blocks shall be obtained from sources identified by the contractor and haulage distance shall be unlimited

Add the following section:

SERIES 8000: SPEED CALMING FEATURES

PS8100	HUMPS AND RUMBLE STRIPS

Humps and rumble strips shall be constructed, arranged and spaced according to details provided in the drawings.

PS8101	Measurement and Payment

| Item |  | Unit |
| --- | --- | --- |

PS81.01	Humps and Rumble Strips

(a) Installation of humps as per drawing detail

RA/CON/2022-23/PCL/STD/TCM/001-002………………….…………………………… No.

(b)	Installation of rumble strips in sets of five as per drawing detail

RA/CON/2022-23/PCL/STD/TCM/001-002……………………………………………… Set

The tendered rate shall include cost of preparing the area for the hump or strip, setting-out, transport, materials, installation, trimming, cleaning and clearing the area and all other costs associated with the construction of the hump or strips.

Add the following section:

SECTION 9000:	SUPPLY, INSTALLATION AND COMMISSIONING OF STREET LIGHTING SYSTEM

PS 9001: Installation of Glass Fibre poles

Add the following Clause.

The Contractor shall Install glass fibre poles manufactured in accordance with SANS 1749 under the ISO 9002 quality system. If an access opening is required, the access door cover shall be manufactured from glass filled nylon impregnated in the same colour as that of the surface coat. A cable entry with a minimum diameter of 34mm shall be provided at a minimum depth of 400mm below the ground surface. Poles for direct embedment in the ground shall be provided with a 300 x 300 x 1.6mm hot dipped galvanised base plate.

The details of the poles shall be as indicated on the drawings.

PS 9002: Installation of 50w all in one solar street light

Add the following Clause.

The Contractor shall supply and install solar panel power 18v/50Wp (Monocrystalline PV). Life-span 25 years Batteries Capacity/Type 12.8V/36AH (460.80WH) / LiFePO4 Lithium. Lifespan 5+ years (2,000 circles) Controller Type MPPT / Waterproof class IP65 Sensor Microwave Radar (PIR & Timing as optional). LED Light Source Rated Power 12V/ 50W (36Wx2 modules) LED Brand CREE/OSRAM (LED Lumen: 150lm/W) Lumens (LM) 2000-3000lm Life-span 50,000 hours Viewing Angle 1400 x 700 Full Charge Time By Solar 6-8 hours (STC: 1000W/m2, 25° C ) Discharge Time Bright Mode >14 hours , Dim Mode >70 hours Working Temp. -30°C~+80°C Color Temp. Cool White 3000K (3000~3500k) / Space Between Lights 30~35m Materials aluminium alloy Certificate ROHS / IP65/ STQC/MNRE warranty-36 months from the date of supply. “specialized for street lighting purposes”

PS 9003	MEASUREMENT AND PAYMENT

Add the following pay items:

Item			Unit

PS 90.01	Glass Fibre Reinforced Polyester (GRP) poles as per drawing No RA/CON/2021-22/LL-KIA/PCL/308 ………………………………………………………………………	No

The unit of measurement shall be in No. The tendered rates shall include procuring, logistics, installation and including any other works, operation or activity necessary for completing the installation of poles in compliance with the specifications and drawings.

Add the following pay items:

Item	Unit

PS90.02	Supply and installation of 50W all in one solar street light  ..................No

The unit of measurement shall be in No. The tendered rates shall include all items listed above

#### PART B-2: PARTICULAR SPECIFICATIONS FOR ENVIRONMENTAL MANAGEMENT PLAN

1.0	ENVIRONMENTAL MANAGEMENT TEAM (EMT)

The Contracting Authority will be represented on site by a Resident Engineer (RE) and his inspection team will include an Environmental Control Officer (ECO) who shall determine members of the site supervision team as the Environmental Management Team (EMT) that will report on the activities to the Contracting Authority through RE.

The EMT will be responsible for monitoring the performance of the Contractor during the construction phase with regard to Environmental issues and to assess the effectiveness of the impact mitigation measures in protecting the environment on behalf of the Roads Authority and the local communities. The role of the EMT will be “pro-active” with regard to impacts seeking to predict and prevent negative impact and pollution.

The Contractor will provide one full time Contractor’s Environmental, Occupational Health and Safety Expert (EOHSE) to be responsible for the implementation of all environmental mitigation measures. The EOHSE will also undertake liaison with local community leaders and ensure that the Contractor’s compliance with the requirements of the Malawi Environmental Affairs Department, the District Valuer’s Office, and other relevant authorities in connection with environmental and social considerations.

The Contractor shall prepare a Project Environmental Management Plan (PEMP) based on the headings, risks and responsibilities given in the EMP Table.

This Plan shall be particular to the works required under this Contract. The draft PEMP will be discussed, reviewed, where necessary amended and finally agreed in the EMT. The PEMP will form the principal document upon which all Environmental Monitoring will be based throughout the project.

  - IMPACT MITIGATION MEASURES

  - Landscape Preservation

    - General

The Contractor shall exercise care to conserve the natural landscape and shall conduct his construction operations so as to prevent any unnecessary destruction, scarring, or defacing of the natural surroundings in the vicinity of the works. Except where clearing is required for permanent works, diversions or excavation operations, all trees, native shrubbery and vegetation shall be preserved and shall be protected from damage by the contractor’s construction operation and equipment. The edges of clearing and cuts through trees, shrubbery, and vegetation shall be irregularly shaped to soften the undesirable visual impact of straight lines. Movement of labour and equipment within the right-of-way and over routes provided for access to the work shall be performed in a manner to prevent damage to grazing land, crops or property.

Except as otherwise provided special reseeding or replanting will not be required under these specifications; however, on completion of the work all work areas not seeded shall be scarified and left in a condition which will facilitate natural re-vegetation provided for proper drainage and prevent erosion. All unnecessary destruction, scarring, damage or defacing reseeded or the landscape resulting from the Contractor’s operations shall be repaired, replanted reseeded or otherwise corrected as directed by the Resident Engineer and at the Contractor’s expense.

    - Construction Roads

The location, alignment, and grade of construction roads shall be subject to approval of the Resident Engineer. When no longer required by the Contractor, construction roads shall, if required by the Resident Engineer, be restored to the original contour and made impassable to vehicular traffic. The surfaces of such diversions shall be scarified as needed to provide a condition that will facilitate natural re-vegetation provided for proper drainage and prevent erosion.

    - Construction Facilities

The Contractor’s workshops office and yard area shall be located and arranged in a manner to preserve trees and vegetation to the maximum practicable extent. On completion of the project all temporary buildings including concrete footings and slabs, and all construction materials and debris shall be removed from the site. The area shall be regarded, as required, so that all surfaces drain naturally, blend with natural terrain, and are left in a condition that will facilitate natural re-vegetation, provide for proper drainage and prevent erosion.

    - Blasting Precautions

In addition to any requirements of local regulations, the contractor shall adopt precautions when using explosives that will prevent scattering rocks, stumps, or other debris outside the work area, and prevent damage to surrounding trees, shrubbery and vegetation.

  - Preservation of Trees and Shrubbery

    - Preservation

All trees and shrubbery which are not specifically required to be cleared or removed for construction purposes shall be protected from any damage that may be caused by the construction operations and equipment. Special care shall be exercised where trees or shrubs are exposed to injuries by construction equipment, blasting excavating, dumping, chemical damage or other operations; and the Contractor shall adequately protect such trees by use of protective barriers or other methods approved by the Resident Engineer. The removal of trees or shrubs will only be permitted after prior approval by the Resident Engineer.

The layout of the Contractor’s construction facilities such as workshops, warehouse storage areas and parking areas; location of access and haul routes; and operation in borrow and spoil areas shall be planned and conducted in such a manner that all trees and shrubbery not approved for removal by the Resident Engineer shall be preserved and adequately protected from either direct or indirect damage by the Contractor’s operations.

Except in emergency cases or when otherwise approved by Resident Engineer, trees shall not be used as anchorages. Where such use is approved, the trunk shall be wrapped in with a sufficient thickness of approved protective material before any rope, cable, or wire is placed.

    - Repair or Treatment of Damage

The Contractor shall be responsible for injuries to trees and shrubs caused by his operations. The term “injury” shall include without limitation, bruising, scarring, tearing and breaking of roots, trunk or branches. All injured trees and shrubs shall be repaired or treated without delay, at the Contractor’s expense. If damage occurs, the Resident Engineer will determine method of repair or treatment to be used for injured trees and shrubs as recommended by an experienced horticulturist or a licensed tree surgeon provided by and at the expense of the Contractor.

    - Replacement

Trees or Shrubs that in the opinion of the Resident Engineer are beyond savings shall be removed and replaced early in the next planning season. The replacement shall be the same species or other approved species and of the maximum size that is practicable to plant and sustain growth in the particular environment. Replacement trees and shrubs shall be stayed, watered and maintained for a period of 1 year from the date of replacement.

  - Prevention of Water Pollution

    - General

The Contractor’s construction activities shall be performed by methods that will prevent entrance or accidental spillage, of solid matter, contaminants, debris, and other pollutants and wastes into streams, flowing or dry watercourses, lakes, and underground water sources, concrete, sanitary waste, industrial waste, radioactive substances, oil and other petroleum products, aggregate processing tailings, mineral salts and thermal pollution.

Dewatering work for structure foundations or earthworks operations adjacent to or encroaching on streams or watercourses shall be conducted in a manner to prevent muddy water and eroded materials from entering the streams or watercourses by construction of intercepting ditches, bypass channels, barriers, settling ponds or by other approved means. Excavated materials or other construction materials shall not be stockpiled or deposited near or on-stream banks, lake shorelines or other watercourse perimeters where they can be washed away by high water or storm runoff or can in any way encroach upon watercourse itself.

Turbidity increases in a stream or other bodies of after that are caused by construction activities shall be strictly controlled. When necessary to perform required construction work in a stream channel, the turbidity may be increased, as approved by the Resident Engineer, for the shortest practicable period required to complete such work. This required construction work may include such work as diversion of a stream, construction or removal of cofferdams, specified earthworks in or adjacent to a stream channel, pile driving, and construction of turbidity control structures. Mechanised equipment shall not be operating in flowing water except as necessary to construct crossing or to perform the required construction.

Wastewater from aggregate processing, concrete batching, or other construction operations shall not enter streams, watercourses, or other surface waters without the use of such turbidity control methods as settling ponds, gravel-filter entrapment dikes, approved flocculating processes that are not harmful to fish, re-circulation systems for washing of aggregates or other approved methods. Any such wastewaters, discharged into surface of these specifications, settle-able material is defined as that material possible. For the purpose of these specifications settle-able material is defined as material which will settle from the water by gravity during a 1- hour quiescent detention period.

    - Compliance with law and regulations

The Contractor shall comply with applicable laws and regulations and water quality standards concerning the control and abatement of water pollution.

  - Abatement of Air Pollution

The Contractor shall comply with applicable laws and regulations concerning the prevention and control of air pollution. Notwithstanding the above in conduct of construction activities and operation of equipment, the Contractor shall utilize such practicable methods and devices as are reasonably available to control prevent and otherwise minimize atmospheric emissions or discharges of air contaminants.

The emission of dust into the atmosphere shall be strictly controlled during the manufacture, handling and storage of concrete and road aggregates, and the Contractor shall use such methods and equipment as are necessary for the collection and disposal or prevention of dust during these operations. The Contractor’s methods of storing and handling cement and lime

shall also include means of eliminating atmospheric discharges of dust. Equipment and vehicles that show excessive emissions of exhaust gases due to poor engine adjustments or other inefficient operating conditions. Shall not be operated until corrective repairs or adjustments are made.

Burning of materials resulting from clearing of trees and bush, combustible construction materials, and rubbish will be permitted only when atmospheric conditions for burning are considered favourable and when authorized by the Resident Engineer. In lieu of burning, such combustible materials may be disposed of by other methods as provided in Clause 2.10 hereof. Where open burning is permitted, the burn piles shall be properly constructed to minimize smoke, and in no case shall unapproved materials such as tires, plastic rubber products, asphalt products, or other materials, that create heavy black smoke or nuisance odours, be burned.

  - Dust Abatement

During the performance of the work required by this specifications or any other appurtenant thereto, whether on right-of-way provided by the Employer or elsewhere, the Contractor shall furnish all the labour, equipment, materials, and means required, and shall carry out proper and efficient measures wherever and as often as necessary to reduce the dust nuisance and to prevent dust which has originated from his operations from damaging crops, orchards, cultivated fields and dwellings or causing nuisance to obtain adequate control.

  - Noise Abatement

The Contractor shall comply with applicable National laws, orders and regulations concerning the prevention, control and abatement of excessive noise.

Blasting, the use of jackhammers, pile driving, rock crushing or other operations producing high-intensity impact noise may be not be performed during the night.

  - Light Abatement

The Contractor shall exercise special care to direct all stationary flood-light to shine downwards at an angle less than horizontal. These floodlights shall also be shielded so as not to be a nuisance to surrounding areas. No lighting shall include a residence in its direct beam.

The Contractor shall be responsible for correcting light problems when they occur as directed by the Resident Engineer.

  - Preservation of Historical & Archaeological Data

Should the Contractor or any of his employees in the performance of his contract discover evidence of possible scientific, prehistoric, or archaeological data he will notify the Resident Engineer immediately, giving the location and nature of the findings. Written confirmation shall be forwarded within 2 days. The Contractor shall exercise care so as not to damage artefacts or fossils uncovered during excavation operation and shall provide such co-operation and assistance as may be necessary to preserve the findings for removal or other disposition by the employer. The Contractor will also report his findings for the Ministry of Forestry, Fisheries and Environmental Affairs and the authority responsible for antiquities.

Where appropriate by reasons of a discovery the Resident Engineer may order delays in the time of performance, or changes in the work, or both. If such delays, or changes or both are ordered, the time of performance and contract price shall be adjusted in accordance with the applicable clause in the conditions of contract.

The Contractor shall insert this Clause in all subcontracts that involve the performance of work on the project site.

  - Pesticides

Pesticides include herbicides, insecticides, fungicides rodenticides, and pesticides, surface disinfectants animal repellent and insect repellent. Should the Contractor find it necessary to use pesticides in work areas of this contract, he shall submit his plan for such use to the Resident Engineer for written approval.

The Contractor shall read and comply with all labelling requirements when using pesticides.

  - Clean-Up and Disposal of Waste Materials

    - Clean – Up

The Contractor shall, at all times keep the construction area, including storage areas used free from accumulation of waste material or rubbish.

All waste water and sewerage from office, residential and mobile camps shall be piped to soak pits or other disposal areas constructed in accordance with local government regulations, and where and when regulations require it the Contractor shall obtain a permit or other appropriate documentation approving the disposal methods used.

All used fuels, oils, other plant or vehicle fluids, and old tyres and tubes shall be collected to a central disposal area on a daily basis and disposed of in a manner approved by the Resident Engineer.

Servicing of plant equipment and vehicles shall whenever possible be carried out at a workshop area. This workshop area shall be equipped with secure storage areas for fuels oils and other fluids and constructed in such a way as to contain any spillage, which may occur, and similar storage where fluids can be stored securely prior to their disposal.

When servicing of plant, equipment and vehicles is carried out away from the workshop area it shall be done at locations and in such a manner as to avoid spillage and contamination of streams and other drainage courses. Any spillage shall be cleaned up by either burning in place or collecting the contaminated soils and burning them at the central disposal area, all to the satisfaction of the Resident Engineer.

Prior to the completion of the work, the Contractor shall remove from the vicinity of the work all facilities, buildings, rubbish, unused materials, concrete forms and other like material, belonging to him or used under his directions during construction.

All work areas shall be graded and left in a neat manner conforming to the natural appearance of the landscape as provided in these specifications.

Any residue deposited on the ground from washing out truck mixers, agitating trucks or any other similar concrete operations shall be buried or cleaned up in a manner acceptable to the Resident Engineer.

In the event of the Contractor’s failure to perform the above work, the work may be performed by the Employer at the expense of the Contractor, and his surety or sureties shall be liable therefore.

    - Disposal of Waste Material

      - General

Waste materials including, but not restricted to refuse, garbage, sanitary wastes industrial wastes and oil and other petroleum products, shall be disposed of by the Contractor. Disposal of combustible materials shall be by burying, where burial of such materials is approved by the Resident Engineer by burning, where burning of approved materials is permitted; or by removal from the construction area. Disposal of non-combustible materials shall be by burying where burial of such materials is approved by the Resident Engineer or by removal from the construction area. Waste materials removed from the construction area shall be dumped at an approved dump

      - Disposal of Material by Burying

Only materials approved by the Resident Engineer may be buried. Burial shall be in pits and the location, size and depth of which shall be approved by the Resident Engineer. The pits shall be covered by at least 0.6 metre of earth material prior to abandonment.

      - Disposal of Material by Burning

All materials to be burned shall be piled in designated burning areas in such a manner as will cause the least fire hazards. Burning shall be through and complete and all charred pieces remaining after burning, except for scattered small pieces, shall be removed from the construction area and disposed of as otherwise provided in this Clause.

The Contractor shall at all times, take special precautions to prevent fire from spreading beyond the piles being burned and shall be liable for any damage caused by this burning operation. The Contractor shall have available, at all times, suitable equipment and supplies for use in preventing and suppressing fires and shall be subject to all laws and regulations locally applicable for pre-suppression, suppression and prevention of fires.

      - Disposal of Material by Removal

Material to be disposed of by removal from the construction area shall be removed from the area prior to the completion of the work under these specifications. All materials removed shall become the property of the Contractor.

Materials to be disposed of by dumping shall be hauled to an approved dump. It shall be the responsibility of the Contractor to make any arrangements of such dumping. Any fees for charges required to be paid for dumping of materials shall be paid by the Contractor and shall be included in the prices tendered in the Bill of Quantities for other work.

  - PROJECT ENVIRONMENTAL MANAGEMENT PLAN (PEMP)

The Contractor will be deemed to have prepared his tender upon sound environmental practice and the guidelines contained in this section together with the entire contents of the Guidelines to Environmental Impact Assessment issued by the Ministry of Forestry, Fisheries and Environmental Affairs in December 1997 and the heading applicable to this contract in the Environmental Management Plan that follows this Section; as well as Environmental and Social Management Guidelines in the Road Sector issued by the Roads Authority in March 2008.

The PEMP will be read in conjunction with and shall be deemed to include all descriptions of environmental protection and mitigation described elsewhere in the Specification, Design Standards and Conditions of Contract. The PEMP will supplement but not supersede normal Regulatory Controls from Health and Safety Inspectorates and shall be made available to all parties.

The following is a summary of the guidelines to be incorporated into the PEMP:

    - Specific proposals

      - Drainage

Drainage and Proper installation of drainage structures

      - Soil erosion

        - Controlling and management of excavation activities

        - Installation of erosion control measures such as check dams, scour checks and impact dissipaters

        - Landscaping and re-vegetating road embankment and gravel sites

      - Pollution (air, noise, water)

        - Supervision of construction traffic, including control of speed

        - Sensitisation of workforce

        - Maintenance of plant and equipment

        - Proper disposal of construction debris, proper handling, storage and disposal of oil and oil wastes, and disposal of wastewater / sewage at Contractor’s

- /workmen’s camps

      - Materials sources

        - Planned, controlled and restricted access to all materials sites

        - Proper management of excavation activities

        - Landscaping, terracing where necessary, and grassing and re-vegetation of materials sites

        - Compensation of individuals/ communities as required for use of material

        - Controlled blasting of hard stone material

      - Water Sources

        - Consultation with communities during identification of sources

        - Management of water usage

      - Deviations

        - Planning of deviations

        - Reinstating deviations (and old tracks) to original condition

      - Vegetation

        - Prohibition of use of herbicides

        - Landscaping and planting all disturbed areas (pits, deviations, embankments, camps sites)

        - Planting of trees at main towns/trading centres along road for aesthetics and as pollution screens.

      - Demobilisation/ Decommissioning

        - Proper removal and disposal of construction buildings and structures required for the contractors’/workmen’s camp, and construction wastes including oil, solid wastes, and debris after construction works are complete, and restoration to original condition where applicable.

      - Land/property and crops

        - Notification to people about non – compensation for annual crops within road reserve

        - Evaluate land/property loss due to deviations, materials sites and Contractor’s camp

        - Compensation to be paid for land, crops and all property on land temporarily acquired for road construction works (camps and deviations) and for all crops outside road reserve that are removed/destroyed for clearing of carriageway, gravel pits and deviations

      - Public Health and Occupational Safety

        - Provision of water supply for the workforce, and proper facilities for the disposal of solid and sanitary waste

        - Provision of protective gear to workforce

        - Provision of a first aid kit on site

      - Road Safety

        - Supervision of construction traffic and management of construction activities

        - Provision of safe access/egress to work sites

        - Warning signs are erected.

      - Site of cultural, historical and traditional value

        - All findings to be reported to the Resident Engineer, RA Ministry responsible for antiquities and Department of Environmental Affairs.

        - All graves are avoided.

    - Planning and prevention

      - Frequency of Environmental site meetings to be chaired by the Environmental Control Officer and attended by relevant parties.

      - Adoption of time scale and planning for all relevant measures

      - Procedure for correction of bad practice

      - Reinstatement of borrow pits

    - Borrow areas

Borrow areas shall be reinstated in compliance with the following minimum specifications in the table below:

PIT AND QUARRY REINSTATEMENT SPECIFICATION

1. At the completion of operations, the Contractor shall rehabilitate used, exhausted and obsolete pits and quarries.

2. The sides and floors of pits shall be formed to a flowing finish with side slopes not steeper than 1 vertical to 6 horizontals.

3. During pit reshaping any material carried to the pit shall be spread uniformly over the entire shaped surface. The Contractor shall ensure that non – biodegradable and inert waste is removed and disposed of in licenced sites. The same will apply to toxic waste.

4. Topsoil shall be spread over the shaped batters, filled areas and bare areas of the pits to a reasonable depth.

5. Following the spreading of topsoil, the entire pit shall be ripped along the contours to a depth of 500mm and at not more than 500mm spacing.

REVEGETATION SPECIFICATION

1. Planting and direct seeding shall be carried out after the topsoil has been placed, shaped and prepared for planting and seeding operations

2. The Contractor shall prepare a plant and seed species list that is representative of the native vegetation (trees, and understorey species) in adjacent areas and the list is to be included in the Environmental Management Plan.

3. The plant and seed list shall describe the plant size and spacing of all plants, the quantities by seed species in a seed mix and the seeding rate (kg per hectare) to be used in any revegetation of the area to be rehabilitated.

REVEGETATION SPECIFICATION

4. The Contractor shall supply and hand-plant tube stock in good condition using the species and spacing chosen in the plant list.

5. The Contractor shall supply and direct seed the areas to be seeded using the seed species mix and seeding rate (kg per hectare) as described in the plant list.

6. All planting, seeding and or weed control operations shall be undertaken in accordance with basic principles of REVEGETATION AND LANDSCAPING.

7. The completion criteria for revegetation shall be in accordance with the Environmental Management Plan.

4.0	ENVIRONMENTAL TRAINING

The ECO will be responsible for organising the environmental training of all the Engineer’s and Contractor’s staff. It is suggested that this training is coupled with the safety training that the Contractor should include in his own site management plan. The Contractor shall ensure that the Resident Engineer is informed of all staff that will work on the site and their general responsibilities and shall make sure that they are available to attend suitable briefing sessions arranged by the ECO on the environmental mitigation measures that are to be in place on the site.

The Contractor shall provide the ECO with a suitable room for the briefing and such administrative support and facilities as shall be ordered by the ECO.

5.0	MEDICAL AND HIV/AIDS PREVENTION PROGRAMMES

To assist in the general health and well-being of both all the site staff and the residents in the community local to the works, the Roads Authority will organize and coordinate appropriate awareness training as well as health screening (other than accident prevention and medical aid facilities provided by the Contractor).

The Contractor shall ensure that the Resident Engineer is informed when any new staff commence work on the site such that health and HIV awareness and counselling can be provided either in group sessions or on an individual basis. The Contractor shall ensure that staff are available for briefing by the RA’s staff and shall make available suitable rooms, administrative support and provide any facilities or supplies against an order from the RA. The Contractor shall ensure that condoms provided as part of the HIV/STD control programme are readily available to all staff.

The RA will also arrange for the health screening of site workers in local medical facilities and the Contractor shall cooperate fully in these programmes by making staff available. The Contractor shall ensure that the Resident Engineer and local medical officials are informed promptly of any workers suffering from the symptoms of infectious disease so appropriate help and treatment can be arranged promptly.

6.0	ROAD SAFETY TRAINING

The RA will be arranging road safety training and awareness sessions in local schools and community centres. The Contractor will assist the RA when requested with administrative support and where ordered the provision of supplies for these courses and programmes.

7.0	RESPONSIBLE AUTHORITIES

The Contractor is advised that the following authorities have an interest in the environmental and social protective measures associated with this road construction project.

- Environmental Affairs Department Public Health Department

- Health and Safety Office

- Each District Assembly of Districts through which the road traverses.

8.0	SITE CLEARANCE

No trees are to be cut or removed unless required to be cleared or removed for construction works. Where there are branches overhanging roads or traffic diversion routes the Contractor shall agree with the SR the cutting back necessary to provide for clear vehicle access. The Branch cutting shall then be carried carefully using saws to leave a clean-cut face with no damages or snags.

    - FINISHING OF VERGES AND OTHER WORKS AREA

Verges, routes of diversion roads, site camps and all other areas where the Contractor’s work has heavily compacted the soil shall be loosened, spread with a thin layer of grass plant rich soil and firmed by foot or a light roller so as to encourage the re-growth of natural vegetation.

    - WATER POLLUTION

The Contractor shall observe the requirements to avoid the pollution of watercourses and ground water. Sanitary facilities for all site workers convenient to the working sites shall be provided to enable environmentally sensitive disposal of the waste. The storage of bitumen fuel and oil for the works operations shall be arranged in working sites, refuelling of all plant and equipment and servicing practices shall be arranged to prevent the uncontrolled spilling of any oil-based products.

Mitigation measures shall include drip trays, working on paved surfaces with waste collection arrangements and the provision of oil absorbing material for spills that can be subsequently disposed safely by burning.

Environmental and Social Management Plan Table

| Environmental Social Impact | Proposed Mitigation and Aspect for Monitoring | Responsibility for intervention and monitoring during design, construction and defects liability period | Responsibility for mitigation monitoring and/or maintenance after defects liability period | Monitoring means (c) = Construction (o) = operation | Recommended frequency of monitoring |
| --- | --- | --- | --- | --- | --- |
| ENVIRONMENTAL MANAGEMENT |  |  |  |  |  |
| Changes in hydrology impeded drainage | - Install drainage structure properly - Efficiency of drainage structures | Design consultant Supervising Engineer Supervising Engineer | Contractor District Works Offices | Inspection (o) routine maintenance and road condition survey | (c) during construction and on completion of each structure |
| Soil erosion | - Control earthworks - Install drainage structures properly - Install erosion control measures - Landscape and re-vegetate gravel sites - Management of excavation activities - Impact on erosion (on road, off road, embankments, riverbanks, etc) - Efficiency of erosion control measures - Landscape and grass road embankment | Supervising Engineer and Contractor Designer /RA District Works Offices RA | Supervising Engineer and Contractor | (c ) inspection (o) routine maintenance and road condition survey (c ) inspection (o) routine maintenance and road condition survey | (c) daily erosion control measures during construction and on completion of measures (o ) once in 6 months (c ) once a month |
| Air pollution | - Control speed of construction vehicles - Prohibit idling of vehicles - Sensitive workforce - Maintenance of plant and equipment - Plant trees in towns as pollution screens - Impose speed limits for all vehicles, especially at towns and villages - sensitize motorists/road users | Supervising Engineer and Contractor Designer/ RA | TA \Health and Environment committees Traffic police | (c ) inspection/ observation (o) observation | (c) Daily /random (o) random |
| Noise pollution | - Sensitize workforce - Supervise construction traffic - Sensitise drivers of construction vehicles - Maintain plant and equipment | Supervising Engineer and Contractor | TA Health and environment Committees Traffic police | (c ) inspection/ observation (o) observation | (a) Daily /random (o) random |
|  | - Impose speed limits for all vehicles, especially at towns and villages - Sensitize motorists /road users |  |  |  |  |
| Water pollution | - Incorporate erosion control measures - Works on culverts to be done in the dry season - Proper disposal of construction debris - Proper handling, storage and disposal of oil and oil wastes - Proper disposal of wastewater /sewerage at Contractor’s workmen’s camps | Designer/ RA | Contractor | (c ) inspection | (c ) daily |
|  |  | Supervising Engineer and Constructor |  |  |  |
| Oil pollution | - Construct parking bays at larger trading centres for heavy vehicles. - Proper storage, handling and disposal of oil and oil wastes - Maintain plant and equipment - Maintenance of construction vehicles should be carried out in the Contractor’s camp | Design Consultant Supervising Engineer and Contractor | Contractor | (c ) Inspection (o) routine maintenance | (c ) during construction and on completion |
|  |  |  |  |  | (o) once in 6 months |
|  |  | Supervising Engineer and Contractor |  |  | (c) daily |
| Gravel sites | - Inform people living at/near the sites that the pits have been selected for exploitation. - Plan access to gravel sites - Control and restrict access to gravel sites (e.g. by fencing ) - Control earthworks - Proper management of excavation activities - Landscape terrace if necessary, and grass site s. Replace trees that were removed during excavation - Discourage pits being made into water pans after construction | Supervising engineer and Contractor |  | ( c) meeting (c ) Inspection (c ) Payment records (o ) Inspection | (c ) Once immediately after selection of sites |
|  |  | Supervising Engineer and Contractor Contractor | District Works offices RA |  | (c ) daily (o) once before excavation begins and at specified periods as agreed thereafter (c ) once in 2 months (o) once in 6 months |
|  |  | Supervising Engineer |  |  |  |
|  | Rehabilitate old unused gravel pits - Compensate individuals/ communities as required for use of material - Progress of rehabilitated gravel sites (use of site, established vegetation) |  |  |  |  |
| Hard stone sources | - Inform communities living at/near the sites that the sites have been selected for exploitation. - Plan access to hard stone sites - Control and restrict access to hard stone sites (e.g. by fencing) - Control blasting - Proper management of exploitation activities - Landscape site after exploitation and grass sites. Replace trees or vegetation that were removed during excavation - Compensate individuals / communities as required for use of material | Supervising Engineer and Contractor |  | (c ) meeting (c ) inspection | (c) Once immediately after selection of sites |
|  |  | Supervising Engineer and Contractor |  |  | (c) daily |
|  |  | Contractor |  | (c) payments records | (o) once before excavation begins and at specified periods as agreed thereafter |
| Sand sources | - Take sand from beds of large rivers only - Extraction to be done during low flow | Supervising Engineer and Contractor | n/a | (c ) inspection | (c ) during mining |
| Water sources | - Consult with communities during identification of sources - Management of water usage | Designer /RA | n/a | (c ) meetings, inspection , check plans and schedule | c) during rains during abstraction at source and at random |
| Deviations | - Plans deviations - Adhere to road reserve if possible - Obtain permission from | Supervising Engineer | Contractor | (c) check plans | (o) daily |
|  |  | and |  | inspections | when |
|  |  | Contractor |  |  | deviations are |
|  |  |  |  |  | in use |
|  | inhabitant/comm unity if deviation goes beyond road reserve - Re instate deviations (and old tracks) to original condition - Pay compensation for crops/property removed/ destroyed by deviations - Monitor rehabilitation of deviations | Contractor | District Works Offices RA | (o) Payment records | (c ) once before constructing deviations |
|  |  |  |  |  | (o) Once in 6 months |
| Vegetation / flora / forests | - Control clearing - Prohibit clearing using herbicides - Replant areas where vegetation is unnecessarily removed - Landscaping and planting all disturbed areas (pits, deviations embankments, camp sites) - Plant trees at main towns/ trading centres along road | Supervising Engineer and Contractor | Contractor | ( c) inspection | (c ) daily |
|  |  | TA Health and Environment Committees |  |  |  |
|  | - Planting and grassing should be done just before the rains - Discourage use of firewood/charcoal by providing alternatives - Care for tree/plants |  | TA Health and Environment Committees | (c ) observation (o ) observation | (c ) weekly ( o) Random |
| Workmansh ip | - locate camp in terminal town - provide water supply - provide proper sanitation facilities on site - Provide proper solid waste disposal facilities - Have central canteen facilities - Discourage use of firewood/charcoal by providing alternatives - Manage water use in camps | Supervising Engineer and Contractor | Contractor | (c ) inspection | (c ) daily |
| Visual Enlargemen t | - Landscaping and planting of deviations, gravel sites and camp - Plant trees at terminal towns and trading centres - Care for plants and trees | Designer /RA TA health and Environment committees | Contractor TA Health and Environment Committees | (c ) inspection (c ) observation (o) observation | (c ) daily / random (c ) Weekly (o) random |
| Constructio n waste | - Proper disposal of construction wastes including oil, solid wastes and debris | Supervising Engineer and Contractor | Contractor | (c ) inspection | (c ) weekly |
| Demobilisati on | - Clean up site - Remove all debris - Remove to original condition | Supervising Engineer and Contractor | Contractor | (c ) inspection and certificate of completion | (c ) on completion of road construction works |
| SOCIAL MITIGATION |  |  |  |  |  |
| Settlement | - Plan for increased population and subsequent expansion of terminal towns and trading centres - Conduct STD/AIDS awareness campaign - Plan for local security | District Physical Planning Department Supervising Engineer | District Physical Planning Department | (c ) meetings, Barraza’s (o) reports (c ) inspection records | (c ) once during construction (o) annually (c ) continuous (c ) continuous (o ) continuous |
|  |  | TAs |  | (c ) meetings, deployment of local police |  |
| Loss of Land /property | - Identify project affected people - Notify people about non- compensation for annual crops within road reserve - Evaluate land/property loss due to deviations, materials sites and contractor’s camp - Compensation to be paid for land and all property on land to temporally acquired for road construction works | RA | n/a | (c ) inspection (c) notices, meetings | (c ) Once before construction commences |
|  |  | Contractor |  | (c ) inspection (c ) payments records | (c ) compensation paid once after assessment of loss before construction |
| Loss of crops | - Limits clearing of crops as much as possible - Pay compensation for | RA Supervising Engineer and Contractor | Supervising Engineer and Contractor | (c ) inspector (c ) payment records | (c ) Daily (c ) Once after assessment of |
|  | all crops outside road reserve that are removed/destroy ed for clearing of carriage way , gravel pits and deviations - Compensation to be paid for perennial crops within road reserve | RA |  |  | loss before construction |
| Employment | Recruit local people, of which at least 25% should be women | Contractor | n/a | (o) certificate of employment | (o ) quarterly |
| Public Health and Occupational safety | - Reduce/minimiz e pollution as above - Provide water supply at camps - Proper disposal of solid and sanitary waste at camps - Design and locate pit latrines prudently - Have communal ablution facilities - Conduct STD/AIDS, awareness campaign and distribute condoms - Provide potable water for workforce - Provision of protective gear to workforce - First Aid Kit on site - Appoint Health Safety and Environment officer on site - Contractor should have workmen’s compensation cover - Monitor impact on public health (incidence of malaria, respiratory diseases such as Covid-19, STDs HIV/AIDS) | Supervising Engineer and Contractor RA/Ministry of health | Contractor RA Ministry of Health | (c ) Inspection (o) Independent study | (c ) daily (o ) once in 6 months |
|  | - Conduct Covid- 19 awareness campaign and provide prevention measures. |  |  |  |  |
| Disturbance to public | - Minimise pollution as above - Erect information and warning signs - Control construction activities - Construct special parking bay at terminal towns for trucks/heavy vehicles | Supervising Engineer Supervising Engineer Supervising Engineer and Contractor Design Consultant | Contractor District Works Offices | ( c) Inspection ( c) Inspection ( c) Inspection ( c) Inspection (o) routines maintenance | (c )daily (c ) when affected (c )daily (c ) during construction and on completion (o ) once in 6 months |
| Road Safety | - Install speed bumps near school and trading centres - Supervise construction traffic - Ensure safe access/egre ss to work sites - Erect warning signs - Construct shoulders which can be used by pedestrians and non motorized traffic - Construct special parking bay at large trading centres for trucks/heavy vehicles - Impact on road safety (number of accidents) | Design Engineer Supervising Engineer and Contractor Design Consultant | Supervising Engineer and Contractor District Works Offices District Works offices RA | (o) (c) Inspection (c) Inspection (o) routines maintenance (c) Inspection (o) routine maintenance (o) Police report | (c)daily (c) when designed (o) once in 6 moths |
| Socio-economic status | - Changes in income level - Change in health status | n/a | RA | (o) Independent Study | (o) once in 5 years |
|  | - Changes in education levels. - Changes in gender equality |  |  |  |  |
| Economic activity in project area | - Changes in agricultural production and marketing - Changes in livestock production and marketing | n/a | District Agricultural Officers/RA | (o) Independent study | (o) once in 5 years |

E. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY REQUIREMENTS

[The Procuring and Disposing Entity shall use the services of suitably qualified environmental, social, health and safety specialists to prepare the specifications for ESHS.

The Procuring and Disposing Entity shall attach or refer to its environmental, social, health and safety policies that will apply to the project.

If these are not available, it shall use the guidance in the User Guide in drafting an appropriate policy for the works]

ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION

We, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

1. PLEDGE THAT-

- We have read, understood, and will comply with:

- the Environment Management legal framework or policies in conservation and management of the environment;

- all necessary and appropriate measures to protect and manage the environment;

- all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources; and

- all steps and measures necessary for ensuring that social safeguards including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters.

2. AGREE THAT -

- In the event that our Bid is successful, we shall, within fifteen (15) days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation  Plan.

- Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters.

Signed: ………………………………………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of …………………………………………………………………………………………………… [insert legal capacity of person signing the Bid]

Name: ………………………………………………………………………………………………………

….[insert complete name of person signing the Bid]

Duly authorised to sign the Bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

F. COMPLETION SCHEDULE

G. SUPPLEMENTARY INFORMATION

Technical Specifications for 4WD Double Cab Vehicle with Lockable canopy

| (a) Item | (b) Technical Specification Required Including Applicable Standards |
| --- | --- |
| - General | - Must be factory new and latest model - Must conform to all road conditions and tropical environment. |
| - Body Type | - Double cabin with canopy. - Electric operated windows - Four doors central locking system - Must have SRS air bags for driver and passengers - Dual airbag system - Seating capacity of five including a driver - Seats with seat belts and rear view mirrors - Side steps should be provided - With keyless starting system/with two smart entry keys |
| - Colour | - White/Silver |
| - Engine | - Four-cylinder diesel four cylinder inline OHC OR DOHC - Electronic Fuel injection system - 1850cc - 2500cc with turbo-charger - Minimum power 120@3200 rpm - Minimum torque 380@1800-2200 rpm |
| - Tyres | - Manufactures model specified size and one spare tyre. |
| - Gross Weight | - Minimum 2900kgs. |
| - Transmission | - 6 speed automatic and reverse gear. - Rear diff lock. - Four wheel drive |
| - Wheel Base | - Above 3075mm |
| - Ground Clearance | - Minimum 220mm. |
| - Chassis | - Rigid steel with rust protection. |
| - Suspension | - Heavy-duty upper and lower wishbone. - Rear- Rigid semi-elliptic leaf spring. |
| - Steering | - Right Hand Drive. - Power assisted steering system. - Telescopic and tilt steering system |
| - Brakes | - Ventilated disc in front and brake drum at rear. - With EBD and ABS |
| - Fuel Tank Capacity | - Not less than 70 litres |
| - Electrical System | - 12 volts electrical system to conform to all Road traffic Act and laws of Malawi |
| - Instruments | - Full Board thus speedometer LCD/ fuel gauge, temperature gauge, oil gauge. - Pressure gauge, low-level warning lamp. |
| - Miscellaneous Equipment | - Air conditioner non-cfc, heater - Radio with FM and AM, CD player Mp3 and speakers. - Manufactures approved Jack, wheel spanner, and tool kit - Two reflecting red warning triangles plates - Owner’s manual in English. - Fire extinguishers should be provided and properly secured. - Bluetooth and USB port - Fog lights should provided - Roll bar nudge bar and tow bar hook should be fitted - Lockable canopy factory fitted |
| - Local Back up Service | - Must be available in Malawi. - Authorized Agent/ dealership be available. |
| - Warranty | - Must be provided for a specified period or kilometers whichever comes first - Free service must be provided |

# SECTION 8. GENERAL CONDITIONS OF CONTRACT

SECTION 8. GENERAL CONDITIONS OF CONTRACT

| - GENERAL |
| --- |
| - DEFINITIONS |
| - In these General Conditions of Contract, unless the context otherwise requires - “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clause 28 hereunder; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Compensation Events” are those defined in clause 46; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 58; “Contract” is an agreement between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Nofication of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed Bid document submitted by the Contractor to the Procuring and Disposing Entity; “day” means calendar day; “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date during which the contractor has an obligation to return to the site to correct any defects; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Price listed in the Procuring and Disposing Entity’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “month” means a calendar month; Procuring and Disposing Entity” is the party named in the SCC which employs the Supplier to carry out the Works; “plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Performance Security” is any monetary surety required by the Client to guarantee performance by the Contractor under the Contract; “Site” is an area where a project is being implemented as defined in the Special Conditions of Contract; “Site Investigation Report” means the factual and interpretative report about the surface and subsurface conditions at the Site; “site possession date” means the formal handing over of a construction site by the Client to the Contractor, granting the Contractor exclusive access and control of the area to begin construction work; “specification” means the specification of the Works included in the Contract and any modification or addition made or approved by the Client; “start date” means the the latest date when the Contractor shall commence execution of the Works as provided in the SCCs. It does not necessarily coincide with any of the Site Possession Dates; “subcontractor” means a person or corporate body assigned to carry out part of the work in the Contract, which includes work on the Site; “temporary Works” means works designed, constructed, installed, and removed by the Contractor that are needed for construction or installation of the Works; “variation” means an instruction given by the Client which varies the Works; and “works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - INTERPRETATION |
| - In interpreting these General Conditions of Contract, singular includes plural, male also means female or neuter, and the other way around. - Headings have no significance. - Words have their normal meaning under the language of the Contract unless specifically defined. The Client will provide instructions clarifying queries about these General Conditions of Contract. - If sectional completion is specified in the Special Conditions of Contract, references in the General Conditions of Contract to the Works, the Completion Date, and the Intended Completion Date apply to any Section of the Works (other than references to the Completion Date and Intended Completion Date for the whole of the Works). |
| - The documents forming the Contract shall be interpreted in the following order of priority- - Agreement (signed by both parties); - Minutes of Contract Negotiations; - Notification of Award; - Bid Submission Sheet; - Special Conditions of Contract; - General Conditions of Contract; - Specifications; - Drawings; Priced Bill of Quantities; and - Any other documents listed in the Special Conditions of Contract as forming part of the Contract. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. - In line with the existing Anti-Corruption law and policy, a Bidder, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. |  |
| - LANGUAGE AND LAW |
| - The language of the Contract is English and the law governing the Contract is that of Republic of Malawi. |
| - Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - JOINT VENTURE, CONSORTIUM OR ASSOCIATION If the Supplier is a joint venture, consortium, or association, all the parties shall be jointly and severally liable to the Procuring and Disposing Entity for the fulfilment of the provisions of the Contract and shall designate one party to act as a leader with authority to bind the joint venture, consortium, or association as specified in the SCC. The composition or the constitution of the joint venture, consortium, or association shall not be altered without the prior consent of the Procuring and Disposing Entity. - DELEGATION |
| 6.1 The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. 6.2 The Client’s specific approval is required for actions detailed in the SCC. |
| - COMMUNICATIONS |
| 7.1 Any communications between parties that are referred to in these Conditions shall be made in writing. 7.2 A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| 8.1 The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the written approval of the Client. 8.2 Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| 9.1 The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client on the dates given in the Schedule of Other Suppliers. The Contractor shall also provide facilities and services for them as described in the Schedule. 9.2 The Client may modify the Schedule of other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL |
| - The Contractor shall employ the key personnel named in the Schedule of Key Personnel, referred to in the SCC, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. - The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. - The Project Manager may request the Contractor to remove a person who is a member of the Contractor’s staff or work force and state the reasons thereof. - The Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract. |
| - PROCURING ENTITY’S AND CONTRACTOR’S RISKS |
| The Client carries the risks which this Contract states are Client’s risks, and the Contractor carries the risks which this Contract states are Contractor’s risks. |
| - PROCURING ENTITY’S RISKS |
| - From the Start Date until the Defects Liability Certificate has been issued, the following are the Client’s risks- - the risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to- - use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works; or - negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. - The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi. |
| - From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to - - a Defect which existed on the Completion Date; - an event occurring before the Completion Date, which was not itself a Client’s risk; or - the activities of the Contractor on the Site after the Completion Date. |
| - CONTRACTOR’S RISKS |
| From the Starting Date until the Defects Liability Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) which are not Client’s risks are Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts and deductibles stated in the SCC for the following events which are due to the Contractor’s risks: - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death. |
| - The Contractor shall deliver policies and certificates for insurance to the Project Manager for the Project Manager’s approval before the Start Date. All such insurance shall provide for compensation to be payable in the types and proportions of currencies required to rectify the loss or damage incurred. - If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of insurance shall not be made without the approval of the Project Manager. - Both parties shall comply with any conditions of the insurance policies. |
| - SITE INVESTIGATION REPORTS |
| The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder. |
| - QUERIES ABOUT THE SPECIAL CONDITIONS OF CONTRACT |
| The Project Manager shall be responsible for clarification of queries from the Contractor on the Special Conditions of Contract. |
| - CONTRACTOR TO CONSTRUCT THE WORKS |
| The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - COMMENCEMENT AND COMPLETION DATES |
| The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Programme submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - APPROVAL BY THE PROJECT MANAGER |
| - The Contractor shall submit Specifications and Drawings showing the proposed Temporary Works to the Project Manager, for approval if they comply with the Specifications and Drawings. - The Contractor shall be responsible for design of Temporary Works. |
| - The Project Manager’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works. - The Contractor shall obtain approval of third parties to the design of the temporary works, where required. - All Drawings prepared by the Contractor for the execution of the temporary or permanent works, shall be subject to prior approval by the Project Manager before use. |
| - HEALTH AND SAFETY |
| - The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - DISCOVERIES |
| 21. 1 Anything of historical or other interest or of significant value unexpectedly discovered on the Site shall be the property of the Client. 21. 2The Contractor shall notify the Project Manager of such discoveries and carry out the Project Manager’s instructions for dealing with them. |
| - POSSESSION OF THE SITE |
| 22.1 The Client shall formally give possession of all parts of the Site to the Contractor on an agreed date. 22.2 If possession of a part is not given by the date stated in the SCC, the Client will be deemed to have delayed the start of the relevant activities, and this will be a compensation event. |
| - ACCESS TO THE SITE |
| The Contractor shall allow the Project Manager and any person authorised by the Project Manager access to the Site and to any place where work in connection with the Contract is being carried out or is intended to be carried out. - CONTRACTOR’S EQUIPMENT 24.1 The Contractor shall be responsible for all Contractor’s equipment. 24.2 When brought on to the Site, Contractor’s equipment shall be deemed to be exclusively intended for the execution of the Works. 24.3 The Contractor shall not remove from the Site any major items of Contractor’s Equipment without the consent of the Project Manager. 24.4 The consent of the Project Manager shall not be required for vehicles transporting Goods or Contractor’s Personnel off Site. - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of its operations. - The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. - Within thirty (30) days after signing of the contract, the successful Bidder shall where applicable, furnish to the Procuring and Disposing Entity if required in the BDS, the Environmental and Social (ES) Performance Security in the amount stipulated in the SCC and in the form of an on-demand Bank Guarantee denominated in the type and proportions of the currencies of the Contract. The Environment and Social (ES) Performance Security shall be issued by a Bank located in Malawi or a foreign Bank through correspondence with a Bank located in Malawi. - Failure of the successful Bidder to submit the Environmental and Social (ES) Performance Security shall constitute sufficient ground for annulment of the contract award decision. - Failure to submit the ES or failure to sign the contract as stated in ITB clause 43.6, shall lead to forfeiture of the successful Bidder’s Bid Security. In that event, the PDE may award the contract to the next best ranked Bidder whose Bid was evaluated at the financial comparison stage. - PROHIBITION OF CHILD LABOUR AND OTHER HARMFUL LABOUR PRACTICES - The Contractor and its Subcontractor(s) shall not employ children under the age of eighteen (18) in accordance with the labour laws and regulations applicable in Malawi and internationally. - A Contractor and its Subcontractor(s) shall ensure that they comply with all laws, policies, programs and interventions against gender inequality, sexual exploitation and abuse, as applicable in Malawi and internationally. |
| - INSTRUCTIONS |
| The Contractor shall carry out all instructions of the Project Manager which comply with the applicable laws where the Site is located. |
| - PROCEDURE FOR DISPUTES RESOLUTION |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to an Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the BDS and SCC, together with reimbursable expenses of the types specified in the SCC, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. - Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The arbitration shall be conducted in accordance with the arbitration procedure published by the institution named and, in the place, shown in the SCC. |
| - Where the Adjudicator resigns or dies or the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor within thirty (30) days. - In case of disagreement between the Client and the Contractor,on the appointment of the Adjudicator under clause 28.6, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party, within fourteen (14) days of receipt of such request. |
| - TIME CONTROL |
| - PROGRAMME OF WORKS |
| - Within the time stated in the SCC, the Contractor shall submit to the Project Manager, for approval, a Revised Programme of Works showing the general methods, arrangements, order, and timing for all the activities in the Works . - An update of the Programme shall be a programme showing the actual progress achieved on each activity and the effect of the progress achieved on the timing of the remaining work, including any changes to the sequence of the activities. |
| - The Contractor shall submit to the Project Manager for approval an updated Programme at intervals no longer than the period stated in the SCC. - If the Contractor does not submit an updated Programme within this period, the Project Manager may withhold the amount stated in the SCC from the next payment certificate and continue to withhold this amount until the next payment after the date on which the overdue Programme has been submitted. - The Project Manager’s approval of the Programme shall not alter the Contractor’s obligations. - The Contractor may revise the Programme and submit it to the Project Manager again at any time. - A revised Programme shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager, with approval of the Client, shall extend the Intended Completion Date if a Compensation Event occurs or a variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. - The Project Manager, with approval of the Client, shall decide whether and by how much to extend the Intended Completion Date within twenty-one (21) days of the Contractor requesting the Project Manager for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information. If the Contractor has failed to give early warning of a delay or has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new Intended Completion Date. |
| - ACCELERATION |
| - When the Client requires the Contractor to complete the works before the Intended Completion Date, the Project Manager will obtain priced proposals for achieving the necessary acceleration from the Contractor. - If the Client accepts these proposals, the Intended Completion Date will be adjusted accordingly and confirmed by both the Client and the Contractor. - If the Contractor’s priced proposals for acceleration are accepted by the Client, the proposals will be incorporated in the Contract Price and treated as a Variation. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| The Project Manager, with approval of the Client, may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - MANAGEMENT MEETINGS |
| - Either the Project Manager or the Contractor may require the other to attend a management meeting to review the plans for remaining works and to deal with matters raised in accordance with the early warning procedure. - The Project Manager shall record the business of management meetings and provide copies of the record to those attending the meeting and to the Client. The responsibility of the parties for actions to be taken shall be decided by the Project Manager either at the management meeting or after the management meeting and stated in writing to all who attended the meeting. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. - The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. - The Contractor as soon as reasonably possible and no later than the period specified in the SCC, shall provide the estimate. - Where the Contractor fails to give an early warning within such period as stated in the SCC, the time for Completion shall not be extended, the Contractor shall not be entitled to additional payment because of a Compensation Event and the Client shall be discharged from all Liability in connection with claims for extension of the Intended Completion Date and for a Compensation Event. - The Contractor shall cooperate with the Project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone involved in the work and in carrying out any resulting instruction of the Project Manager. |
| - QUALITY CONTROL |
| - IDENTIFYING DEFECTS |
| 35.1 The Project Manager shall check the work of the Contractor and notify the Contractor of any defect found. 35.2 Such checking shall not affect the Contractor’s responsibilities under the contract. 35.3 The Project Manager may instruct the Contractor to search for a Defect and to uncover and test any work that the Project Manager considers may have a Defect. |
| - TESTS |
| If the Project Manager instructs the Contractor to carry out a test that is not specified under clause 35 and the test shows a defect, the Contractor shall pay for the test and any samples. If there is no Defect, the test shall be a Compensation Event. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period. - The Defects Liability Period shall be extended for as long as identified defects remain to be corrected. - Every time notice of a defect is given, the Contractor shall correct the notified Defect within the time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| 38.1 If the Contractor has not corrected a defect within the time specified under clause 37, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. 38.2 The amount in clause 38.1 will be deducted from current and future payment certificates or paid by the Contractor if insufficient funds are due under the contract. |
| - COST CONTROL |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is - - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, as indicated in the SCC. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities shall be used to calculate the Contract Price. - The Contractor shall be paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Project Manager shall request the Contractor to provide an updated Activity Schedule. - The Contractor shall provide an updated Activity Schedule within fourteen (14) days of being instructed by the Project Manager. The activities on the Activity Schedule shall be co-ordinated with the activities on the Programme. - The Contractor shall show delivery of materials to the Site separately on the Activity Schedule if payment for materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, Provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if the Initial Contract Price is exceeded by more than the percentage stated in the SCC, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Programme or method of working made at the Contractor’s own discretion. - Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| The Contractor shall include all Variations in updated Programmes (or in the case of Lump Sum Contracts in updated Programmes and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out a variation when requested to do so by the Project Manager. - The quotation in clause 42.1 shall be submitted within seven (7) days of the request or any longer period as stated by the Project Manager. - The Project Manager shall assess the quotation. - For Admeasurement Contracts only, if the work in the variation corresponds with an item description in the Bill of Quantities and if, in the opinion of the Project Manager, the quantity of work above the limit stated in clause 40.1 or the timing of its execution do not cause the cost per unit of quantity to change, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates, which shall be lower, for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given, and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - CASH FLOW FORECASTS |
| 43.1 When the Programme or in the case of Lump Sum Contracts, the Programme or Activity Schedule, is updated, the Contractor shall provide the Project Manager with an updated cash flow forecast. 43.2 The cash flow forecast shall include different currencies, where applicable and as defined in the Contract, converted as necessary using the Contract exchange rates. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager, monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s monthly statement and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - The value of work executed and materials on site shall comprise the value of- - the quantities of the items in the Bill of Quantities completed in the case of Admeasurement Contracts; or - completed activities in the Activity Schedule in the case of Lump Sum Contracts. - The value of work executed shall include the valuation of variations and Compensation Events. - The Project Manager may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. - The Client shall pay the Contractor the amounts certified by the Project Manager within forty-five (45) days of the date of each certificate. - If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. - Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing for each of the currencies in which payments are made. - If an amount certified is increased in a later certificate as a result of an award by the Adjudicator or an Arbitrator, the Contractor shall be paid interest upon the delayed payment as set out in this clause. Interest shall be calculated from the date upon which the increased amount would have been certified in the absence of dispute. |
| - Unless otherwise stated, all payments and deductions will be paid or charged in the proportions of currencies comprising the Contract Price. - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events - - the Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract; - the Client modifies the Schedule of Other Suppliers in a way that affects the work of the Contractor under the Contract; - the Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time; - the Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects; - the Project Manager unreasonably does not approve a subcontract to be let; - ground conditions are substantially more adverse than could reasonably have been assumed before issuance of the Notice of Acceptance from the information issued to Bidders (including the Site Investigation Reports), from information available publicly and from a visual inspection of the Site; - the Project Manager gives an instruction for dealing with an unforeseen condition, caused by the Client, or additional work required for safety or other reasons. - other Suppliers, contractors, public authorities, utilities, or the Client does not work within the dates and other constraints stated in the Contract, and they cause delay or extra cost to the Contractor; - the advance payment is delayed. - the adverse effects on the Contractor of any of the Client’s Risks; - the Project Manager unreasonably delays issuing a Certificate of Completion beyond a period of thirty (30) days; and - other Compensation Events described in the SCC or determined by the Project Manager shall apply. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased or the Intended Completion Date shall be extended. The Project Manager, with the approval of the Client, shall decide whether and by how much the Contract Price shall be increased and where determined necessary, the period of extension for the Intended Completion Date. - The Project Manager shall submit information indicating or demonstrating the effect of each Compensation Event and the forecast on cost for the Contractor. - The Project Manager shall assess the information submitted under clause 46.3, and the Contract Price shall be adjusted accordingly. - If the Contractor’s forecast is deemed unreasonable, the Project Manager shall adjust the Contract Price based on the Project Manager’s own forecast. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor’s not having given early warning or not having cooperated with the Project Manager. |
| - TAXES |
| 47. 1 The Project Manager shall adjust the Contract Price if taxes, duties, and other levies are changed twenty-eight (28) days before the submission of Bids for the Contract and the date of the last Completion certificate. 47.2 The adjustment shall be the change in the amount of tax payable by the Contractor, provided such changes are not already reflected in the Contract Price or are a result of clause 50. |
| - CURRENCIES |
| Where payments are made in currencies other than Malawi Kwacha, the exchange rates used for calculating the amounts to be paid shall be the exchange rates stated in the Bid Data Sheet. |
| - PRICE ADJUSTMENT |
| - Prices shall be adjusted for fluctuations in the cost of inputs only if provided for in the SCC. - If so provided, the amounts certified in each payment certificate, after deducting for Advance Payment, shall be adjusted by applying the respective price adjustment factor to the payment amounts due in each currency. - A separate formula of the type indicated below applies to each Contract currency: Pc = Ac + Bc Imc/Ioc where: Pc is the adjustment factor for the portion of the Contract Price payable in a specific currency “c”. Ac and Bc are coefficients specified in the Special Conditions of Contract, representing the nonadjustable and adjustable portions, respectively, of the Contract Price payable in that specific currency “c”; and Imc is the index prevailing at the end of the month being invoiced and Ioc is the index prevailing twenty-eight (28) days before Bid opening for inputs payable; both in the specific currency “c”. - If the value of the index is changed after it has been used in a calculation, the calculation shall be corrected, and an adjustment made in the next payment certificate. The index value shall be deemed to take account of all changes in cost due to fluctuations in costs. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor, the proportion stated in the SCC until completion of the whole of the works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and the remaining half when the Defects Liability Period has passed, and the Project Manager has certified that all defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, upon completion of the whole Works, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the SCC for each day that the Completion Date is later than the Intended Completion Date. - The total amount of liquidated damages shall not exceed the amount provided in the SCC. - The Client may deduct liquidated damages from payments due to the Contractor. - Payment of liquidated damages shall not affect the Contractor’s liabilities. - If the Intended Completion Date is extended after liquidated damages have been paid, the Project Manager shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment certificate. - The Contractor shall be paid interest on the underpayment, calculated from the date of payment to the date of repayment, at the rates specified in clause 45.1. |
| - BONUS |
| The Contractor shall be paid a Bonus calculated at the rate per day stated in the SCC for each day (less any days for which the Contractor is paid for acceleration) that the Completion is earlier than the Intended Completion Date. The Project Manager shall certify that the Works are complete, although they may not be due to be complete. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment to the Contractor of the amounts stated in the SCC by the date stated in the SCC, against provision by the Contractor of an Unconditional Bank Guarantee in a form and by a bank acceptable to the Client in amounts and currencies equal to the advance payment. - The Guarantee shall remain effective until the advance payment has been repaid, but the amount of the Guarantee shall be progressively reduced by the amounts repaid by the Contractor. - Interest shall not be charged on the advance payment. - The Contractor shall use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. Any expenditure apart from these will be considered ineligible. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, following the schedule of completed percentages of the Works on a payment basis. No account shall be taken of the advance payment or its repayment in assessing valuations of work done, Variations, price adjustments, Compensation Events, Bonuses, or Liquidated Damages. |
| - SECURITIES |
| - The Contractor shall provide a Performance Security to the Client within thirty (30) calendar days of receipt of the Notice of Acceptance in the amounts indicated in the SCC. - The contractor shall provide a Performance Security and an Environmental and Social, (ES) Performance Security for compliance with the Contractor’s ESHS obligations for the due performance of the Contract. - The Performance Security and the ES Performance Security shall be in the amount specified in the SCC in the form of a Bank Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client) and shall be denominated in the currency in which the Contract Price is payable. - The proceeds of the Performance Security and, if applicable, the ES Performance Security shall be payable to the Procuring and Disposing Entity as compensation for any loss resulting from the Contractor’s failure to complete its obligations under the Contract. - The Performance Security and the ES Performance Security shall be in the form stipulated in Section 10 of the Bidding document. - The Performance Security and, if applicable, the ES Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Acceptance and shall be issued in the form of a Bank Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client, and denominated in the types and proportions of the currencies in which the Contract Price is payable. The Performance Security (Bank Guarantee) shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion. - An advance payment shall not be made unless and until the Contractor furnishes an advance payment guarantee covering the amount of the advance payment. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Liability period shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION OF THE CONTRACT |
| - COMPLETION |
| The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so determining that the work is completed. |
| - SITE TAKEOVER |
| The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| 59.1 The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. 59.2 The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within sixty (60) days of receiving the Contractor’s account if it is correct and complete. 59.3 If the Contractor’s account is incorrect or incomplete, it is not, the Project Manager shall issue within sixty (60) days a schedule that states the scope of the corrections or additions that are necessary. 59.4 If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - OPERATING AND MAINTENANCE MANUALS |
| - If “as built” Drawings or operating and maintenance manuals are required, the Contractor shall supply them by the dates stated in the SCC. |
| - If the Contractor does not supply the Drawings or manuals by the dates stated in the SCC, or they do not receive the Project Manager’s approval, the Project Manager shall withhold the amount stated in the SCC from payments due to the Contractor. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include the following - |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Programme and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is declared bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor does not maintain a Security, which is required; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgment of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under clause 61.2, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the grounds listed in clause 61.2, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the SCC. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure event or situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. - RELEASE FROM PERFORMANCE |
| If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

# SECTION 9A CONTRACT DATA

PARTICULAR CONDITIONS PART A – CONTRACT DATA

| Conditions | Sub-Clause | Data |
| --- | --- | --- |
| Employer’s name | - 1.1.31 | The Government of Malawi represented by Roads Authority |
| Engineer’s name | 1.1.35 | TBA |
| Section | 1.1.73 | N/A |
| Time for Completion | 1.1.84 | 730 days |
| Notices and other Communications | 1.3 (a) (ii) | Electronic transmission systems include email and file sharing web sites. Electronic transmission of documents shall be followed by a hard copy |
| Notices and other Communications | 1.3 (d) | The address for the Employer is: Chief Executive Officer Roads Authority of Malawi Private Bag B346 Lilongwe MALAWI Email: ra@ra.org.mw |
| Notices and other Communications | 1.3 (d) | The address for the Contractor is: ……………………………………….. ………………………………………... ………………………………………… |
| Law and Language | 1.4 | The Contract shall be governed by the Laws of Republic of Malawi. The ruling language of the contract shall be English. The Language for communication shall be English |
| Care and supply of documents | 1.8 | The additional paper copies shall be One (1). |
| Right of access to the Site | 2.1 | No later than the Commencement Date |
| Engineer’s Duties and Authority | 3.2 | The Engineer shall obtain the specific approval of the Employer before taking action under the following Clauses: a) Clause 5.1 Subcontractors b) Clause 8.5 Extension of Time for Completion c) Clause 8.9 Employer’s Suspension d) Clause 10.2: Taking Over Parts e) Clause 13.3: Variation Procedure f) Clause 20.1: Claims and Clause 20.2 Claims for Payment and/or EOT |
| Performance Security | 4.2 | The performance security will be in the form of a Bank Guarantee in the amount(s) of Ten (10) percent of the Accepted Contract Amount and in the same currency (ies) of the Accepted Contract Amount. |
| Sub-Contractors | 5.1 (a) | 30 percent |
| Normal working hours | 6.5 | Monday to Saturday 7:30am – 17:00 hours with exception of Gazetted Public Holidays at a maximum of 45 hours in a week. |
| Staff Removal | 6.9 | Insert after 6.9(f); (g) acts in a manner that breaches the Code of Conduct (ES) (e.g. sexual harassment, gender-based violence, illicit activity or crime).” |
| Commencement | 8.1 | ES Management Strategies and Implementation Plans The following is inserted at the end of 8.1: “Notwithstanding the Commencement Date as specified in this Sub-Clause, the Contractor shall not proceed implementing the works 28 days after the commencement date unless the Engineer is satisfied that appropriate measures are in place to address environmental and social risks and impacts. At a minimum, the Contractor shall apply the Management Strategies and Implementation Plans and Code of Conduct, submitted as part of the Bid and agreed as part of the Contract. The Contractor shall submit, on a continuing basis, for the Engineer’s prior approval, such supplementary Management Strategies and Implementation Plans as are necessary to manage the ES risks and impacts of ongoing works. These Management Strategies and Implementation Plans collectively comprise the Contractor’s Environmental and Social Management Plan (C-ESMP). The C-ESMP shall be approved prior to the commencement of construction activities (e.g. excavation, earth works, bridge and structure works, stream and road diversions, quarrying or extraction of materials, concrete batching and asphalt manufacture). The approved C-ESMP shall be reviewed, periodically (but not less than every six (6) months), and updated in a timely manner, as required, by the Contractor to ensure that it contains measures appropriate to the Works activities to be undertaken. The updated C-ESMP shall be subject to prior approval by the Engineer.” |
| Programme | 8.3(d) (iv) | Insert at end of GC 8.3(d)(iii): (iv) “In addition to the progress report, the Contractor shall also provide a report on the Environmental and Social (ES) metrics set out in Part C and D. In addition to Part C and D reports, the Contractor shall also provide immediate notification to the Engineer of incidents in the following categories. Full details of such incidents shall be provided to the Engineer within the timeframe agreed with the Project Manager. - confirmed or likely violation of any law or international agreement; - any fatality or serious (lost time) injury; - significant adverse effects or damage to private property (e.g. vehicle accident, damage from fly rock, working beyond the boundary) - major pollution of drinking water aquifer or damage or destruction of rare or endangered habitat (including protected areas) or species; or - any allegation of sexual harassment or sexual misbehavior, child abuse, defilement, or other violations involving children. |
| Delay damages for the Works | 8.8 & 14.15(c) | 0.05% of the Contract Price per day. |
| Maximum amount of delay damages | 8.8 | 5% of the final Contract Price. |
| Defects Notification Period | 11.3 | 365 days. |
| Provisional Sums | 13.4.(b)(ii) | A percentage for adjustment of Provisional Sums is 7.5 % |
| Adjustments for Changes in Cost | 13.7 | Not applicable. |
| Advance Payment | 14.2 | The total advance payment shall be 20% Percentage of the Accepted Contract Amount payable in the currencies and proportions in which the Accepted Contract Amount is payable, subject to acceptance of an Advance Payment Guarantee. |
| Percentage of Retention | 14.3 | 5% |
| Limit of Retention Money | 14.3 | 2.5% of the Accepted Contract Amount |
| Plant and Materials intended for the works | 14.5(b)(i) | If Sub-Clause 14.5 applies: Plant and Materials for payment when shipped. N/A. |
|  | 14.5(c)(i) | Plant and Materials for payment when delivered to the Site. - Bitumen - Steel |
| Minimum Amount of Interim Payment Certificates | 14.6.2 | 7 % of the Accepted Contract Amount (This requirement will be waived for the first 4 months from commencement of the contract). |
| Payment | 14.7 (a) | 42 days |
| Payment | 14.7 (b) (ii) | 42 days |
| Publishing source of commercial interest rates for financial charges in case of delayed payment | 14.8 | Prime Lending Rate of the Commercial Bank of Malawi + 1% or if not available the Inter Bank offered rate and shall be calculated at simple interest |
| Currencies of payment | 14.15 | The Contract Price shall be paid in Malawi Kwacha |
| Insurance to be provided by the Contractor | 19.2 | The permitted deductible limits shall be: - The minimum cover for insurance of equipment is MK450 million |
| Insurance to be provided by the Contractor | 19.2.3 (a) | 1.2 times the value of the Works |
| Insurance to be provided by the Contractor | 19.2.4 | - The minimum cover for insurance of property is: MK450 million - The minimum cover for personal injury or death insurance is MK300 million |
| Constitution of the DAAB | 21.1 | The DAAB shall comprise of one suitably qualified person. The sole member shall be selected from a list of qualified arbitrators from the Malawi Engineering Institution |
| Failure to appoint DAAB member(s) | 21.2 | The president of the Malawi Engineering Institution |

| Official Language | 4.1 | English |
| --- | --- | --- |
| Time for the Parties to sign a Contract Agreement |  | 30 days after receipt of the Letter of Acceptance |
| Total liability of the Contractor to the Procuring and Disposing entity under or in connection with the Contract | N/A |  |
| Site | 1.1 | [Describe any other places as forming part of the Site] |
| Conditions |  |  |
| Environmental and Social (ES) Performance Security |  | [ Ideally, the right of access to and possession of all parts of the Site shall be given by the Commencement Date. If this is the case, insert: “No later than the Commencement Date”] [If it is not practical or feasible to give the right of access to and possession of all parts of the Site by the Commencement Date, state the following and delete the remaining text in this Particular Conditions, clause 2.1: “ No later than the Commencement Date, except for the following parts (include detailed description of parts concerned): within such times as may be required to enable the Contractor to proceed in accordance with the Programme or, if there is no Programme at that time, the initial program submitted under clause 8.3 [Programme”]] |
| Maximum allowable accumulated value of work subcontracted (as a percentage of the Accepted Contract Amount) |  |  |
| Normal working hours |  | Monday to Saturday 7:30am – 17:00 hours with exception of Gazetted Public Holidays at a maximum of 45 hours in a week. |
| Time for access to the Site |  |  |
| Performance Security | 54.2 | The performance security will be in the form of a Bank Guarantee in the amount(s) of Ten (10) percent of the Accepted Contract Amount and in the same currency (ies) of the Accepted Contract Amount. |

| Conditions | Clause | Data |
| --- | --- | --- |
| The amount of insurance required for liability for breach of professional duty | 14 |  |
| Insurance required against liability for fitness for purpose | N/A | Yes/No [ delete as appropriate] |
| Period of insurance required for liability for breach of professional duty | 14 |  |
| Amount of insurance required for injury to persons and damage to property | 14.1. (C) |  |
| Other insurances required by Laws and by local practice (give details) | 14.3 |  |

# SECTION 9B. SPECIAL CONDITIONS OF CONTRACT

SECTION 9B. SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC Clause Reference | Special Conditions |
| --- | --- |
| GCC 1.1 | The Procuring and Disposing Entity is: Roads Authority The name and procurement reference number of the Contract is: Completion of Chitipa to ilomba Road The Works are: The Site is: Chitipa to Ilomba Road and is defined in Drawings Nos.: The Start Date shall be: TBA The Intended Completion Date for the whole of the Works shall be: 730 Days |
| GCC 1.4 | Law and Language Add the following new sub-paragraph: The Contractor shall keep himself informed of all the latest laws of Malawi, regulations and bylaws promulgated by the government or any other statutory authority, which may have relevance to the execution of the Contract. |
| GCC 1.5 | Delete the sequence of the documents presented in Clause GCC 1.5 in its entirety and replace with the following sequence: - the Agreement (if completed) - Minutes of Contract Negotiations (if any) - the Notice of Acceptance - the Letter of Tender - the Particular Conditions part A- Contract Data - the Particular Conditions part B- Special Provisions - these General Conditions - the Particular Specifications - the Standard Specifications (SATCC 1998, reprinted 2001) - the Drawings and - the priced Bill of Quantities - the completed Qualification Information Forms and any other documents forming part of the Contract. |
| GCC 2.1 | Right of Access to the Site Add the following after the first paragraph: For this Contract, the Employer shall, on the Commencement Date, give the Contractor right of access to the Site and possession of so much of the Site as may be required to enable the Contractor to commence and proceed with the construction of the Works. |
| GCC3.2 | Add the following to this Clause: The Engineer shall obtain the specific approval of the Employer before taking action under the following clauses - Clause GCC 5: Subcontracting - Clause GCC 8.5: Extension of time for Completion - Clause GCC 10: Employer’s Taking Over - Clauses GCC 13: Variations and adjustments - Clause GCC 20: Employer’s and Contractor’s Claims Notwithstanding the obligation as set out above to obtain approval, if in the opinion of the Engineer, an emergency occurs affecting the safety of life or of the works or of adjoining property, the Engineer may without relieving the Contractor of any of his duties and responsibilities under the Contract instruct the Contractor to execute all work or to do all things as may, in the opinion of the Engineer be necessary to abate or reduce the risk. The Contractor shall forthwith comply, despite the absence of the approval of the Employer, with any such instruction of the Engineer. The Engineer shall determine an addition to the contract price in respect of such instruction if and as may be relevant and shall notify the Contractor accordingly, with a copy to the Employer. |
| GCC 4.1 | The following is inserted after the paragraph “The Contractor shall, whenever required by the Engineer...”: “The Contractor shall not proceed with implementation of works 28 days after commencement unless the Engineer gives a Notice of No-objection to the Contractor, a Notice that shall not be unreasonably delayed, to the measures the Contractor proposes to manage the environmental and social risks and impacts, which at a minimum shall include applying the Management Strategies and Implementation Plans (MSIPs) and Code of Conduct for Contractor’s Personnel submitted as part of the Bid and agreed as part of the Contract. The Contractor shall submit, to the Engineer for Review and approval, any additional MSIPs as are necessary to manage the ES risks and impacts of ongoing Works (e.g. excavation, earth works, bridge and structure works, stream and road diversions, quarrying or extraction of materials, concrete batching and asphalt manufacture). These MSIPs collectively comprise the Contractor’s Environmental and Social Management Plan (C-ESMP). The Contractor shall review the C-ES, periodically (but not less than every six (6) months), and update it as required to ensure that it contains measures appropriate to the Works. The updated C-ESMP shall be submitted to the Engineer for Review The C-ESMP and the Contractor’s Code of Conduct shall be included as Contractor’s Documents. The procedures for Review of the C-ESMP and its updates shall be as described in Sub-Clause 4.4.1 [Preparation and Review].” |
| GCC 4.2.1 | Performance Security Delete wording of the first Paragraph and replace with the following: The Contractor shall deliver the Performance Security to the Employer within 28 days after receiving the Letter of Acceptance, and shall send a copy to the Engineer. The Performance Security shall be issued by a bank registered in the Republic of Malawi or licensed to do business in that country. The Performance Security shall be presented in accordance with the Form of Performance Security included in these Tender Documents. The Performance Security shall be in the form of a Bank Guarantee issued by: - A bank located in Malawi or - A foreign bank through a correspondent bank located in Malawi. The Performance Security for this Contract shall be ten percent (10%) of the accepted contract amount. |
| GCC 4.8 | Safety Procedures Add the following item: - Provide, install and maintain adequate personnel and measures to ensure the safety of road users during construction of the works. In particular, the site must be left in a safe, trafficable condition with adequate traffic control measures outside normal working hours. |
| GCC 4.10 | Use of Site Data Add the following at the end of the first Paragraph: The information issued by the Employer is for information only and shall neither form part of the Contract nor relieve the Contractor of his obligations under the Contract. |
| GCC 4.17 | Contractor’s Equipment Add the following at the end of the Paragraph: The Employer is not liable for compensation in regards to any construction equipment or material brought on the site which was not fully used during the construction and maintenance of the works, and the Employer cannot be held liable for the loss or damage of any of the said equipment or material brought on the site by the Contractor or which was used during the execution of this Contract. |
| GCC 4.18 | Protection of the Environment Add the following Paragraph at the end: The Contractor shall adhere at all times to the Environmental and Social Management Plan contained in the Particular Specifications. The Contractor will be held accountable for any costs arising from his negligence with regard to the environment. The Employer reserves the right to recover any such costs by deducting the relevant amount from interim payment certificates. |
| GCC 4.21 | Security of the Site Add to Clause 4.21 the following item: (c) The Contractor shall note that the site is a public road and therefore the public is entitled to the continued use of the road. Notwithstanding, the Contractor is still responsible for ensuring the safe passage of the public through the site and for preventing unauthorised entry to areas where work is in progress. |
| GCC 4.22 | Contractor’s Operations on Site Add the following after the first sentence of the first Paragraph: For the additional land required, the Contractor shall arrange with the owners or tenants the necessary rent and cost in connection therewith. The Contractor shall be responsible for all damage to such land and property and shall indemnify the Employer and hold him harmless in respect of all claims, demand proceedings, damage costs including attorney’s and client costs charges and expenses arising in respect thereof. The Contractor shall furnish the Engineer for his approval, copies of letters of consent from owners of additional land acquired. |
| ### Sub-Clause 4.24 Code of Conduct | Add the following sub-clause The Contractor shall have a Code of Conduct for the Contractor’s Personnel. The Contractor shall take all necessary measures to ensure that each Contractor’s Personnel is made aware of the Code of Conduct including specific behaviors that are prohibited, and understands the consequences of engaging in such prohibited behaviors. These measures include providing instructions and documentation that can be understood by the Contractor’s Personnel and seeking to obtain that person’s signature acknowledging receipt of such instructions and/or documentation, as appropriate. The Contractor shall also ensure that the Code of Conduct is visibly displayed in multiple locations on the Site and any other place where the Works will be carried out, as well as in areas outside the Site accessible to the local community and project affected people. The posted Code of Conduct shall be provided in languages comprehensible to Contractor’s Personnel, Employer’s Personnel and the local community. The Contractor’s Management Strategy and Implementation Plans shall include appropriate processes for the Contractor to verify compliance with these obligations. |
| GCC 5.1 | Subcontracting Add the following to Clause GCC 5.1: It is an explicit requirement of the Contract that thirty percent (30%) of the total value of the works, excluding escalation, contingencies, provisional sums and VAT, be subcontracted to Malawian Local Contractors. These Small to medium Size Malawian Business Enterprises are solely and wholly owned by one or more Malawians Persons and whose management and daily business operations are under the control of, and performed by one or more Malawian persons who effectively own and control it. They shall be functioning as the subcontractor to the main Contractor, which assigns Commercially Useful Work Item to be executed under a subcontract agreement to them. Commercially Useful Work is the performance of real and actual work or provision of the services, in the discharge of any contractual obligation which shall include but not be limited to the performance of a distinct element of the work, which the business has the skills and expertise to undertake, as well as the responsibility for managing and supervising that function. The Contractor shall prepare and attach to his payment certificates in a form provided by the Employer: - A brief report which describes the Commercially Useful Work Items performed by the Malawian Local Contractors in the execution of the Contract, both over the interim period and on cumulative basis; - A schedule reflecting the estimated total value of goods to be supplied and work and services to be performed, the cumulative value of goods supplied and/or performed, over the period for which the payment is claimed in respect of each and every Malawian Local Contractor. The acceptance of the Main Contractor bid shall not be construed as approval of all or any of the listed Malawian Local Contractors in Form 4.6 of the Bidding Forms (Section 4) Should any or all the Malawian Local Contractors not be approved as a Sub contractor subsequent to the acceptance of the Tender, this shall in no way invalidate this tender and tendered units rates for various items of works which shall remain final and binding even in the event of Malawian Local Contractor not approved by the Engineer. Should random inspection conducted by the Project Manager on the Main Contractor’s activities indicate that Main Contractor is not adhering to the requirements of this Specification; this may constitute sufficient grounds for cancellation of the contract depending on the seriousness of such non-conformance. The Contractor shall enter into a written Sub contract with each Specialist and Malawian Local Contractor and submit to the Project Manager and Employer details of all such Sub-Contract agreements which shall comply with all terms and conditions of this contract. |
| GCC 5.2 | Nominated Subcontractors Add the following new Sub-Clause: PCC 5.2.5 Employer’s assumption of subcontract If the Contract shall have been terminated in terms of Clause 15, the Employer shall have the right, by written notice given to any Nominated Subcontractor no later than 28 days after the said cancellation, to convert the subcontract concerned to a direct contract between the Employer and the Subcontractor provided that: (a) the terms of the said direct contract shall mutatis mutandis be those of the subcontract concerned and (b) The Employer shall have the right notwithstanding any breach of the subcontract by the Contractor subject to his forthwith paying to the Subcontractor all amounts then owing to the Subcontractor by the Contractor and perform any obligation, which the Contractor has failed to perform. |
| GCC 6 | Delegation of the following duties will require Clients’ approval The Engineer shall obtain the specific approval of the Employer before taking action under the following clauses (i) Clause GCC 5: Subcontracting (ii) Clause GCC 8.5: Extension of time for Completion (iii) Clause GCC 10: Employer’s Taking Over (iv) Clauses GCC 13: Variations and adjustments (v) Clause GCC 20: Employer’s and Contractor’s Claims Notwithstanding the obligation as set out above to obtain approval, if in the opinion of the Engineer, an emergency occurs affecting the safety of life or of the works or of adjoining property, the Engineer may without relieving the Contractor of any of his duties and responsibilities under the Contract instruct the Contractor to execute all work or to do all things as may, in the opinion of the Engineer be necessary to abate or reduce the risk. The Contractor shall forthwith comply, despite the absence of the approval of the Employer, with any such instruction of the Engineer. The Engineer shall determine an addition to the contract price in respect of such instruction if and as may be relevant and shall notify the Contractor accordingly, with a copy to the Employer. |
| GCC 6.1 | Engagement of staff and Labour Add the following at the end of the paragraph: The Contractor shall enter into written contract with all his personnel detailing their engagement terms and conditions. |
| GCC 6.6 | Facilities for Staff and Labour Add the following sentence at the end of the first Paragraph: The facilities in particular for housing and ablutions shall be decent with lockable doors and cubicles and shall have privacy and be acceptable to the Engineer. |
| ### Sub-Clause 6.9 Contractor’s Personnel | The Sub-Clause is replaced with: “The Contractor’s Personnel (including Key Personnel, if any) shall be appropriately qualified, skilled, experienced and competent in their respective trades or occupations. The Engineer may require the Contractor to remove (or cause to be removed) any person employed on the Site or Works, including the Contractor’s Representative and Key Personnel (if any), who: - persists in any misconduct or lack of care; - carries out duties incompetently or negligently; - fails to comply with any provision of the Contract; - persists in any conduct which is prejudicial to safety, health, or the protection of the environment; - based on reasonable evidence, is determined to have engaged in Fraud and Corruption during the execution of the Works; - has been recruited from the Employer’s Personnel in breach of Sub-Clause 6.3 [Recruitment of Persons]; - undertakes behaviour which breaches the Code of Conduct for Contractor’s Personnel (ES). If appropriate, the Contractor shall then promptly appoint (or cause to be appointed) a suitable replacement with equivalent skills and experience. In the case of replacement of the Contractor’s Representative, Sub-Clause 4.3 [Contractor’s Representative] shall apply. In the case of replacement of Key Personnel (if any), Sub-Clause 6.12 [Key Personnel] shall apply. Subject to the requirements in Sub-Clause 4.3 [Contractor’s Representative] and 6.12 [Key Personnel], and notwithstanding any requirement from the Engineer to remove or cause to remove any person, the Contractor shall take immediate action as appropriate in response to any violation of (a) through (g) above. Such immediate action shall include removing (or causing to be removed) from the Site or other places where the Works are being carried out, any Contractor’s Personnel who engages in (a), (b), (c), (d), (e) or (g) above or has been recruited as stated in (f) above.” |
| ### GCC 6.10 | Contractors Records Add the following to Sub-Clause 6.10: The information required by the Engineer in respect of the Contractor’s Personnel shall be submitted three working days before each monthly site meeting. The information required by the Engineer in respect of the Contractor's Equipment shall also be presented three working days before each monthly site meeting, and shall include details of plant availability, reasons for downtime, source of plant whether hired or owned, and manufacturer's ratings. |
| ### GCC 6.12 | Add the following to Sub-Clause 6.12 Foreign Personnel The Contractor may import any personnel who are necessary for the execution of the Works, provided that these personnel are in possession of the required residence visas and work permits. The Contractor shall be responsible for the return to the place where they were recruited or to their domicile of imported Contractor’s Personnel. In the event of the death in Malawi of any of these personnel or members of their families, the Contractor shall similarly be responsible for making the appropriate arrangements for their return or burial. No employee of the Contractor originating from any other country shall enter Malawian territory without a work and residence permit, which is obtainable from the Ministry of Home Affairs. The Contractor shall note that he is responsible for the procurement of work and residence permits for his staff. Ample time shall be allowed for the processing of the applications by the Ministry of Home Affairs. The Employer will not honour any claim resulting from the late issuance of work and residence permits. The legal spouse and children of the Contractor’s personnel shall not be entitled to employment themselves, unless the necessary work permits have been obtained from the relevant authorities |
| ### GCC 6.13 | Add the Following New sub clauses: Employment of Local Personnel It is an explicit Particular Condition of this contract that no unskilled labour may be employed on the works unless he or she is a Malawian citizen. It is a further condition that no skilled or semi-skilled non-Malawian person may be employed on the works unless the Contractor can prove that there is no suitable trained Malawian citizen available. Tenderers are required to specify the non-Malawian personnel they intend bringing to Malawi for the sole purpose of executing the works. This listing does not absolve the Contractor from compliance with Clause 6.12. Contractors shall further note that they must reinvestigate the availability of Malawian persons every six months, and if a suitable person is then available, he shall be employed in the place of the Non-Malawian person, who shall then leave the country. The Contractor is also required to employ at least 10% of his labour force from the female gender. Failure to comply with this clause may result in the contract being stopped until the contractor has fulfilled this requirement. The Employer will not honour claims resulting from the stoppage of the contract due to the contractor’s failure to comply with this clause. |
| ### GCC 6.14 | Funeral Arrangements The contractor shall make all necessary arrangements for the transport, to any place as required for burial, of any of his expatriate employees or members of families who may die in Malawi. The contractor shall also be responsible, to the extent required by the local regulations, for making any arrangements with regard to burial of any of his local employees who may die while engaged upon the works. |
| ### GCC 6.15 | Alcoholic Liquor and Drugs The Contractor shall not, otherwise than in accordance with the statuses, Ordinances and Government Regulations or Orders for the time being in force, import, sell, give, barter or otherwise dispose of any alcoholic liquor or drugs, or permit or suffer any such importance, gift, barter or disposal by his Sub-contractors, agents, staff and labour. |
| ### GCC 6.16 | Arms and Ammunition The Contractor shall not give, barter, or otherwise dispose of to any person or persons any arms or ammunition of any kind or permit or suffer the same as aforesaid. |
| ### GCC 6.17 | Festival and Religious Customs The Contractor shall, in all dealings with his staff and labour, have due regard to all recognized festivals, days of the rest and religious or other customs prevalent in the country of the Employer prior to submission of Tender, The Contractor is required to satisfy himself with the respective said holidays, customs and festivals. If unscheduled official events take place on designated project working days (e.g., special election days) for which the Contractor could not have known during Tender Stage, the Contractor is required to submit to the Employer for his for his approval ahead of the event taking place, with a copy to the Engineer, the official notifications, any proposed action to be undertaken and any resultant time or financial aspects. |
| ### GCC 6.18 | Epidemics In the event of any outbreak of illness of an epidemic nature, the Contractor, at his own cost, shall comply with and implement such regulations, orders and requirements as may be made by the Government, or the local medical or sanitary authorities, for the purpose of dealing with and overcoming the same. |
| ### GCC 6.19 | Books and Records The Contractor shall keep proper wages’ books and time sheets, showing the wages paid to and time worked by the workmen in and about the execution of the Contract. He shall be bound, whenever required, to furnish such wages books and time sheets for the inspection of the Engineer, the Government Agent, or the Employer. |
| ### GCC 6.20 | Evidence of Compliance The Contractor shall, from time to time, furnish to the Engineer any detailed information and evidence the Engineer may require in order to satisfy himself that the labour conditions of the contract have been complied with. |
| ### GCC 6.21 | Breach of Wages Any Contractor or Sub-Contractor who is found to be in breach of the wages enforced pursuant to Clause 6.2 shall cease to be approved as a Contractor or Sub-Contractor for any further public contracts. Should a claim be made to the Employer alleging the Contractor’s default in payment of wages of any workmen employed on the Contract and if complaints are brought to the notice of the Engineer and satisfactory proof thereof is furnished to the Engineer, the Engineer may, failing payment by the Contractor, arrange for the payment of such claim out of the monies due to the Contractor under the said Contract. |
| ### GCC 6.22 | Employment Records of Workers The Contractor shall keep complete and accurate records of the employment of labour at the site. The records shall include the names, ages, genders hours worked and wages paid to all workers. These records shall be summarised on a monthly basis and submitted to the Engineer, and these records shall be available for inspection by Auditors during normal working hours. These records shall be included in the details to be submitted by the Contractor under GC Clause 6.10 [Records of Contractor’s Personnel and Equipment]. |
| ### GCC 6.23 | Employment of Local Personnel It is an explicit Particular Condition of this contract that no unskilled labour may be employed on the works unless he or she is a Malawian citizen. It is a further condition that no skilled or semi-skilled non-Malawian person be employed on the works unless the Contractor can prove that there is no suitable trained Malawian citizen available. Tenderers are required to specify the non-Malawian personnel they intend bringing to Malawi for the sole purpose of executing the works. This listing does not absolve the Contractor from the compliance with Clause 6.12. Contractors shall further note that they must reinvestigate the availability of Malawian persons every six months, and if a suitable person is then available, he shall be employed in the place of the Non-Malawian person, who shall then leave the country. The contractor is also required to employ at least 10% of his labour force from the female gender. Failure to comply with this clause may result in the contract being stopped until the contractor has fulfilled this requirement. The Employer will not honour claims resulting from the stoppage of the contract due to the Contractor’s failure to comply with this clause. |
| ### GCC 7.7 | Ownership of Plant and Materials Add the following at the end of Clause 7.7: All Plant and Materials owned by the Contractor, or by any company in which the Contractor has a controlling interest, shall, when delivered on the Site for incorporation into the works, be deemed to be the property of the Employer. Provided always that the vesting of such property in the Employer shall not prejudice the right of the Contractor to the sole use of the said Contractor's Plant and Materials for the purpose of the Works nor shall it affect the Contractor's responsibility to operate and maintain the same under the provisions of the Contract. |
| ### GCC 7.9 | Overloading of Vehicles The Contractor shall implement sufficient measures on site to prevent overloading of construction vehicles. No vehicle on site shall be loaded more than the load for which the vehicles was designed or is licensed to carry, whichever is smaller. The Engineer shall have the right to instruct the Contractor to reduce loads on construction vehicles if in his opinion the vehicles damage any part of the asphalt road network. The Engineer shall also be entitled to check the weight to ensure that no vehicle was overloaded. A penalty in line with applicable penalties for overloading of Ministry of Transport and Public Works will be payable by the Contractor to the Employer for every incident of overloading. Such penalties will be deducted from payments due to the Contractor by the Employer. |
| GCC 8 | The Contractor shall not assign the contract without the approval of the Procuring and Disposing Entity: “The Contractor shall not proceed with implementation of works 28 days after commencement unless the Engineer gives a Notice of No-objection to the Contractor, a Notice that shall not be unreasonably delayed, to the measures the Contractor proposes to manage the environmental and social risks and impacts, which at a minimum shall include applying the Management Strategies and Implementation Plans (MSIPs) and Code of Conduct for Contractor’s Personnel submitted as part of the Bid and agreed as part of the Contract. The Contractor shall submit, to the Engineer for Review and approval, any additional MSIPs as are necessary to manage the ES risks and impacts of ongoing Works (e.g. excavation, earth works, bridge and structure works, stream and road diversions, quarrying or extraction of materials, concrete batching and asphalt manufacture). These MSIPs collectively comprise the Contractor’s Environmental and Social Management Plan (C-ESMP). The Contractor shall review the C-ES, periodically (but not less than every six (6) months), and update it as required to ensure that it contains measures appropriate to the Works. The updated C-ESMP shall be submitted to the Engineer for Review The C-ESMP and the Contractor’s Code of Conduct shall be included as Contractor’s Documents. |
| GCC 8.2 | Time for Completion Add the following sentence at the end: The time for completion of the works stated in PCC Part A (Contract Data) is inclusive of special non-working days and the normal construction industry holidays. |
| GCC 8.3 | Programme Add the following sub-item in item (d): (iii) The critical path and the planned production rates of all activities shall be clearly indicated on the programme, with due allowance being made for non-working periods, and periods where for any reason, for instance weather conditions, when production rates will be reduced. Add the following at the end of the clause. The Employer shall withhold 5% of Current Interim Payment Certificate amount for late submission of an updated Programme. |
| GCC 10.1 | Key personnel as indicated in the Qualification Information Form (paragraph 1.5 of this Form) is part of the Contract |
| GCC 12.3 | Valuation of the works Add the following Paragraph at the end of this Sub-Clause: If, on the issue of the Taking-Over Certificate for the whole of the Works, it is found that as a result of variations issued and all adjustments upon measurement of the estimated quantities set out in the Bill of Quantities, excluding Provisional Sums and price adjustments, there have been additions or deductions from the Accepted Contract Amount which taken together are in excess of fifteen (15) percent of the Accepted Contract Amount less Provisional Sums, Budget Amounts and Contingencies, then and in such event, after due consultation by the Engineer with the Employer and the Contractor, there shall be added to or deducted from the Contract Price ten (10) percent of the total amount of additions or deductions. |
| GCC 14.1 | The insurance cover and deductibles shall be: - The minimum cover for insurance of the works, plant and materials is: MWK 1 million (≤15 million contract amount); MWK 2.0 million (≥ 15 million contract amount); MWK 3.0 million (≥ 50 million contract amount); MWK 4.5.0 million (≥ 200 million contract amount); MWK 7.0 million (≥ 500 million contract amount); per occurrence with the number of occurrences unlimited. - The maximum deductible for insurance of the Works, Plant and Materials is: N/A - The minimum cover for insurance of equipment is MWK1.5 million (≤15 million contract amount); MWK 3.0 million (≥ 15 million contract amount); MWK 5.0 million (≥ 50 million contract amount); MWK 7.0 million (≥ 200 million contract amount); MWK 12.0 million (≥ 500 million contract amount); per occurrence with the number of occurrences unlimited. - The maximum deductible for insurance of equipment is: N/A - The minimum cover for insurance of property is MWK 1 million (≤15 million contract amount); MWK 1.5 million (≥ 15 million contract amount); MWK 3.0 million (≥ 50 million contract amount); MWK 4.5 million (≥ 200 million contract amount); MWK 6.5.0 million (≥ 500 million contract amount); - The maximum deductible for insurance of property is: N/A - The minimum cover for personal injury or death insurance is MWK5 million with no deductible. |
| GCC 14.3 | Application for Interim Payment Certificates Add the following at the end of the Clause: The estimated contract value of the Works executed during the month shall be agreed with the Engineer’s Representative on site prior to the preparation of the Statement. The quantities claimed for the various items shall be accurate and not simply guessed or based on a percentage of the scheduled quantity. |
| GCC 14.8 | Delayed Payment Calculation of Financing Charges for delayed payment shall be Prime Lending Rate of the Contractors Commercial Bank + 1% and shall be calculated at simple interest |
| GCC 15 | Site Investigation Report(s) shall not be part of the contract. |
| GCC 18.1 | Add the following to the list of exceptional events unforeseeable events not within the control of either party and which by the exercise of due diligence neither party is able to overcome. |
| GCC 22 | The Site Possession Date shall be: TBA |
| GCC 25.3 | The ES Performance Security will be in the amounts of 2% of the Contract Price and in the same currency(ies) |
| GCC 28.3 | Fees and reimbursable expenses to be paid to the Adjudicator are …………. |
| GCC 28.5 | The institution whose arbitration procedures shall be used is: Arbitration shall take place at: |
| GCC 28.5 | The Appointing Authority for the Adjudicator is: Malawi Engineering Institution |
| GCC 29.1 | The Contractor shall submit a revised Programme for the Works within 30 days of delivery of the Notice of Acceptance. |
| GCC 29.3 | The period between programme updates is: The amount to be withheld for late submission of an updated programme is …….% of current interim Payment Certificate amount |
| GCC 37.1 | The Defects Liability Period is: 12Months |
| GCC 39.1 | This contract is Admeasurement contract |
| GCC 46.1 | The following shall also be Compensation Events: |
| GCC 49.1 | The Contract subject to price adjustment and the following information regarding coefficients apply. The coefficients for adjustment of prices are: - For currency: - percent nonadjustable element (coefficient A). - percent adjustable element (coefficient B). - For currency: - percent nonadjustable element (coefficient A). - percent adjustable element (coefficient B). |
| GCC 49.3 | The Index I for Malawi Kwacha will be: The Index I for the specified international currency will be: The Index I for currencies other than Malawi Kwacha and the specified international currency will be: |
| GCC 50.1 | The proportion of payments retained is …...% from each interim Payment Certificate and the maximum amount retained shall be …...% of the accepted Contract Price |
| GCC 51.1 | The rate per day for liquidated damages is 0.01% of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is percent of the final Contract Price. |
| GCC 52 | The Bonus for the whole of the Works is ………… of the final Contract Price per day. The maximum amount of Bonus for the whole of the Works is …...% of the final Contract Price. |
| GCC 53.1 | The Advance Payment will be equivalent to 20% of the Contract Price and will be paid in the same currencies and proportions as the Contract Price. It will be paid to the Contractor no later than |
| GCC 53.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending………months after the Start Date. |
| GCC 54.1 | The Performance Security in the amount of 8% of the Contract Price is required |
| GCC 60.1 | The date by which operating and maintenance manuals are required is: The date by which “as built” drawings are required is: |
| GCC 60.2 | The amount to be withheld for failing to produce “as built” drawings and/or operating and maintenance manuals by the date required is: 5% |
| GCC 62.1 | The percentage to apply to the value of the work not completed upon termination, representing the Client’s additional cost for completing the Works, is: |

# SECTION 10. CONTRACT FORMS

SECTION 10. CONTRACT FORMS

AGREEMENT

PROCUREMENT REFERENCE NO:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Employer is desirous that the Contractor execute …………………….. (Hereinafter called the “Works”) and the Employer has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (Hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

- In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

- The documents forming the Contract shall be interpreted in the following order of priority -

    - Agreement (signed by both parties);

    - Minutes of Contract Negotiations;

    - Notification of Award;

    - Bid Submission Sheet(5);

    - Special Conditions of Contract;

    - General Conditions of Contract;

    - Specifications;

    - Drawings;

    - Priced Bill of Quantities; and

    - Any other documents listed in the Special Conditions of Contract as forming part of the Contract.

- In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

- The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

- The Contract Price or such other sum as may be payable shall be paid …. percent in Malawi Kwacha,  …. percent in ………….. and ….. percent in …………….                  .

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ………………………………. …in the capacity of ……………………………….

Signature………………………………

Witness  ………………………..Signature………………………………….

For and on behalf of the Contractor

Name ………………………………. ..	in the capacity of ……………………………….

Signature………………………………

Witness ……………………………Signature

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Financial Institution and should be signed by a person with the proper authority to sign documents that are binding on the Financial Institution.

PERFORMANCE BANK GUARANTEE

PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date: …………………………………………………………… [insert date]

Procurement Reference No.:………………………………………. [insert procurement reference number]

To: ………………………………………………………………………………………………………………… [name and address of Employer]

WHEREAS ……………………………………………………………………………………………………..[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No……………………… [number] dated ………………………………..[date] to execute ………………………………………………………………………………………….[name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognized bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758, except that subparagraph (ii) of Sub-article 20(a) is hereby excluded.

Signature and seal of the Guarantor:

Name of Financial Institution:

Address:

Date:

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Financial Institution.

ADVANCE PAYMENT SECURITY

Date:………………………………………………………………………………………………….. [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………………………………. [insert Procurement Reference number]

To: ………………………………………………………..	[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ………………………………………………………………………………………[insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of……………………………………………………… [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said clause of the Contract, in the amount of…………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned…………………………………………………………………… [insert complete name of Guarantor], legally domiciled in ………………………………………………………………………………………….[insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding…………………………………………………………………………………………. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until…………………………………………… [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name:……………………………………………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of……………………………………………………………………………………….. [insert legal capacity of person signing the Security]

Signed:…………………………………………………………………………………………………………. [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: [insert complete name of the Bank]

Dated on ____________ day of __________________, _______ [insert date of signing]

ENVIRONMENTAL AND SOCIAL (ES) PERFORMANCE SECURITY

[The Environmental and Social Performance Security should be on the letterhead of the issuing Financial Institution and should be signed by a person with the proper authority to sign documents that are binding on the Financial Institution. The draft is for an unconditional Security. The amount of the guarantee must represent the percentage of the Contract Price specified in the Contract, and should be denominated either in the currency(ies) of the Contract or in a freely convertible currency acceptable to the Procuring and Disposing Entity].

Date: …………………………………………………………………………………………………………………………………… [insert date (as day, month and year) of ES Performance Security]

Procurement Reference No:……………………………………………………………………………………. [insert Procurement Reference Number]

To: ……………………………………………………………………………………………………………………[insert complete name and address of Procuring and Disposing Entity]

WHEREAS ………………………………………………………………………………………………. [insert name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, pursuant to the Contract referenced above, dated……………………………………………………………………………………………… [insert date (as day, month and year) of contract] to execute ………………………………………………………………………………….. [insert brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by Client in the aforementioned Contract that the Provider shall furnish the Client with a demand guarantee issued by a financial institution for the sum specified therein as security for compliance with the Provider’s performance obligations in accordance with the Contract;

AND WHEREAS the undersigned ……………………………………………………………………………………………………. [insert complete name of Guarantor], legally domiciled in ……………………………………………………………….. [insert complete address of Guarantor], (hereinafter the “Guarantor”}, have agreed to give the Contractor a security;

THEREFORE WE hereby affirm that we are Guarantors and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………………………………………………. [insert currency and amount of Guarantee in words and figures], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand declaring the Contractor to be in default under the Contract, without cavil or argument, any sum or sums within the limits of …………………………………………………………………………………………………………………………………………………….[insert currency and amount of Guarantee in words and figures] as aforesaid without your needing to prove or to show grounds or reasons for your demand or the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall remain in force up to and including _________________ [insert date: day, month, year]

This guarantee is subject to the Uniform Rules for Demand Guarantees ICC Publication No. 458, except that sub - article 20(a) is hereby excluded.

Name: [insert complete name of person signing the Performance Security]

In the capacity of [insert legal capacity of person signing the Performance Security]

Signed: [signature of person whose name and capacity are shown above]

Duly authorised to sign the Performance Security for and on behalf of: [insert complete name of Financial Institution]

Dated on _______ day of __________________, _______ [insert date of signing]

SITE ORGANIZATION AND METHOD PLAN

The Bidder shall—

- provide a comprehensive Method Statement, with drawings where applicable, showing the methods proposed by the Bidder for carrying out the Works, including—

- proposed location of main office on the site, workshops, stations (steel/concrete/asphalt structures), warehouses, laboratories, accommodation, etc. (sketches to be attached as required);

- site organization;

- the method including the number of equipment, labour and materials to be used for carrying out each major category of Works;;

- the logical sequence and correlation between the major categories of activities of the Works;

- traffic measures during the Works; and

- provide details of the temporary and permanent Works to be constructed, taking into account the prevailing climatic conditions and the requirement to obtain various permits and approvals and that the existing system must remain functioning during construction.

As a minimum, the Method Statement shall include the following content:

- Location of Sites (e.g., site offices, stocks, warehouses);

- Project Organisation (e.g., Project Management, Elaboration of Shop Drawings, Material Procurement);

- Method for Removal of existing Surfaces and their Reinstatement;

- Method for Earthworks;

- Method for pipe installation;

- Method for Demolition Works, incl. separation into and handling of hazardous waste, residue and recyclable material;

- Method for Concrete Works;

- Method for Block Works;

- Method for Electrical Works;;

- Health and Safety Plan; and

- Environmental and Social Management Plan.

MOBILIZATION AND CONSTRUCTION SCHEDULE

The Contractor shall not carry out mobilization to Site unless the Contract Manager gives consent that appropriate measures are in place to address environmental and social   risks and impacts, which as a minimum shall include applying the Management Strategies and Implementation Plans (MSIPs) and Code of Conduct for Contractor’s Personnel, submitted as part of the Bid and agreed as part of the Contract.

- Attach a Graphic Work Schedule (critical milestone bar chart) for mobilisation, preparation of designs and drawings (Shop Drawings), ordering, manufacturing and delivery of equipment and material, construction, detailing the relevant activities, dates, allocation of labour and plant resources, etc. The planned input of the joint venture members and sub-Contractors shall be highlighted as well (in terms of activities undertaken, timing, etc.).

ESHS Management Strategies and Implementation Plans

- The Bidder shall submit comprehensive and concise Environmental, Social, Health and Safety Management Strategies and Implementation Plans (ESHS-MSIP) as required by clause 38 of the ITB. These strategies and plans shall describe in detail the actions, materials, equipment, management processes etc. that will be implemented by the Contractor, and its subcontractors.

- In developing these strategies and plans, the Bidder shall have regard to the ESHS provisions of the contract including those as may be more fully described in the following:

- [THE WORKS REQUIREMENTS DESCRIBED IN SECTION 7];

- [ENVIRONMENTAL AND SOCIAL MANAGEMENT PLAN (ESMP)]

CODE OF CONDUCT: ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY (ESHS)

The Bidder shall submit the signed Code of Conduct that will apply to the Contractor’s employees and subcontractors as required by ITB 38 of the Bid Data Sheet. The Code of Conduct shall ensure compliance with the ESHS provisions of the contract, including those as may be more fully described in the following____

- [the Works Requirements described in Section 7];

- [Environmental and Social Management Plan (ESMP)];

In addition, the Bidder shall submit an outline of how this Code of Conduct will be implemented. This will include: how it will be introduced into conditions of employment/engagement, what training will be provided, how it will be monitored and how the Contractor proposes to deal with any breaches.

CODE OF CONDUCT FOR CONTRACTOR’S PERSONNEL

Note to the Bidder:

The minimum content of the Code of Conduct form as set out by the Client shall not be substantially modified. However, the Bidder may add requirements as appropriate, including to take into account Contract-specific issues/risks.

The Bidder shall initial and submit the Code of Conduct form in support of its Bid.

We, being the Contractor, [enter name of Contractor]. have signed a contract with [enter name of Client] for [enter description of the Works]. These Works will be carried out at [enter the Site and other locations where the Works will be carried out]. Our contract requires us to implement measures to address environmental and social risks related to the Works, including the risks of sexual exploitation and assault and gender-based violence.

This Code of Conduct is part of our measures to deal with environmental and social risks related to the Works. It applies to all our staff, labourers and other employees at the Works Site or other places where the Works are being carried out. It also applies to the personnel of each subcontractor and any other personnel assisting us in the execution of the Works. All such persons are referred to as “Contractor’s Personnel” and are subject to this Code of Conduct.

This Code of Conduct identifies the behaviour that we require from all Contractor’s Personnel.

Our workplace is an environment where unsafe, offensive, abusive or violent behaviour will not be tolerated and where all persons should feel comfortable raising issues or concerns without fear of retaliation.

REQUIRED CONDUCT

Contractor’s Personnel shall –

- carry out his duties competently and diligently;

- comply with this Code of Conduct and all applicable laws, regulations and other requirements, including requirements to protect the health, safety and well-being of other Contractor’s Personnel and any other person;

- maintain a safe working environment by -

  - ensuring that workplaces, machinery, equipment and processes under each person’s control are safe and without risk to health;

  - wearing required personal protective equipment;

  - using appropriate measures relating to chemical, physical and biological substances and agents; and

  - following applicable emergency operating procedures.

- report work situations that he believes are not safe or healthy and remove himself from a work situation which he  reasonably believes presents an imminent and serious danger to his life or health;

- treat other people with respect, and not discriminate against specific groups such as women, people with disabilities, migrant workers or children;

- not engage in any form of sexual harassment including unwelcome sexual advances, requests for sexual favours, and other unwanted verbal or physical conduct of a sexual nature with other Contractor’s or Client’s Personnel;

- not engage in Sexual Exploitation, which means any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another.  In Bank financed projects, sexual exploitation occurs when access to or benefit from Bank financed Goods, Works, Consulting or Non-consulting services is used to extract sexual gain;

- not engage in Sexual Assault, which means sexual activity with another person who does not consent. It is a violation of bodily integrity and sexual autonomy and is broader than narrower conceptions of “rape”, especially because (a) it may be committed by other means than force or violence, and (b) it does not necessarily entail penetration.;

- not engage in any form of sexual activity with individuals under the age of 18, except in case of pre-existing marriage;

- complete relevant training courses that will be provided related to the environmental and social aspects of the Contract, including on health and safety matters, and Sexual Exploitation and Assault (SEA);

- report violations of this Code of Conduct; and

- not retaliate against any person who reports violations of this Code of Conduct, whether to us or the Employer, or who makes use of the [Project Grievance [Redress] Mechanism].

RAISING CONCERNS

If any person observes behaviour that he believes may represent a violation of this Code of Conduct, or that otherwise concerns him/her, he/she should raise the issue promptly. This can be done in either of the following ways:

- Contact [enter name of the Contractor’s Social Expert with relevant experience in handling gender-based violence, or if such person is not required under the Contract, another individual designated by the Contractor to handle these matters] in writing at this address [   ] or by telephone at [   ] or in person at [   ]; or

- Call [  ]  to reach the Contractor’s hotline (if any) and leave a message.

The person’s identity will be kept confidential, unless reporting of allegations is mandated by the country law. Anonymous complaints or allegations may also be submitted and will be given all due and appropriate consideration. We take seriously all reports of possible misconduct and will investigate and take appropriate action. We will provide warm referrals to service providers that may help support the person who experienced the alleged incident, as appropriate.

There will be no retaliation against any person who raises a concern in good faith about any behaviour prohibited by this Code of Conduct.  Such retaliation would be a violation of this Code of Conduct.

CONSEQUENCES OF VIOLATING THE CODE OF CONDUCT

Any violation of this Code of Conduct by Contractor’s Personnel may result in serious consequences, up to and including termination and possible referral to legal authorities.

FOR CONTRACTOR’S PERSONNEL:

I have received a copy of this Code of Conduct written in a language that I comprehend.  I understand that if I have any questions about this Code of Conduct, I can contact [enter name of Contractor’s contact person with relevant experience in handling gender-based violence] requesting an explanation.

Signed: ……………………………………………………………………………………………………………

………………………………………………..….[insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………… [insert legal capacity of person signing the Bid]

Name: ………………………………………………………………………………………………..[insert complete name of person signing the Bid]

Duly authorised to sign the Bid for and on behalf of: …………………………………………………………………..………………………….[insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

ATTACHMENT 1 TO THE CODE OF CONDUCT FORM

BEHAVIORS CONSTITUTING SEXUAL EXPLOITATION AND ABUSE (SEA) AND BEHAVIORS CONSTITUTING SEXUAL HARASSMENT (SH)

The following non-exhaustive list is intended to illustrate types of prohibited behaviours:

- EXAMPLES OF SEXUAL EXPLOITATION AND ABUSE INCLUDE -

- A Contractor’s Personnel tells a member of the community that he/she can get them jobs related to the work site (e.g. cooking and cleaning) in exchange for sex.

- A Contractor’s Personnel that is connecting electricity input to households says that he can connect women headed households to the grid in exchange for sex.

- A Contractor’s Personnel rapes, or otherwise sexually assaults a member of the community.

- A Contractor’s Personnel denies a person access to the Site unless he/she performs a sexual favour.

- A Contractor’s Personnel tells a person applying for employment under the Contract that he/she will only hire him/her if he/she has sex with him/her.

- EXAMPLES OF SEXUAL HARASSMENT IN A WORK CONTEXT

- Contractor’s Personnel comment on the appearance of another Contractor’s Personnel (either positive or negative) and sexual desirability.

- When a Contractor’s Personnel complains about comments made by another Contractor’s Personnel on his/her appearance, the other Contractor’s Personnel comment that he/she is “asking for it” because of how he/she dresses.

- Unwelcome touching of a Contractor’s or Employer’s Personnel by another Contractor’s Personnel.

- A Contractor’s Personnel tells another Contractor’s Personnel that he/she will get him/her a salary raise, or promotion if he/she sends him/her naked photographs of himself/herself.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.