GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Nachitipa Stream - Navikweta Stream along M026 Road in Chitipa District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-027 RA/MAI/2025-26/T/SGR/NR/CP/27 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Nachitipa Stream - Navikweta Stream along M026 Road in Chitipa District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/CP/27 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/CP/27

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Nachitipa Stream - Navikweta Stream along M026 Road in Chitipa District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Nachitipa Stream - Navikweta Stream along M026 Road in Chitipa District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/CP/27 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Nachitipa Stream - Navikweta Stream along M026 Road in Chitipa District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Navikweta Stream - Lufilya Bridge along M026 Road in Chitipa District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-028 RA/MAI/2025-26/T/SGR/NR/CP/28 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Navikweta Stream - Lufilya Bridge along M026 Road in Chitipa District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/CP/28 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/CP/28

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Navikweta Stream - Lufilya Bridge along M026 Road  in Chitipa District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Navikweta Stream - Lufilya Bridge along M026 Road in Chitipa District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/CP/28 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Navikweta Stream - Lufilya Bridge along M026 Road in Chitipa District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Lufilya Bridge - Mwapu Bridge along M026 Road in Karonga District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-029 RA/MAI/2025-26/T/SGR/NR/KA/29 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Lufilya Bridge - Mwapu Bridge along M026 Road in Karonga District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/KA/29 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/KA/29

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from  Lufilya Bridge - Mwapu Bridge along M026 Road in Karonga District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Lufilya Bridge - Mwapu Bridge along M026 Road in Karonga District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/KA/29 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Lufilya Bridge - Mwapu Bridge along M026 Road in Karonga District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Mwapu Bridge - Karonga (Junction to Stadium) along M026 Road in Karonga District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-030 RA/MAI/2025-26/T/SGR/NR/KA/30 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Mwapu Bridge - Karonga (Junction to Stadium) along M026 Road in Karonga District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/KA/30 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/KA/30

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Mwapu Bridge - Karonga (Junction to Stadium) along M026 Road in Karonga District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Mwapu Bridge - Karonga (Junction to Stadium) along M026 Road in Karonga District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/KA/30 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Mwapu Bridge - Karonga (Junction to Stadium) along M026 Road in Karonga District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Songwe Border - Kaporo (Pusi) along M001 Road in Karonga District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-031 RA/MAI/2025-26/T/SGR/NR/KA/31 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Songwe Border - Kaporo (Pusi) along M001 Road in Karonga District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/KA/31 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/KA/31

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Songwe Border - Kaporo (Pusi) along  M001 Road in Karonga District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Songwe Border - Kaporo (Pusi) along M001 Road in Karonga District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/KA/31 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Songwe Border - Kaporo (Pusi) along M001 Road in Karonga District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Kaporo (Pusi) - Karonga (Junction to Mwanjabala) along M001 Road in Karonga District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-032 RA/MAI/2025-26/T/SGR/NR/KA/32 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Kaporo (Pusi) - Karonga (Junction to Mwanjabala) along M001 Road in Karonga District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/KA/32 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/KA/32

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Kaporo (Pusi) - Karonga (Junction to Mwanjabala) along  M001 Road in Karonga District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Kaporo (Pusi) - Karonga (Junction to Mwanjabala) along M001 Road in Karonga District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/KA/32 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Kaporo (Pusi) - Karonga (Junction to Mwanjabala) along M001 Road in Karonga District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Ipyana Bridge - Kasimba Bridge along M001 Road in Karonga District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-033 RA/MAI/2025-26/T/SGR/NR/KA/33 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Ipyana Bridge - Kasimba Bridge along M001 Road in Karonga District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/KA/33 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/KA/33

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Ipyana Bridge - Kasimba Bridge along  M001 Road in Karonga District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Ipyana Bridge - Kasimba Bridge along M001 Road in Karonga District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/KA/33 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Ipyana Bridge - Kasimba Bridge along M001 Road in Karonga District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Kasimba Bridge - Nyungwe Bridge along M001 Road in Karonga District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-034 RA/MAI/2025-26/T/SGR/NR/KA/34 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Kasimba Bridge - Nyungwe Bridge along M001 Road in Karonga District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/KA/34 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/KA/34

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Kasimba Bridge - Nyungwe Bridge along M001 Road in Karonga District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Kasimba Bridge - Nyungwe Bridge along M001 Road in Karonga District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/KA/34 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Kasimba Bridge - Nyungwe Bridge along M001 Road in Karonga District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Nyungwe Bridge - Chilumba Jetty Junction along M001 Road in Karonga District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-035 RA/MAI/2025-26/T/SGR/NR/KA/35 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Nyungwe Bridge - Chilumba Jetty Junction along M001 Road in Karonga District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/KA/35 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/KA/35

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Nyungwe Bridge - Chilumba Jetty Junction along M001 Road in Karonga District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Nyungwe Bridge - Chilumba Jetty Junction along M001 Road in Karonga District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/KA/35 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Nyungwe Bridge - Chilumba Jetty Junction along M001 Road in Karonga District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Chilumba Jetty - Chitimba Bridge along M1 and S102 Roads in Karonga District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-036 RA/MAI/2025-26/T/SGR/NR/KA/36 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Chilumba Jetty - Chitimba Bridge along M1 and S102 Roads in Karonga District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/KA/36 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/KA/36

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Chilumba Jetty  - Chitimba Bridge along M1 and S102 Roads in Karonga District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Chilumba Jetty - Chitimba Bridge along M1 and S102 Roads in Karonga District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/KA/36 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Chilumba Jetty - Chitimba Bridge along M1 and S102 Roads in Karonga District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Chitimba Bridge - Chiweta (M001); and Bwengu to Chikwawa (M024) Roads in Rumphi District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-037 RA/MAI/2025-26/T/SGR/NR/RU/37 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Chitimba Bridge - Chiweta (M001); and Bwengu to Chikwawa (M024) Roads in Rumphi District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/RU/37 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/RU/37

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Chitimba Bridge - Chiweta (M001); and Bwengu to Chikwawa (M024) Roads in Rumphi District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Chitimba Bridge - Chiweta (M001); and Bwengu to Chikwawa (M024) Roads in Rumphi District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/RU/37 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Chitimba Bridge - Chiweta (M001); and Bwengu to Chikwawa (M024) Roads in Rumphi District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Phwezi - Phwamphwa - Lura on T305 and T306 Roads in Rumphi District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-038 RA/MAI/2025-26/T/SGR/NR/RU/38 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Phwezi - Phwamphwa - Lura on T305 and T306 Roads in Rumphi District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/RU/38 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/RU/38

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Phwezi - Phwamphwa - Lura on T305 and T306 Roads in Rumphi District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Phwezi - Phwamphwa - Lura on T305 and T306 Roads in Rumphi District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/RU/38 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Phwezi - Phwamphwa - Lura on T305 and T306 Roads in Rumphi District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Lura - Hananiya - Livingstonia on T305 and S103 Roads in Rumphi District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-039 RA/MAI/2025-26/T/SGR/NR/RU/39 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Lura - Hananiya - Livingstonia on T305 and S103 Roads in Rumphi District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/RU/39 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/RU/39

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Lura - Hananiya - Livingstonia on T305 and S103 Roads in Rumphi District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Lura - Hananiya - Livingstonia on T305 and S103 Roads in Rumphi District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/RU/39 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Lura - Hananiya - Livingstonia on T305 and S103 Roads in Rumphi District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Kacheche Junction - Lukonkhowe Bridge and Kacheche Junction - Kacheche on M1 and T308 Roads in Mzimba District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-040 RA/MAI/2025-26/T/SGR/NR/MZ/40 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Kacheche Junction - Lukonkhowe Bridge and Kacheche Junction - Kacheche on M1 and T308 Roads in Mzimba District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/MZ/40 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/MZ/40

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Kacheche Junction - Lukonkhowe Bridge and Kacheche Junction - Kacheche on M1 and T308 Roads in Mzimba District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Kacheche Junction - Lukonkhowe Bridge and Kacheche Junction - Kacheche on M1 and T308 Roads in Mzimba District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/MZ/40 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Kacheche Junction - Lukonkhowe Bridge and Kacheche Junction - Kacheche on M1 and T308 Roads in Mzimba District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Lukonkhowe Bridge - Kaka Motel on M001 Road in Mzimba District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-041 RA/MAI/2025-26/T/SGR/NR/MZ/41 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Lukonkhowe Bridge - Kaka Motel on M001 Road in Mzimba District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/MZ/41 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/MZ/41

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Lukonkhowe Bridge - Kaka Motel on M001 Road in Mzimba District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Lukonkhowe Bridge - Kaka Motel on M001 Road in Mzimba District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/MZ/41 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Lukonkhowe Bridge - Kaka Motel on M001 Road in Mzimba District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Ekwendeni - Ezondweni on S107 and T308 Roads in Mzimba District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-042 RA/MAI/2025-26/T/SGR/NR/MZ/42 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Ekwendeni - Ezondweni on S107 and T308 Roads in Mzimba District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/MZ/42 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/MZ/42

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Ekwendeni - Ezondweni on S107 and T308 Roads in Mzimba District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Ekwendeni - Ezondweni on S107 and T308 Roads in Mzimba District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/MZ/42 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Ekwendeni - Ezondweni on S107 and T308 Roads in Mzimba District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Geisha (Mzuzu) - Lwafwa on M001 Road in Mzimba District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-043 RA/MAI/2025-26/T/SGR/NR/MZ/43 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Geisha (Mzuzu) - Lwafwa on M001 Road in Mzimba District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/MZ/43 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/MZ/43

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Geisha (Mzuzu) - Lwafwa on M001 Road in Mzimba District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Geisha (Mzuzu) - Lwafwa on M001 Road in Mzimba District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/MZ/43 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Geisha (Mzuzu) - Lwafwa on M001 Road in Mzimba District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Lwafwa - Champhoyo on M001 Road in Mzimba District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-044 RA/MAI/2025-26/T/SGR/NR/MZ/44 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Lwafwa - Champhoyo on M001 Road in Mzimba District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/MZ/44 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/MZ/44

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Lwafwa - Champhoyo on M001 Road in Mzimba District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Lwafwa - Champhoyo on M001 Road in Mzimba District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/MZ/44 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Lwafwa - Champhoyo on M001 Road in Mzimba District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Champhoyo - Mzimba Bridge on M001 Road in Mzimba District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-045 RA/MAI/2025-26/T/SGR/NR/MZ/45 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Champhoyo - Mzimba Bridge on M001 Road in Mzimba District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/MZ/45 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/MZ/45

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Champhoyo - Mzimba Bridge on M001 Road in Mzimba District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Champhoyo - Mzimba Bridge on M001 Road in Mzimba District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/MZ/45 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Champhoyo - Mzimba Bridge on M001 Road in Mzimba District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Mzimba Bridge - Mzimba T/Off - Mzimba Police and Mzimba Police - Mtangatanga on M001, M009 and M022 Roads in Mzimba District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-046 RA/MAI/2025-26/T/SGR/NR/MZ/46 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Mzimba Bridge - Mzimba T/Off - Mzimba Police and Mzimba Police - Mtangatanga on M001, M009 and M022 Roads in Mzimba District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/MZ/46 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/MZ/46

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Mzimba Bridge - Mzimba T/Off - Mzimba Police  and Mzimba Police - Mtangatanga on M001, M009 and M022 Roads in Mzimba District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Mzimba Bridge - Mzimba T/Off - Mzimba Police and Mzimba Police - Mtangatanga on M001, M009 and M022 Roads in Mzimba District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/MZ/46 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Mzimba Bridge - Mzimba T/Off - Mzimba Police and Mzimba Police - Mtangatanga on M001, M009 and M022 Roads in Mzimba District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Jenda T.C. - Embangweni on S112 Road in Mzimba District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-047 RA/MAI/2025-26/T/SGR/NR/MZ/47 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Jenda T.C. - Embangweni on S112 Road in Mzimba District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/MZ/47 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/MZ/47

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Jenda T.C.  - Embangweni on S112 Road  in Mzimba District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Jenda T.C. - Embangweni on S112 Road in Mzimba District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/MZ/47 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Jenda T.C. - Embangweni on S112 Road in Mzimba District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Mzuzu State Lodge Junction - Kawalazi T/Off on M005 Road in Nkhata Bay District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-048 RA/MAI/2025-26/T/SGR/NR/NB/48 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Mzuzu State Lodge Junction - Kawalazi T/Off on M005 Road in Nkhata Bay District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/NB/48 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/NB/48

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Mzuzu State Lodge Junction -  Kawalazi T/Off on M005 Road in Nkhata Bay District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Mzuzu State Lodge Junction - Kawalazi T/Off on M005 Road in Nkhata Bay District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/NB/48 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Mzuzu State Lodge Junction - Kawalazi T/Off on M005 Road in Nkhata Bay District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Kawalazi T/Off - Mukwiya - Nkhata Bay Boma on M005 and T308 Roads in Nkhata Bay District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-049 RA/MAI/2025-26/T/SGR/NR/NB/49 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Kawalazi T/Off - Mukwiya - Nkhata Bay Boma on M005 and T308 Roads in Nkhata Bay District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/NB/49 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/NB/49

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Kawalazi T/Off - Mukwiya - Nkhata Bay Boma on M005 and T308 Roads in Nkhata Bay District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Kawalazi T/Off - Mukwiya - Nkhata Bay Boma on M005 and T308 Roads in Nkhata Bay District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/NB/49 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Kawalazi T/Off - Mukwiya - Nkhata Bay Boma on M005 and T308 Roads in Nkhata Bay District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Mukwiya - Luweya Bridge on M005 Road in Nkhata Bay District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-050 RA/MAI/2025-26/T/SGR/NR/NB/50 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Mukwiya - Luweya Bridge on M005 Road in Nkhata Bay District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/NB/50 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/NB/50

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Mukwiya - Luweya Bridge on M005 Road in Nkhata Bay District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Mukwiya - Luweya Bridge on M005 Road in Nkhata Bay District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/NB/50 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Mukwiya - Luweya Bridge on M005 Road in Nkhata Bay District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Luweya Bridge - Lifupa Bridge on M005 Road in Nkhata Bay District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-051 RA/MAI/2025-26/T/SGR/NR/NB/51 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Luweya Bridge - Lifupa Bridge on M005 Road in Nkhata Bay District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/NB/51 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/NB/51

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Luweya Bridge - Lifupa Bridge on M005 Road in Nkhata Bay District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Luweya Bridge - Lifupa Bridge on M005 Road in Nkhata Bay District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/NB/51 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Luweya Bridge - Lifupa Bridge on M005 Road in Nkhata Bay District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

GOVERNMENT OF THE REPUBLIC OF MALAWI

Accelerating Malawi’s Economic Growth

Roads Authority

BIDDING DOCUMENT FOR THE

PROCUREMENT OF MINOR WORKS

| Subject of Procurement | Shrub and Grass Cutting from Lifupa Bridge - Dwambazi Bridge on M005 Road in Nkhata Bay District |
| --- | --- |
| Project ID No.: Procurement Reference Number | MAI-2-NR-052 RA/MAI/2025-26/T/SGR/NR/NB/52 |
| Procurement Method | Open Tendering |
| Date of Issue: | 22nd June 2026 |

TABLE OF CONTENTS

PART 1	-	BIDDING PROCEDURES

Section 1 – Instructions to Bidders

Section 2 – Bid Data Sheet

Section 3 – Evaluation and Qualification and Criteria

Section 4 – Bidding Forms

Section 5 – Eligible Countries

Section 6 – Corruption and Fraud

PART 2	-	SCHEDULE OF REQUIREMENTS

Section 7(A) – Scope of Works

Section 7(B) – Technical Specifications

Section 7(C) – Drawings

Section 7(D) – Bills of Quantities (or Activity Schedule)

PART 3	-	CONTRACT

Section 8 – General Conditions of Contract

Section 9 – Special Conditions of Contract

Section 10 – Contract Forms

SECTION 1: INSTRUCTIONS TO BIDDERS TABLE OF CONTENTS - Scope of Bid 4 - Eligible Bidders 4 - Documents Comprising the Bid 4 - Bid Prices 4 - Currencies of Bid and Payment 5 - Bid Validity 5 - Bid Security or Bid Securing Declaration 5 - Format and Signing of Bid 5 - Sealing and Marking of Bids 5 - Deadline for Submission of Bids 6 - Late Bids 6 - Bid Opening and Evaluation 6 - Correction of Errors 6 - Domestic Preference and Participation of Micro, Small and Medium Enterprises 6 - Award Criteria 7 - Procuring and Disposing Entity’s Right to Accept a Bid and to Reject any or all Bids 7 - Notification of Award and Signing of Agreement 7 - Performance Security 7 - Adjudicator 7 - Corrupt or Fraudulent Practices 7

| - SCOPE OF BID |
| --- |
| - The Procuring and Disposing Entity indicated in the Bid Data Sheet (BDS), invites bids for the construction of Works, as described in Section 7, Schedule of Requirements. The subject and procurement reference number are provided in the Bid Data Sheet. - The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Bid Data Sheet. |
| - ELIGIBLE BIDDERS |  |
| - A Bidder shall— - have the legal capacity to enter into a contract; - not be insolvent, in receivership, bankrupt or being wound up, not have had their business activities suspended and not be the subject of legal proceedings for any of the foregoing; and - have fulfilled all obligations to pay taxes according to the tax laws of Malawi. - To demonstrate compliance with the criteria a Bidder shall submit with its Bid copies of— - its certificate of Contractor Registration from the National Construction Industry Council; - tax clearance certificates or equivalent for the last financial year; and - other appropriate documentary evidence demonstrating its compliance. - A Bidder that has been debarred from participating in public procurement in accordance with section 79 of the Public Procurement and Disposal of Public Assets Act, at the date of the deadline for bid submission or thereafter, shall be disqualified. |
| - To qualify for award of the Contract, Bidders shall meet the minimum qualifying criteria specified in Section 3, Evaluation and Qualification Criteria. - Bidders applying for eligibility for a margin of preference in Bid evaluation, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Bidders to be eligible for set-aside earmarked for micro, small and medium enterprises, if permitted in the Bid Data Sheet, shall supply all information to satisfy the criteria for eligibility as described in Section 3, Evaluation and Qualification Criteria. - Pre-bidding meetings maybe required. Where they are required, they shall be made mandatory. |
| - DOCUMENTS COMPRISING THE BID |
| - The Bid submitted by the Bidder shall comprise the following, in the format indicated in Section 4, Bidding Forms— - Bid Submission Form; - Bid Security or Bid Securing Declaration; - Priced Bill of Quantities or Activity Schedule; |
| - Qualification Information Form and Documents; and - any other document or information required to be completed and submitted by bidders, as specified in the BDS. |
| - BID PRICES |
| - The Contract will be an Admeasurement or Lump Sum Contract, as indicated in the Bid Data Sheet. - The Contract shall be for the whole Works, based on the— - priced Bill of Quantities submitted by the Bidder in the case of an Admeasurement Contract; or - priced Activity Schedule submitted by the Bidder in the case of a Lump Sum Contract. |
| - Bids shall cover all costs of labour, materials, equipment, overheads, profits including all associated cost for performing the works. All duties, taxes, and other levies payable by the Contractor under the Contract, shall be included in the rates, prices and total Bid price (or in the case of a lump sum contract, in the total bid price) submitted by the Bidder. |
| - CURRENCIES OF BID AND PAYMENT |
| - The unit rates and prices (or in the case of a lump sum contract, the lump sum price) shall be quoted by the Bidder and paid entirely in Malawi Kwacha. |
| - BID VALIDITY |
| Bids shall remain valid for the period specified in the BDS. |
| - BID SECURING DECLARATION |
| - The Bidder shall furnish, as part of the Bid, a Bid Securing Declaration in its original form. |
| - The format of the Bid Securing Declaration should be in accordance with the form included in Section 4, Bidding Forms. |
| - FORMAT AND SIGNING OF BID |
| - The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 3 of these Instructions to Bidders, bound with the volume containing the Bid Submission Form, and clearly marked "ORIGINAL." In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
| - The original and all copies of the Bid must be typed or written in indelible ink and signed by a person or persons duly authorised to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made must be initialled by the person or persons signing the Bid. |
| - The Bid shall contain no alterations or additions, except those as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. |
| - SEALING AND MARKING OF BIDS |
| - The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. - The inner and outer envelopes shall— be addressed to the Procuring and Disposing Entity at the address provided in the BDS; bear the name and procurement reference number of the Contract as defined in the BDS and SCC; and provide a warning not to open except in the presence of the Internal Procurement Committee and not to be opened before the specified time and date for Bid opening as defined in the BDS. - In addition to the identification required in sub-clause 9.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to clause 11. |
| - If the outer envelope is not sealed and marked as above, the Procuring and Disposing Entity will assume no responsibility for the misplacement or premature opening of the Bid. |
| - DEADLINE FOR SUBMISSION OF BIDS |
| - Bids shall be delivered to the Procuring and Disposing Entity at the address specified in the BDS no later than the time and date specified in the BDS. - The Procuring and Disposing Entity may extend the deadline for submission of Bids by issuing an amendment, in which case all rights and obligations of the Procuring and Disposing Entity and the Bidders previously subject to the original deadline will then be subject to the new deadline. |
| - LATE BIDS |
| Any Bid received by the Procuring and Disposing Entity after the deadline prescribed in the BDS will be returned unopened to the Bidder. |
| - BID OPENING AND EVALUATION |
| - The Procuring and Disposing Entity will open the Bids, in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the BDS. |
| - The Procuring and Disposing Entity will prepare minutes of the Bid opening, including the information disclosed to those present. Copies of the minutes will be made available to any Bidder who requests them. |
| - No Bid will be rejected at Bid opening except for late Bids, which will be returned unopened to the Bidder. |
| - CORRECTION OF ERRORS |
| - Bids determined to be substantially responsive will be checked by the Procuring and Disposing Entity for any arithmetic errors. - The amount stated in the Bid will be adjusted by the Procuring and Disposing Entity in accordance with the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid will be rejected, and the Bid Security or Bid Securing Declaration may be forfeited in accordance with sub-clause 7.1. |
| - PREFERENCE AND PARTICIPATION OF MICRO, SMALL AND MEDIUM ENTERPRISES |
| - If so, indicated in the BDS, domestic Bidders or other Bidders using Malawian nationals to carry out the works shall receive a margin of preference in Bid evaluation in accordance with the procedure and criteria specified in Section 3, Evaluation and Qualification criteria. - If so, indicated in the BDS, participation of micro, small and medium enterprises shall have some works set-asides for them. In addition, for some works, MSME shall receive a margin of preference in Bid evaluation in accordance with the procedures and criteria specified in Section 3, Evaluation and Qualification Criteria. |
| - AWARD CRITERIA |
| - The Procuring and Disposing Entity will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been determined to be both eligible and qualified in accordance with the provisions of Clause 2. |
| - PROCURING AND DISPOSING ENTITY’S RIGHT TO ACCEPT ANY BID AND TO REJECT ANY OR ALL BIDS |
| - The Procuring and Disposing Entity reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Procuring and Disposing Entity’s action. |
| - NOTICE OF AWARD OF THE CONTRACT, NOTIFICATION OF AWARD AND CONTRACT NEGOTIATIONS |
| - The Procuring and Disposing Entity shall publish the results of the award of contract, as required by the Public Procurement and Disposal of Public Assets Act. |
| - The Contract will incorporate all agreements between the Procuring and Disposing Entity and the successful Bidder. It will be signed by the Procuring and Disposing Entity and sent to the successful Bidder, within fourteen (14) days following the notification of award. Within fourteen (14) days of receipt, the successful Bidder will sign and date the Contract and deliver it to the Procuring and Disposing Entity. - Upon the furnishing by the successful Bidder of the Performance Security, the Procuring and Disposing Entity will, within one (1) week, notify the other Bidders that their Bids have been unsuccessful. |
| - PERFORMANCE SECURITY |
| - Within thirty (30) days after receipt of the Notice of Acceptance, the successful Bidder shall deliver to the Procuring and Disposing Entity a Performance Security in the form of a Bank Guarantee or other form acceptable to the Procuring and Disposing Entity, in the amount specified in the Special Conditions of Contract. |
| - Failure of the successful Bidder to comply with the requirements of sub-clause 15.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Bid Security. |
| - ADJUDICATOR |
| The Procuring and Disposing Entity proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Notice of Acceptance, the Procuring and Disposing Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the SCC at the request of either party. |
| - CORRUPTION AND FRAUD - The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Anti-Corruption legal framework; and - In line with the existing ant-corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in the bidding documents as part of the qualification criteria.. |

SECTION 2.  BID DATA SHEET

| INSTRUCTIONS TO BIDDERS (ITB) REFERENCE | DATA RELEVANT TO ITB |
| --- | --- |
| ITB 1.1 | The Procuring and Disposing Entity is: Roads Authority The subject of the Works is: Shrub and Grass Cutting from Lifupa Bridge - Dwambazi Bridge on M005 Road in Nkhata Bay District The procurement reference number is: RA/MAI/2025-26/T/SGR/NR/NB/52 |
| ITB 1.2 | The Intended Completion Date for the Works shall be: 45 days |
| ITB 3.1(e) | The Bidder shall submit with its Bid the following additional documents or information: |
| ITB 4.1 | The Contract is an Admeasurement Contract. |
| ITB 6.1 | Bids shall remain valid for 120 days. |
| ITB 7.1 | A Bid Securing Declaration shall be required |
| ITB 8.1 | In addition to the original of the bid, the number of copies is: 1 |
| ITB 10.1 | For clarification purposes only, the Procuring and Disposing Entity’s address is: Attention: Regional Manager Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Postal Address: P.O. Box 20050, Mzuzu 2, Malawi Tel.: +265 888 355 895 Email address: fmkandawire@ra.org.mw / ipc@ra.org.mw Deadline date for request for clarifications is: 7 days prior to the submission date |
| ITB 12.1 | The Bid opening shall take place at: Street Address: Off Road to NOCMA Name of Building: Roads Authority Floor/Room number: Town/City: Area 4, Mzuzu Date: 8th July 2026 Time: 10:00 Hrs |
| ITB 14.1 | A margin of preference shall not apply. Where a margin of preference applies, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. |
| ITB 14.2 | A margin of preference for micro, small and medium enterprises shall not apply. Where a margin of preference applies for MSME, the criteria for eligibility and the application methodology are described in Section 3 Evaluation Methodology and Criteria. The following works under this procurement have been set-aside for micro, small and medium enterprises. N/A |
| ITB 19.1 | The Adjudicator proposed by the Procuring and Disposing Entity is: The hourly fee for this proposed Adjudicator shall be: MWK50,000.00. The biographical data of the proposed Adjudicator is as attached to this Bid Data Sheet. |

SECTION 3. EVALUATION AND QUALIFICATION CRITERIA

This section, read in conjunction with Section 1, Instructions to Bidders and Section 2, Bid Data Sheet, contains all the factors, methods and criteria that the Procuring and Disposing Entity shall use to evaluate a bid and determine whether a bidder has the required qualifications. No other factors, methods or criteria shall be used.

- QUALIFICATION CRITERIA

To qualify for award of the Contract, in accordance with sub-clause 15.1 of the ITB, Bidders shall meet the minimum qualifying criteria—

(a)	average annual volume of construction work over the past 5 years:  N/A

(b)	experience as prime contractor in the construction of at least 2 works of a nature and complexity equivalent to the Works over the last 5 years (to comply with this requirement, works cited should be at least seventy (70) percent complete); N/A

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the following essential equipment: Hoes, shovels, picks, rakes, Slashers, Panga Knives, Wheelbarrows, Measuring Tapes etc;

(d)	personnel with the following qualifications and experience:

| No. | Position | General Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | 1 x Site Foreman: | 3 years with Road Foremanship Certificate | 2 |

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than MK2,000,000.00;

A consistent history of litigation or arbitration awards against the Bidder may result in disqualification.

Subcontractors’ experience and resources will not be taken into account in determining the Bidder’s compliance with the qualifying criteria.

2.	APPLICATION OF DOMESTIC PREFERENCE

If so, indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of domestic preference Bid evaluation shall provide such information, including details of ownership, certificates of registration, and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for domestic preference.

A margin of domestic preference may be awarded to established domestic contractors who are registered as Malawian contractors by the National Construction Industry Council. This margin of domestic preference is also extended to joint ventures between a foreign and such a qualifying Malawian partner provided that at least seventy-five (75) percent of the labour force to be used in the construction and supervision of the works is of Malawian nationality.

The margin of domestic preference shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by domestic contractors and joint ventures

eligible for the preference.

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the Bid amount shall be added to Bids received from contractors in Group B.

3.	PARTICIPATION BY MICRO, SMALL AND MEDIUM ENTERPRISES

If so indicated in the Bid Data Sheet, Bidders for works contracts applying for a margin of participation by micro, small and medium enterprises (MSME) in Bid evaluation shall provide such information, including details of ownership, certificates of registration, certificate of the category within the MSMEs and composition of the labour force as are necessary to confirm whether a particular supplier or group of suppliers qualifies for preference based on being a micro, small and medium enterprise.

A margin of preference may be awarded to established MSME contractors who are registered as Malawian contractors by the Construction Industry Regulatory Authority (CIRA), and Ministry of Trade.

The margin of preference for MSMEs shall be applied as follows—

After Bids have been received and reviewed by the Procuring and Disposing Entity, responsive bids shall be classified into the following groups—

Group A, namely, Bids offered by MSMEs contractors and joint ventures eligible for the preference; or

Group B, namely, Bids offered by other contractors.

For the purpose of evaluation and comparison of Bids only, an amount equal to ten (10) percent of the bid amount shall be added to bids received from contractors in Group B.

Note to Bidders: This Bid Submission Form should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.

# BID SUBMISSION FORM

Date: ………/……../……….. [insert date]

Procurement Reference No.: ………………………………………………………………………… [insert procurement reference number]

Page …………………………………………………… [insert page number] of ………………………………………………. [insert total number of pages] pages

To: ………………………………………………………………………………………………………………

……………………………………………………………………………………………………. [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that—

- We have examined and have no reservations to the Bidding Documents;

- We offer to execute the …………………………………………………………………………………………………….. [insert the name and procurement reference number of the Works] in conformity with the Bidding Documents for the Contract Price of …………………………………………………………………………………………………………………………………………………………………………………. [insert amount in numbers and words] Malawi Kwacha;

- Our bid shall be valid for a period of …………………………………………………………. [specify the number of days that the bid is valid for] calendar days from the date fixed for the bid submission;

- We have not been debarred from participation in public procurement by the Authority, in accordance with sub-clause 2.3 of the ITB;

- Our firm, its affiliates or subsidiaries, including subcontractors or suppliers for any part of the contract are not under investigation by the Anti-Corruption Bureau or any other law enforcement body in Malawi relating to participation in any public procurement tender exercise or execution of any public procurement contract relating to the purchase of goods, works and services by any Procuring and Disposing Entity;

- The names and physical addresses of the Directors of our firm are provided in the table below or we enclose a copy of our latest Audited Accounts (issued within the last twenty-four (24) months) —

| NAME | ADDRESS |
| --- | --- |

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and

- We accept the appointment of …………………………………………………………………

…………………. [insert name of adjudicator proposed in the BDS] as the Adjudicator. [or] We do not accept the appointment of ……………………………………………………………………………………………………………………… [insert name of adjudicator proposed in the BDS] as the Adjudicator, and propose instead that ………………………………………………………………………….. [insert name] be appointed as Adjudicator, whose daily fees and biographical data are attached.

Signed: …………………………………………………………………………………………………………………… [insert signature of person whose name and capacity are shown] In the capacity of ………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………….…………………

………………………………………………………….…… [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Beneficial Ownership Disclosure Form

Date: [insert date]

Procurement Reference No.: [insert procurement reference number]

Page [insert page number] of [insert total number of pages] pages

To: [insert complete name of Procuring and Disposing Entity]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 5% or more of the shares (Yes / No) | Directly or indirectly holding 5 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder.

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 5% or more of the shares

- directly or indirectly holding 5% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

- directly or indirectly, has a substantial economic interest in or receives substantial economic benefit from, a company, whether acting alone or together with other persons;

- has a significant stake in a company and on whose behalf activity of a company is conducted; or

- exercises significant control or influence over a person through a formal or informal agreement, and where such ownership, control or interest is through a trust, the trustee (s), beneficiaries, or anyone who controls the trust.

Name of the Bidder: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder: [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above:

Date signed [insert ordinal number] day of [insert month], [insert year]

Note to Bidders: Bidders shall submit a fully priced Bills of Quantities for Admeasurement Contracts or Activity Schedule for Lump Sum Contracts as provided in Section 6 of the Bidding Documents.

Each page of the Bills of Quantities or the Activity Schedule should be signed by a person with the proper authority to sign documents for the Bidder.

# Priced Schedules

# (Bills of Quantities or Activity Schedule)

# (The following tabulation shall be used when calculating final Bid Prices for works procurements)

| DESCRIPTION | TOTAL PRICE |
| --- | --- |
| 1 |  |
| 2 |  |
| Sub Total |  |
| VAT (17.5%) |  |
| PPDA Levy (1%) |  |
| TOTAL |  |

Note to Bidders: This Bid Securing Declaration should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign the Bid Securing Declaration. It should be included by the Bidder in its bid, in accordance with ITB Clause 7; except for indicated fields, no changes shall be made in this template.  Any changes made shall result to rejection of the bid.

BID SECURING DECLARATION

[The Bidder shall fill in this form in accordance with the instructions indicated.]

Date:……./………../………….. [insert date ( as day, month and year) of bid submission]

Procurement Reference No.: ……………………………… [insert number of bidding process]

Alternative No.:…………………………………………………………………………………. [insert identification No. if this is a bid for an alternative]

To: ……………………………………………………………………………………………………………… [insert complete name of Procuring and Disposing Entity]

We, the undersigned, declare that

- We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

- We accept that we will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and/or any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Government of Malawi if we are in breach of our obligation(s) under the bid conditions, because we:____

- have withdrawn our Bid during the period of Bid validity specified by us in the Bid Data Sheet;

- having been notified of the acceptance of our Bid by the Procuring and Disposing Entity during the period of Bid validity____

- fail or refuse to execute the contract, if required; or

- fail or refuse to furnish the Performance Security, in accordance with the clause 18 of the ITB; or

- accept the correction of its Bid by the Procuring and Disposing Entity, pursuant to clause 13 of the ITB.

- We understand that this Bid Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification of the name of the successful bidder; or (ii) thirty (30) days after the expiration of the Bid.

- We understand that if we are a Joint Venture, the Bid Securing Declaration must be in the name of the Joint Venture that submits the Bid.  If the Joint Venture has not been legally constituted at the time of bidding, the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent.

Signed: ………………………………………………………………………………………………  [insert signature of person whose name and capacity are shown]  In the capacity of ………………………………………………………………………………………………………………………………………………………………………………………………………………….. [insert legal capacity of person signing the Bid Securing Declaration]

Name: ……………………………………………………………………………………………………….…

…………………………………………………………………………….  [insert complete name of person signing the Bid Securing Declaration]

Duly authorized to sign the bid for and on behalf of ………………………………………………………………………………………… [insert complete name of Bidder]

Date: on …………….. day of  ………….,…………..  [insert date of signing]

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

Note to Bidders: The information to be filled in by bidders in the following pages will only be used for purposes of post-qualification or for verification of pre-qualification as provided for in Clause 2 of the Instructions to Bidder and will not form part of the Contract. Attach additional pages as necessary. If used for pre-qualification verification, the Bidder should fill in updated information only.

QUALIFICATION INFORMATION FORM

1. Constitution or legal status of Bidder: [attach copy] Place of registration: [insert certificate] Principal place of business: [insert the place of business] - Average volume of construction work performed in the previous number of years specified in Section 3: [insert details below and state average]

| Year: | NOT APPLICABLE |
| --- | --- |
| Volume: |  |

3. Work performed on works of a similar nature and volume over the last five (5) years. Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| (a) | NOT APPLICABLE |  |  |

4. Major items of Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

5. Qualifications and experience of key personnel for the Contract.

| Position | Name | Qualifications | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- | --- |
| (a) | [Attach cv and qualifications] |  |  |  |

6 Financial reports for the last financial year: balance sheet, profit and loss statement, auditors’ report, etc. Attach copies. 6b. Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of supporting documents. 7. Name, address, and telephone of banks that can provide references if contacted.

8. Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

9. Bidders should provide any additional information required in Sections 2 or 3 of the Bidding Document or to fulfil the requirements of Clause 2 of the Instructions to Bidders, as applicable. ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY DECLARATION We, _______________________ (Name of bidder) bearing the company registration number ___________________________________, hereby: 1. PLEDGE THAT: - We have read, understood, and will comply with: - the Environment Management legal framework or policies in conservation and management of the environment. - all necessary and appropriate measures to protect and manage the environment - all necessary and appropriate measures to conserve natural resources and to promote sustainable utilization of natural resources - all steps and measures necessary for ensuring that social safeguard issues including but not limited to gender, human rights, disability, Child Protection, HIV and AIDS are mainstreamed throughout all construction stages to minimize the negative impacts on the environment, social, health and safety matters 2. AGREE THAT: - In the event that our Bid is successful, we shall, within 15 days from the receipt of the Acceptance Letter comply with the requirements to produce the following environmental, social, health and safety plans as provided in Section 10:- Site Organisation Plan, Mobilisation and Construction Schedule Plan, Code of Conduct for Contractors Personnel Plan, ESHS Management Strategies and Implementation Plan. - Contract negotiations shall only commence if our plans comply with the Malawi standards on the protection and management of the environmental, social, health and safety matters. - We will automatically be suspended from being eligible for bidding in any contract with the Procuring and Disposing Entity and any other government entity for a period of twenty-four (24) months starting on the date as may be determined by the Authority if we are in breach of our obligation(s) under the bid conditions. Signed:………………………………………………………………..[insert signature of person whose name and capacity are shown] In the capacity of…………………………………………………………. [insert legal capacity of person signing the Bid] Name:………………………………………………………………………………. [insert complete name of person signing the Bid] Duly authorised to sign the bid for and on behalf of:………………………………………………………………………… [insert complete name of Bidder] Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 5. ELIGIBLE COUNTRIES

PROCUREMENT REFERENCE NUMBER: RA/MAI/2025-26/T/SGR/NR/NB/52

All countries are eligible except countries subject to the following provisions.

A country shall not be eligible if:

- as a matter of law or official regulation, the Government of the Republic of Malawi prohibits commercial relations with that country, provided that the Government is satisfied that such exclusion does not preclude effective competition for the provision of the works required; or

- by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of the Republic of Malawi prohibits any procurement of works from that country or any payments to persons or entities in that country.

SECTION 6. CORRUPTION AND FRAUD

- The Malawi Government requires that Procuring and Disposing Entities, as well as Bidders and Suppliers, participating in public procurement, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Malawi Government: - defines, for the purposes of this provision, the terms set forth below as follows— - "“coercive practices” mean practices intended at harming or threatening to harm, directly or indirectly, a person or a person’s asset, to influence that person’s participation in a procurement proceeding, or effect the execution of a procurement contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Procuring and Disposing Entity, designed to establish prices at artificial, noncompetitive levels; - "corrupt practice" has the meaning ascribed to the term by the Corrupt Practices Act of 2004; - "fraudulent practice" means a misrepresentation or omission of facts in order to influence a procurement process, the execution of a contract or avoid an obligation; and - “obstructive practice” means deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation. - will reject a recommendation for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - debar a Bidder from participation in public procurement for a specified period of time if it at any time determines that the firm has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a contract. - will cause every Bidder to acknowledge and sign Anti-Corruption Declaration in this Section under Oath, a confirmation that the bidder, its subcontractors, joint venture partners, or any other associate has not been convicted or is under investigation on corruption and fraud related cases. Failure to sign the Declaration shall lead to disqualification.

- expects Bidders to read and understand this provision; and will show acknowledgement of having read and understood the provision by signing compliance Form in this Section below:

ANTI-CORRUPTION DECLARATION FORM

We/I, _______________________ (Name of Bidder) bearing the company registration number ___________________________________, hereby:

- PLEDGE THAT:

  - We have read and understood, and will comply with all applicable laws, regulations and policies relating to anti-corruption and fraud.

  - We shall not, through any of our representatives, agents or any persons associated to     us, commit any corruption offence or breach any of the applicable laws and/or provisions. We shall not encourage any corruption elements within our business practices, activities, operations, and transactions.

  - We have not been convicted nor are we aware that we are subject of any corrupt related investigation, inquiry, or enforcement proceedings by the relevant authorities and will report of such investigation as soon as we become aware as reasonably practicable and to the extent permitted by law.

  - We shall take all measures and implement appropriate measures to ensure compliance with the Anti-Corruption Legal Framework.

  - We shall report to any relevant Authority, a public officer attempting to solicit a bribe or advantage from us, or any other person connected to us to be awarded a contract.

2. AGREE THAT:

In the event that we are in a confirmed breach of this declaration, the Procuring and Disposing Entity may disqualify the Bid, revoke or terminate the contract if awarded to us without any liability whatsoever on its part, indemnify the Procuring and Disposing Entity for any loss.

Signed: ……………………………………………………………………………. [insert signature of person whose name and capacity are shown] In the capacity of [insert legal capacity of person signing the Bid]

Name: ……………………………………………………………………………………………………….. [insert complete name of person signing the Bid]

Duly authorised to sign the bid for and on behalf of:……………………………………………………………….. [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

SECTION 7. SCHEDULE OF REQUIREMENTS

- A. Scope of Works

- B. Technical Specifications

- C. Bill of Quantities or Activity Schedule

# Section 7.  Schedule of Requirements

A. Scope of Works

## A.1 DESCRIPTION OF THE WORKS

### A.1.1 General

The Works comprise shrubs and grass cutting along Shrub and Grass Cutting from Lifupa Bridge - Dwambazi Bridge on M005 Road in Nkhata Bay District in the Northern Region.

SECTION 7B: TECHNICAL SPECIFICATIONS

## SECTION 1300	CONTRACTOR’S ESTABLISHMENT ON SITE AND GENERAL

OBLIGATIONS

PS 1303: Payment

PS 13.01:    The Contractor’s General Obligations

Add the following paragraph after the fourth paragraph (numbered as (iii):

(iv) The combined total amount of pay item 13.01(a), 13.01(b) and 13.01(c) shall not exceed 15 % of the tender sum

PS 13.04: Construction of Sign Boards………………………………………….No.

The unit of measurement shall be number of construction sign boards supplied.

The tendered rate shall include full compensation for procurement, erection and removal of construction sign boards after completion of the project.

The sign board has to comply with the particular drawing.

SECTION 1700	CLEARING AND GRUBBING

PS1701	Scope

Add the following to this Clause:

This section also includes the cutting of grass and bushes along the road to improve visibility. The grass, shrubs and bush shall be cut 50 mm to 100 mm above the ground. The width of cutting shall be 3m to 10m from the edge of the road where grass starts to grow or as directed. This scope shall also include the cutting of tree branches leaning onto the road wherever applicable.

The scope of works shall also include excavation and disposal of any debris in the road reserve

The scope of works shall also includes the treatment of anthills.

PS1703	EXECUTION OF THE WORK

(a)	Areas to Be Cleared, Grubbed and Stripped

At the end of this sub-clause add the following:

Removing topsoil too far in advance of excavation or filling operations may also cause reclearing and regrubbing.  Payment for clearing and grubbing shall be made only once.  Reclearing and regrubbing shall be at the Contractor’s own cost.

(b)	Cutting of Trees

At the end of this sub-clause add the following:

Individual trees designated in writing by the Engineer shall be left standing and uninjured.  A penalty of MK100,000.00 shall be imposed for every tree which is unnecessarily removed or damaged.  The branches of trees to be left standing shall be trimmed so as to leave a 7 m clearance above the carriageway.

PS 1704: Measurement and Payment

Add the following new pay items:

PS 17.04: Cutting and removal of tree branches............................................No.

If necessary and as instructed by the Engineer, tree branches shall be cut in sections from the top downwards. The branches to be left standing shall be trimmed so as to have a 6m clearance above carriageway. Necessary precaution shall be taken to prevent damage to structures and other private and public property. Individual trees designated in writing by the Engineer shall be left standing and uninjured.

The unit of measurement shall be number of tree branches exceeding 300mm girth cut. The girth shall be measured at the narrowest point of the tree or branch.  The tendered rate shall include full compensation for all work necessary for the cutting, removal and disposal of all material.

PS 17.07: Grass and Shrubs Cutting..........................................................Square Metre

Measurement shall be in square metres. Length shall be measured along the centre line of the road. The width shall generally be measured from the shoulder break point into the road verge as instructed by the Engineer. Excessive shrubs shall be determined case by case by the Engineer whether to include in the shrubs and grass cutting rate or to pay as a unit item under bush clearing (PS 17.08)

PS17.08: Bush Clearing..............................................................    Square Metre

Measurement shall be in square metres. The quantity shall be taken as the area in square metres within the road reserve as designated by the Engineer and cleared by manual labour in accordance with these specifications. The tendered rate shall include full compensation for all work necessary for the clearing, removal and disposal of all cleared material.

PS 17.09 Treatment of Anthills................................................................Number

Where anthill material is encountered within the road prism, the contractor shall excavate to a depth of 0.6m below existing ground level over an area as directed by the Engineer. The excavated area shall be treated with an approved pesticide and backfilled with suitable material compacted to specifications.

The rate of payment shall be the number of anthills treated. This rate shall cover the provision of labour, tools, approved pesticides, road signs and safety devices. Excavation and backfilling shall be paid for under their appropriate pay items

SECTION 2100	DRAINS

PS2103 BANKS AND DYKES

Add the following after the last paragraph

“Mitre banks, catch water banks and dykes shall be constructed using manual labour with the exception of hauling operations when haul distance in the opinion of the Engineer preclude the use of wheel barrows.

The Contractor may, however, construct certain banks and dykes using conventional plant based methods where manual methods are not feasible provided that his reasons for using these conventional methods are adequately motivated in writing and approved by the Engineer.

Work executed using manual labour will be measured and paid for separately from work carried out using conventional methods.”

PS2107	MEASUREMENT AND PAYMENT

Add the following new pay items:

“Item                                                                                                     Unit

PS 21.22	Drain Clearing:

- Line Drains

(i)	< 500 mm bottom width……..................………................…metre

(ii)	> 500 mm bottom width…....................……….................…metre

- Unlined Drains

(i)	< 1000 mm …...............................................……................…metre

(ii)	> 1000 mm …..........................................……….................…metre

This item shall include the removal of debris, sediment and other obstructions from the side drains using hand tools and labour. It shall also include the restoration of geometry and hydraulics of the side drains to ease the flow of water. Soil excavated from the drain shall be taken to spoil beyond the side drain where it shall not wash back to the side drain.

SECTION 2200:	PREFABRICATED CULVERTS

PS2201	SCOPE

This section covers also maintenance works of in-situ constructed culverts together with inlet and outlet structures.

PS2218	MEASUREMENT AND PAYMENT

Add the following new pay items

PS 22.31	Culvert Cleaning:

- Pipe Culverts

(i)	< 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

- Box Culverts

(i)	< 900 x 600 mm ….......................................……................…metre

(ii)	> 900 x 600 mm …..................................……….................…metre

- Metal Culverts (Armco or similar)

(i)	= or < 600 mm diameter……..................…......……................…metre

(ii)	> 600 mm diameter…...........................……….................…metre

The unit of measurement shall be the running metre of culvert cleaned. The tendered rate per metre shall include the cutting of vegetation at least 3m distance in both the downstream and upstream channels of the culvert. It also includes the removal of debris, sediment and other obstructions from the culvert barrel, inlet and outlet structures. If in the course of cleaning the culvert any damages to the culvert, such as broken or dislocated pipes, eroded aprons, undermining, etc., are noticed, these will be dealt with under relevant pay items and shall be treated as additional works. The rate shall also include full compensation for all the costs associated with the disposal of the excavated debris, sediments and obstructions off site.

SECTION 3300	MASS EARTHWORKS

PS3301	SCOPE

- Add the following to Clause 3301:

The scope shall also include maintenance activities of earth roads.

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 33.17	Reshaping Earth Roads .............................................................Km

The works comprise initial filling of potholes and erosion gullies with fill from road reserved or side drains followed by continuous reshaping (drain to drain) and cambering of the carriageway using hand tools and labour thereby restoring proper crown, crossfall, drainage and an even riding surface of the road.

The works shall be measured in kilometres (km) of full width of road reshaped (side drains inclusive). Payment shall include all described reshaping works within the carriageway boundaries. Mitre drains shall be paid separately under their appropriate item 21.01. Physical measurements of road length shall be recorded. Unit rates shall include full compensation for all steps necessary to comply with the above including all transport, hand tools, handling, labour, materials and all incidentals necessary to complete the work as specified.

SECTION 3400	PAVEMENT LAYERS OF GRAVEL MATERIAL

PS3407	MEASUREMENT AND PAYMENT

- Add the following new pay item

PS 34.08	Access Ramp to Adjoining Property:............................................m3

The unit of measure shall be cubic metre. The unit price paid per ramp shall be full compensation for all work required in connection with constructing the ramp, including the furnishing of all necessary labour, materials and incidentals.

SECTION 8: GENERAL CONDITIONS OF CONTRACT

| - Definitions |
| --- |
| - The following words and expressions shall have the meanings hereby assigned to them____ “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract; “Adjudicator” is the person appointed jointly by the Client and the Contractor to resolve disputes in the first instance, as provided for in clauses 18 and 19 hereunder; “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Client; “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract; “Client” means the Procuring and Disposing Entity who employs the Contractor to carry out the Works; “Compensation Events” are those defined in clause 32 hereunder; “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with clause 41; “Contract” is the Contract between the Client and the Contractor to execute, complete, and maintain the Works; “Contract Price” is the price stated in the Notification of Award and thereafter as adjusted in accordance with the provisions of the Contract; “Contractor” means the Supplier appointed under the Contract for the performance of the Works; “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring and Disposing Entity; “Days” are calendar days. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant; “Defect” is any part of the Works not completed in accordance with the Contract; “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor; “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date; “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract; “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV)), health and safety; “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works; “Initial Contract Price” is the Contract Price listed in the Client’s Notification of Award; “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order; “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works; “months” are calendar months; “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function; “Procuring and Disposing Entity” is the party who employs the Contractor to carry out the Works; “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Client and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract; “Site” is the area defined as such in the Special Conditions of Contract; “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site; “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager; “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates; “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site; “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity; “Variation” is an instruction given by the Project Manager which varies the Works; and “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Client, as defined in the Special Conditions of Contract. |
| - LANGUAGE AND LAW |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |
| - CORRUPTION AND FRAUD The Malawi Government requires that all Bidders comply with the legal framework on corrupt and fraudulent practices as outlined in Section 6 of the Bidding Document. In line with the existing Anti-Corruption law, regulations, and policy, and as provided in this clause, Bidders, including its agents, sub-contractors, sub-consultants, service providers, suppliers, and personnel are subject to the signed Anti-Corruption Declaration in Section 6, as part of the qualification criteria. - PROJECT MANAGER’S DECISIONS |
| - 4.1 Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Client and the Contractor in the role representing the Client. |
| - DELEGATION. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. However, the Client’s specific approval is required for actions detailed in SCC.. - COMMUNICATIONS |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - SUBCONTRACTING |
| - The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Client in writing. Subcontracting shall not alter the Contractor’s obligations. |
| - OTHER SUPPLIERS |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Client between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Client may modify the Schedule of Other Suppliers and shall notify the Contractor of any such modification. |
| - PERSONNEL The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract |
| - PROCURING AND DISPOSING ENTITY’S RISKS. From the Start Date until the Defects Liability Certificate has been issued, the following are Client’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to: #### use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works, or #### negligence, breach of statutory duty, or interference with any legal right by the Client or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Client or in the Client’s design, or due to war or radioactive contamination directly affecting the Republic of Malawi.. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is a Client’s risk except loss or damage due to— a Defect which existed on the Completion Date; an event occurring before the Completion Date, which was not itself a Client’s risk; or the activities of the Contractor on the Site after the Completion Date.. - CONTRACTOR’S RISKS |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |
| - INSURANCE |
| - The Contractor shall provide, in the joint names of the Client and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks— - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third-Party liability. |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Client may effect the insurance which the Contractor should have provided and recover the premiums the Client has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |
| - SITE INVESTIGATION REPORTS. The Contractor, in preparing the Bid, may rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.. - CONTRACTOR TO CONSTRUCT THE WORKS |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - THE WORKS TO BE COMPLETED BY THE INTENDED COMPLETION DATE |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| - HEALTH AND SAFETY |
| - 15.1 The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. - The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. - The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require |
| - PROTECTION OF THE ENVIRONMENT - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| - PROHIBITION OF HARMFUL CHILD LABOUR |
| - The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of eighteen (18) years shall not be employed in dangerous work. |
| - DISPUTES |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |
| - PROCEDURE FOR DISPUTES |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Client and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The Arbitration shall be conducted in accordance with the Arbitration procedure published by the institution named and, in the place, shown in the Special Conditions of Contract. - Should an Adjudicator resign or die or should the Client and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Client and the Contractor. In case of disagreement between the Client and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |
| - PROGRAM |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| - EXTENSION OF THE INTENDED COMPLETION DATE |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| - DELAYS ORDERED BY THE PROJECT MANAGER |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| - EARLY WARNING |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone in volved in the work and in carrying out any resulting instruction of the Project Manager. |
| - CORRECTION OF DEFECTS |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| - UNCORRECTED DEFECTS |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |
| - BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. OPTION 1: BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACT - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| OPTION 2: ACTIVITY SCHEDULE FOR LUMP SUM CONTRACT - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |
| - CHANGE IN THE BILL OF QUANTITIES OR ACTIVITY SCHEDULE |
| OPTION 1: CHANGES IN THE BILL OF QUANTITIES FOR ADMEASUREMENT CONTRACTS - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Client. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. OPTION 2: CHANGES IN THE ACTIVITY SCHEDULE FOR LUMP SUM CONTRACTS - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |
| - VARIATIONS |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |
| - PAYMENT FOR VARIATIONS |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| - PAYMENT CERTIFICATES |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |
| - PAYMENTS |
| - Payments shall be adjusted for deductions for advance payments and retention. The Client shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Client makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Client and shall be deemed covered by other rates and prices in the Contract. |
| - COMPENSATION EVENTS |
| - The following shall be Compensation Events: - The Client does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Client cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Client’s interests are adversely affected by the Contractor not having given early warning. |
| - CURRENCIES |
| - Payments shall only be made in Malawi Kwacha. |
| - RETENTION |
| - The Client shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Client, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| - LIQUIDATED DAMAGES |
| - The Contractor shall pay liquidated damages to the Client at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Client may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |
| - ADVANCE PAYMENT |
| - The Client shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Client. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |
| - SECURITIES |
| - The Performance Security shall be provided to the Client no later than twenty-one (21) days after receipt of the Notice of Award and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Client. The Performance Security shall be valid until a twenty-eight (28) days from the date of issue of the Certificate of Completion. |
| - DAYWORKS |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| - COST OF REPAIRS |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |
| - COMPLETION |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |
| - TAKING OVER |
| - The Client shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |
| - FINAL ACCOUNT |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - TERMINATION |
| - The Client or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following— |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Client or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Client to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Client has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under sub-clause 43.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Client may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| - PAYMENT UPON TERMINATION |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Client exceeds any payment due to the Contractor, the difference shall be a debt payable to the Client. - If the Contract is terminated for the Client’s convenience or because of a fundamental breach of Contract by the Client, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| - PROPERTY |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Client if the Contract is terminated because of the Contractor’s default. |
| - FORCE MAJEURE |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Client in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Client in writing of such condition and the cause thereof. Unless otherwise directed by the Client in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |
| - RELEASE FROM PERFORMANCE |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Client or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |

SECTION 9.  SPECIAL CONDITIONS OF CONTRACT

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC CLAUSE REFERENCE | SPECIAL CONDITIONS |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: Shrub and Grass Cutting from Lifupa Bridge - Dwambazi Bridge on M005 Road in Nkhata Bay District ; Procurement Reference No.: RA/MAI/2025-26/T/SGR/NR/NB/52 The Project Manager is: The Regional Manager - North The Works consist of: Shrubs and Grass Cutting The Site is located at: Shrub and Grass Cutting from Lifupa Bridge - Dwambazi Bridge on M005 Road in Nkhata Bay District and is defined in Drawings Nos.: N/A The Start Date shall be: 7 days from Site Possession Date The Intended Completion Date for the Works shall be: 45 days from the Start Date The Defects Liability Period shall be: N/A |
| GCC 4 | The Client’s specific approval is required for: individual Variations (GCC Clauses 29 and 30) or Compensation Events (GCC Clause 33) or Measurements (GCC Clause 28) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 7 | The Schedule of Other Suppliers is not part of the Contract |
| GCC 8.1 | The Schedule of Key Personnel is not part of the Contract |
| GCC 11 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: N/A (b) The maximum deductible for insurance of the Works, Plant and Materials is: N/A (c) The minimum cover for insurance of Equipment is: N/A (d) The maximum deductible for insurance of Equipment is: N/A (e) The minimum cover for insurance of property is: N/A (f) The maximum deductible for insurance of property is: N/A (g) The minimum cover for personal injury or death insurance is: N/A with no deductible. |
| GCC 19.2 | The hourly rate to be paid to the Adjudicator is: MWK50,000.00. Fees and types of reimbursable expenses to be paid to the Adjudicator are: MWK50,000.00 per Hour. |
| GCC 19.3 | The institution whose arbitration procedures shall be used is: the Construction Industry Regulatory Authority (CIRA) Arbitration shall take place at: Lilongwe – Malawi Engineering Institution |
| GCC 19.4 | The Appointing Authority for a replacement Adjudicator is: Malawi Engineering Institution |
| GCC 20.1 | The Contractor shall submit a revised Program for the Works within 14 days of delivery of the Notice of Acceptance. |
| GCC 20.2 | The period between Program updates is 14 days. |
| GCC 24.1 | The Defects Liability Period is: N/A |
| GCC 26.1 | This Contract is an Admeasurement Contract. |
| GCC 31.1 | The rate of interest for late payments is 2% above prevailing commercial lending rates in Malawi. |
| GCC 32.1 (a) | The Site Possession Date shall be: within seven (7) days after receipt of Notice of Acceptance. |
| GCC 34.1 | The proportion of payments retained is N/A. |
| GCC 35 | The rate per day for liquidated damages is 0.1% percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is 5% percent of the final Contract Price. |
| GCC 36.1 | The Advance Payment will be: N/A. |
| GCC 36.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 37 | The Performance Security shall be: N/A. |
| GCC 44.1 | The percentage to apply to the value of the work not completed, representing the Client’s additional cost for completing the Works, is: |

SECTION 10. CONTRACT FORMS

# Agreement

Procurement Reference No:

THIS AGREEMENT made the … day of, ………….. ,20.., between …………….…………… of ………………………… (hereinafter called the “Client”), of the one part, and …………. of ………………………… (hereinafter called the “Contractor”), of the other part:

WHEREAS the Client—

- is desirous that the Contractor execute …………………….. (hereinafter called the “Works”) and;

- has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the sum of …………  ……………………………………………………. (hereinafter called the Contract Price).

NOW THIS AGREEMENT WITNESSETH AS FOLLOWS:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

(a) the General Conditions of Contract;

(b) the Special Conditions of Contract;

(c) the Schedule of Requirements;

(d) the Bid Submission Form and the priced Activity Schedule or priced Bill of Quantities submitted by the Contractor; and

(e) the Client’s Notification to the Contractor of award of contract.

3.	In consideration of the payments to be made by the Client to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Client to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Client hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties thereto have caused this Agreement to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

for the Procuring and Disposing Entity

Name ……………………………………………..…in the capacity of ……………………….……………………….

Signature…………………………………………………………………………………………………………………………

Witness  ……………………………………………..…..Signature……………………………………………………….

For and on behalf of the Contractor

Name ………………………………………………..…. ..	in the capacity of ……………..………………………….

Signature…………………………………………………………………………………………………………………………

Witness ………………………………………………………Signature…………………………………………………….

Name: ………………………………………………….Position:………………………………………………..

Note for Bidders:  The Performance Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# PERFORMANCE BANK GUARANTEE

## PERFORMANCE BANK GUARANTEE (UNCONDITIONAL)

Date:  ……………………………………………….[insert date]

Procurement Reference No.:……………………… [insert procurement reference number]

To: ……………………………………………………………………………………………………………………

……………………………………………………………………………….. [name and address of Client]

WHEREAS …………………………………………………………………………………………….[name and address of Contractor] (hereinafter called the “Contractor”) has undertaken, in pursuance of Contract No ………….…. [number] dated ………………… [date] to execute …………………………………………………………………………………………………………………………………. [name of Contract and brief description of Works] (hereinafter called the “Contract”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognised bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE WE hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of …………………………………………………………………….. [amount of Guarantee] [amount in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ………………………………………. [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Signature and seal of the Guarantor:

Name of Bank: ………………………………………………………………………………………………………

Address: ……………………………………………………………………………………………………………….

Date: …………………………………………………………………………………………………………………...

Note to Bidders: The Advance Payment Security should be on the letterhead of the issuing Bank and should be signed by a person with the proper authority to sign documents that are binding on the Bank.

# ADVANCE PAYMENT SECURITY

Date:……../………/………… [insert date (as day, month, and year) of Advance Payment Security]

Procurement Reference No.:…………………………………. [insert Procurement Reference number]

To: ………………………………………………………………………………………………………[insert complete name of Client]

In accordance with the payment provision included in the Contract, in relation to advance payments, ……………………………………………………………………………………….. [insert complete name of Contractor] (hereinafter called the “Contractor”) shall deposit with the Client a security consisting of ……………………………………………………………. [indicate type of security], to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of …………………………………………………………………………………………………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

We, the undersigned ………………………………………………………………………… [insert complete name of Guarantor], legally domiciled in …………………………………………………… [insert full address of Guarantor] (hereinafter the “Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligor and not as surety merely, the payment to the Client on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding …………………………………………………………………………………….. [insert currency and amount of guarantee in words and figures].

This security shall remain valid and in full effect from the date of the advance payment received by the Contractor under the Contract until ………………………………………………….. [insert day and month], [insert year].

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

Name: ………………………………………………………………………………………………………………

……………………………………………………………………………….. [insert complete name of person signing the Security]

In the capacity of …………………………………………………………………………………………………. …………………………………………………………………………….[insert legal capacity of person signing the Security]

Signed:……………………………………………………………………………………………………………………………………………………………………………… [signature of person whose name and capacity are shown above]

Duly authorised to sign the Security for and on behalf of: ………………………………………………………………………………………………………………………………………………………… ……………………………..[insert complete name of the Bank]

Dated on ………………………… day of ………………………………., ………………….. [insert date of signing]

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.